## SUMMARY
PRIORITY 1 SUMMARY
REGION | PARISH | NUMBER OF SCHOOLS IN EACH PARISH | TOTAL NUMBER OF SCHOOLS | TOTAL NUMBER OF WORKS IN PROGRESS | TOTAL NUMBER OF CONTRACTS BEING MOBILSED | TOTAL NUMBER OF CONTRACTS TO BE GIVEN SITE POSSESSION | TOTAL NUMBER OF SCHOOLS COMPLETED BY TSU/ NET | TOTAL NUMBER OF WORKS TO BE DONE BY DONORS | TOTAL NUMBER OF SCHOOLS COMPLETED BY DONORS | TOTAL NUMBER OF SCHOOLS CONTRACTORS ARE ASSIGNED TO | PRELIMINARY COST ($) | CONTRACT COST($) | EXPENDITURE TO DATE ($)
1 | St. Andrew | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 308 | 0 | 5955700 | 0
| Kingston | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2 | St. Mary | 9 | 10 | 5 | 0 | 2 | 2 | 1 | 0 |  | 90000000 | 328400516 | 220880758
| St. Thomas | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| Portland | 1 |  | 1 | 0 | 0 | 0 | 0 | 0
3 | St. Ann | 35 | 60 | 32 | 0 | 0 | 5 | 0 | 0 |  | 133998150 | 5698474223.62 | 1470225468.73
| Trelawny | 25 |  | 16 | 2 | 4 | 3 | 0 | 0
4 | Westmoreland | 63 | 149 | 45 | 4 | 11 | 2 | 6 | 1 |  | 4620851697.94 | 11543060363.51 | 565728128.69
| St. James | 53 |  | 37 | 6 | 10 | 0 | 1 | 2
| Hanover | 33 |  | 20 | 3 | 10 | 0 | 1 | 0
5 | Manchester | 17 | 62 | 6 | 0 | 1 | 11 | 0 | 0 |  | 1278720777.29 | 5754021858.98 | 1228205803.71
| St. Elizabeth | 45 |  | 31 | 0 | 6 | 7 | 4 | 1
6 | St. Catherine | 14 | 14 | 12 | 0 | 2 | 0 | 0 | 0 |  | 40000000 | 476854360 | 102891488
7 | Clarendon | 11 | 11 | 7 | 1 | 0 | 3 | 0 | 0 |  | 100000000 | 1500447278.53 | 116191268.77
TOTAL |  | 307 | 307 | 212 | 16 | 46 | 34 | 13 | 4 | 308 | 6263570625.23 | 25307214300.64 | 3704122915.9
17

## REGION 1
POST-HURRICANE ASSESSMENT DATA ― IMPACT OF HURRICANE MELISSA ON SCHOOLS' INFRASTRUCTURE
No of Schools | Region | Parish | Name of School | Preliminary Cost $ | Contract Sum $ | Expenditure to Date $ | Scope of Works | PRIORITY 1. Severely Damaged - may affect school reopening. 2. Moderately Damaged - Significant repairs. School can operate while repairs are done. 3. Minor Damage - school can operate while repairs are done. | Person Responsible (TSU , NET, JSIF , DONOR) | Name of Contractor Assigned | Contractor Grade | Projected Date of Procurement for PS Approval | Contract Start Date | Contract End Date | Status | Remarks
1 | 1 | St. Andrew | Allman Hill Primary and Infant |  | 5955700 |  | Replacement of roof sheeting and boarding on Infant Block | 1 | TSU | Jamlutions Company Limited | 4 |  | 2026-02-11 | 2026-03-31 | Work Completed
1 | TOTAL |  |  | 0 | 5955700

## REGION 2
POST-HURRICANE ASSESSMENT DATA ― IMPACT OF HURRICANE MELISSA ON SCHOOLS' INFRASTRUCTURE
No of Schools | Region | Parish | Name of School | Preliminary Cost $ | Contract Sum $ | Expenditure to Date $ | Scope of Works | PRIORITY 1. Severely Damaged - may affect school reopening. 2. Moderately Damaged - Significant repairs. School can operate while repairs are done. 3. Minor Damage - school can operate while repairs are done. | Person Responsible (TSU , NET, JSIF , DONOR) | Name of Contractor Assigned | Contractor Grade | Projected Date of Procurement for PS Approval | Contract Start Date | Contract End Date | Status | Remarks
1 | 2 | Portland | Comfort Castle Primary and Infant |  | 70846600 | 33956379 | Replacement of the damaged timber roof to include electrical upgrading for the Primary Block as per Standard Building Code | 1 | NET | THLC | 2 |  | 2026-01-26 | 2026-07-25 | 80% - 99% ; work in progress | Project Percentage Completion: 90% completed Proposed Project Completion Date: 6 months June 2026 Project Status: Auditorium & Kitchen Roofing - 95% Electrical - 95% Painting - 90% Admin. & Classroom Bldg. Roofing - 95% Electrical - 85% Painting - 85% Infant Bldg. Plumbing - 25% Electrical - 25% Issues:/Challenges: Graduation and exam activities impacted works.
2 |  | St. Mary | Baxters Mountain Primary | 35000000 |  |  | Repairs to damaged Timber Roof of NOG Classroom Block as per Standard Building Code | 1 | NET |  | 2 |  |  |  | Work to Commence | Rebuild proposed as the structure which sustained damages from the hurricane is of a nog type construction. It currently houses classroom (divided into two areas) and administrative facilities. The building is also showing signs of deterioration to its walls and roof members. Based on the type of structure and its present state (structural failure) it is not recommended or considered feasible that the damages sustained to the roof be repaired. A set of our school standards have been sent to the contractor for them to revise their proposed designs and estimate for a new structure to house the current facilities. School flagged as a small school and cost for replacement did not indicate value for money. A Containerised solution is being explored and to be transferred from Chantilly (which is closing). Pavecon to assess and confirm access is not an issue by July 24, 2026. Procurement to follow up.
3 |  | St. Mary | Devon Pen Primary and Infant |  | 42219000 | 45015000 | Construction of Retaining Wall as per Standard Building Code | 1 | TSU | Macon Construction System Limited | 1 - Civil Engineering Works | Approval granted | 2026-01-16 | 2026-06-05 | Work Completed
4 |  | St. Mary | Richmond Primary and Infant |  | 30160530 | 10873580 | Repairs to Cottage used as Infant Department to include construction of a retaining wall as per Standard Building Code | 1 | TSU | Miller's Electric & Construction Limited | 2 | Approval granted | 2026-01-09 | 2026-09-04 | 51% - 60% ; work in progress | The projected end date has not been finalized - extension of time being prepared
5 |  | St. Mary | St. Mary Technical High | 55000000 |  |  | Replacement of severely damaged Sixth Form Block as per Standard Building Code | 1 | NET | Dwight Construction | 1 |  |  |  | Contractor to be given site possession | Rebuild proposed. Following the assessment, the existing fibre panel structure is not considered durable enough to justify the cost of replacing the roof. As such, roof replacement is not feasible for value for money. A new traditional building is recommended. Design & Build Contract to be executed. Designs required for approval The Scope was submitted to the Procurement Unit for disptach to Contractor by July 22, 2026
6 |  | St. Mary | Highgate Primary |  | 23202900 | 9526870 | Replacement of roof to grade one classroom block and the female sanitation block as per Standard Building Code | 1 | TSU | Art Waterproofing Ltd. | 3 | Approval granted | 2026-03-27 | 2026-09-04 | 41% - 50% ; work in progress
7 |  | St. Mary | Port Maria Primary |  | 28492960 | 14142520 | Repairs to roof of Grade 2 Classroom Block to inlude repairs to roofs of Container Buildings as per Standard Building Code | 1 | TSU | Chin's Equipment Rentals and Construction Co. Ltd. | 1 | Approval granted | 2026-01-07 | 2026-09-04 | 80% - 99% ; work in progress | The projected end date has not been finalized - extension of time being prepared
|  |  | Port Maria Primary (Special Education Unit) |  |  |  | Establishment of Special Education Unit | 1 | DONOR | [6 empty] | Digicel has indicated that the tender process is in progress & this will be presented to its Board on July 30, 2026 for approval
8 |  | St. Mary | St. Mary High |  | 39262000 | 36679100 | Replacement of damaged roofing to Music Room Building, Industrial Arts Building and Block B as per Standard Building Code | 1 | TSU | Costley's Construction | 1 | Approval granted | 2026-01-13 | 2026-09-04 | 80% - 99% ; work in progress | The projected end date has not been finalized - extension of time being prepared
9 |  | St. Mary | Retreat Primary |  | 39279430 | 25045145 | Repairs to damaged roofs of Block A, B & C as per Standard Building Code | 1 | TSU | Modern Waterproofing & Construction | 1 - Roofing | Approval granted | 2026-01-07 | 2026-09-04 | 80% - 99% ; work in progress | The projected end date has not been finalized - extension of time being prepared
10 |  | St. Mary | Wycliffe Martin High (Previously Brimmer Vale High) |  | 54937096 | 45642164 | Repairs to damaged roofing of Canteen, Storeroom, Auditorium, Guidance Department and Industrial Arts Block as per Standard Buildiing Code | 1 | TSU | Tropical Metal Products Limited | 1 - Roofing | Approval granted | 2026-01-08 | 2026-05-06 | Work Completed
10 | TOTAL |  |  | 90000000 | 328400516 | 220880758

## REGION 3
POST-HURRICANE ASSESSMENT DATA ― IMPACT OF HURRICANE MELISSA ON SCHOOLS' INFRASTRUCTURE
No of Schools | Region | Parish | Name of School | Preliminary Cost $ | Contract Sum $ | Expenditure to Date $ | Scope of Works | PRIORITY 1. Severely Damaged - may affect school reopening. 2. Moderately Damaged - Significant repairs. School can operate while repairs are done. 3. Minor Damage - school can operate while repairs are done. | Person Responsible (TSU , NET, JSIF , DONOR) | Name of Contractor Assigned | Contractor Grade | Projected Date of Procurement for PS Approval | Contract Start Date | Contract End Date | Status | Remarks
1 | 3 | St. Ann | Brown's Town Model Infant |  | 20804475.5 | 12164775.5 | Re-construction of 150mm concrete block wall boundary fence with chain-link fence on top. | 1 | TSU | Rhino Construction | 3 | Approval granted | 2026-01-20 | 2026-08-28 | 80% - 99% ; work in progress
2 |  | St. Ann | Alderton Primary and Infant |  | 23945300 | 10841080 | Roof repairs at Admin block, classroom, and cottage, security fence and electrical system. Re-sheeting and replacement of timber roof frame members and installation at ceiling Admin Block, classroom, and replacement of timber roof frame at cottage with reinforced concrete roof slab. Re-construction of security chain-link fence and electrical installation to code.. | 1 | TSU | Bruce's Development and Consultants | 3 | Approval granted | 2026-01-12 | 2026-08-28 | 61% -79% ; work in progress | Project is affected by challenges with material supply and periodic rainfall
3 |  | St. Ann | Irons Mountain Primary and Infant |  | 117280823.72 |  | Roof repairs and general repairs to facilities | 1 | NET | Dwights Construction | 1 | Approval granted | 2025-12-01 | 2026-06-06 | 21% - 40% ; work in progress | Project Percentage Completion: 33% Canteen: 12% Block A: 100 % Block B: 3% Proposed Project Completion Date: August 2026 Works done this Week: 1. Material on site, wall below canteen in progress. 2. Demolition of Block B in progress Works to be done next week: 1. Works to continue on wall below the canteen 2. Demolition of Block B to be completed Issues/Challenges: Addendum required. Certificate #1 $29,331,156.76 submitted July 14, 2026.
4 |  | St. Ann | Parry Town Primary and Infant |  | 43557994 | 29805207.25 | Damage to timber framed roofs at classroom and sanitary facilities. Re-sheeting and replacement of timber roof members and installation of ceiling and electrical installation to code.. | 1 | TSU | Archistruct Limited | 1 | Approval granted | 2026-01-20 | 2026-08-28 | 80% - 99% ; work in progress | Project is affected by challenges with material supply and periodic rainfall
5 |  | St. Ann | Edgehill School of Special Education |  | 183018111 | 37506040 | 1. An extension of 3 additional classrooms and sanitary facilities 2. Repair roof, ceiling and associated works of the Administrative Building 3. Repair roof and associated works on Home Economics Building | 1 | NET | Dutch Construction | 2 | Approval granted | 2026-05-06 | 2026-11-05 | 41% - 50% ; work in progress | This project is approx. 50% completed overall Temporary classrooms 100% Admin. Block - Roofing - 90% Ceiling - 95% Partition - 50% Electrical - 95% Painting 90% Classroom Block Ditto above Extension Fdn. Exca. - 100% Steelwork to Fdn. 100% Substructure Blockwork - 100% Substructure Col. - 100% Ground Floor Blockwork - 90% Ground Floor Columns - 90% Ground floor rendering - 20% First Floor Decking - 30%
6 |  | St. Ann | Beecher Town Primary and Infant |  | 49841903.46 |  | Damage to timber framed roofs at classroom and cottage. Re-sheeting and replacement of timber roof members and installation of ceiling of classroom and cottage with reinforced concrete roof slab and electrical installation to code. | 1 | TSU | Archistruct Limited | 1 | Approval granted | 2026-01-20 | 2026-08-28 | 61% -79% ; work in progress | Project is affected by challenges with material supply and periodic rainfall
7 |  | St. Ann | Alva Primary and Infant |  | 23845430 |  | Damage to timber framed roof at classroom block. Replacement with steel frame roof structure with ceiling and sheeting and general electrical installation and electrical installation to code. | 1 | TSU | Monna Construction Limited | 3 | Approval granted | 2026-08-28 | 2026-08-28 | 80% - 99% ; work in progress | Project is affected by challenges with material supply and periodic rainfall
8 |  | St. Ann | Bethany Primary |  | 23989333.86 | 15595758.62 | Damage to timber framed roofs at grade 5 classroom and cottage. Replacement of damage timber roofs at admin block, classroom, and cottage with reinforced concrete roof slab and electrical installation to code. | 1 | TSU | Monna Construction Limited | 3 | Approval granted | 2026-01-12 | 2026-08-28 | 80% - 99% ; work in progress | Project is affected by challenges with periodic rainfall
9 |  | St. Ann | Brown's Town Primary |  | 50869200 | 28457214 | Repairs to hurricane damaged facilities and re-construction of collapsed boundary fence. | 1 | NET | N.F Barnes Construction | 1 | Approval granted | 2025-12-14 | 2026-03-14 | 80% - 99% ; work in progress | Overall completion is approx. 90% Roof sheeting to classroom block completed and ceiling works 95%. Repairs to roof leak on other classroom blocks are still outstanding. Also approval of quotation to address issues from the fire department has been issued to the contractor. Proposed Project End Date: August 2026
10 |  | St. Ann | Cascade Primary and Infant |  | 101631568.09 |  | Replacement of roofing to Grade 1 & 2 Classroom Blocks, Student Bathrooms, Repairs to Sanitary Facilities & Security Fencing | 1 | NET | Archistruct Limited | 1 | Approval granted | 2026-03-24 | 2026-09-23 | 61% -79% ; work in progress | "Project Percentage Completion: 65% Proposed Project End Date: September 2026 Works done in the week of the current period: Plastering of ceiling and painting continued. Installation of doors complete Retaining wall painting complete Contractor received paint to complete painting activity" Works to be done is next period: 1.Receive drawings for the bathroom on building one 2. Receive the variation cost proposal. 3.Guttering to commence 4. Painting works for the Principal’s Office and Staff Room will commence Issues/ Challenges: Contract Addendum in progress. Design and Build Contract to be in place for Infant School-Certificate #1 submitted June 10, 2026 $34,895,391.82."
11 |  | St. Ann | Higgins Land Primary and Infant |  | 23988950 |  | Damage to steel framed roofs at Block A and B classroom and timber for of cottage. Replacement of sheeting and ceiling at blocks A and B. Replacement of defective timber roof at cottage with reinforced concrete roof slab and electrical installation to code. | 1 | TSU | Bruces Development | 3 | Approval granted | 2026-01-12 | 2026-08-28 | Work Completed | Project is affected by challenges with material supply and periodic rainfall
12 |  | St. Ann | Bamboo Primary |  | 74962770 | 71965706 | Roof repairs for classroom block. Replace roof of the kitchen, canteen and the lower school bathroom. | 1 | NET | Dutch Construction Limited | 1 | Approval granted | 2025-12-27 | 2026-06-25 | 80% - 99% ; work in progress | "Project Percentage Completion: 97% Proposed Project Completion Date: August 2026 Project Status: Practical completion inspection carried out on June 4, 2026. However, some amount of outstanding works remains in the kitchen. Certificate of Taking Over to be issued. Re-inspection to be carried out Issues:/Challenges: None"
13 |  | St. Ann | Free Hill Primary and Infant |  | 112979301 | 53061343.9 | Re-roofing of Grade 6 Classroom Block, Kitchen, Sanitary Facilities, Infant Department, Staff Cottage and repairs to Security Fencing | 1 | NET | N.F Barnes Construction | 1 | Approval granted | 2025-12-19 | 2026-06-17 | 80% - 99% ; work in progress | "Project Percentage Completion: 95% Proposed Project End Date: July 2026 Works done in the week of the current period : 1. Teachers' cottage in progress 2. Timber Information Building in progress Works to be done is next period: TBD Issues/ Challenges: IT Room, not operational. outstanding work required. Continuous moulding in the canteen(Contractor advised) Variation #1 approved for $8,685,732.50 Certificate #2 $3,833,545.90 submitted May 8, 2026 PAID"" Taking Over Certificate pending."
14 |  | St. Ann | Discovery Bay Primary and Infant |  | 37663416 |  | Damage to timber framed roofs at infant department and computer lab and steel framed roof at primary department. Replacement of timber framed roofs at Infant Department and Computer Lab with reinforced concrete roof slab and re-sheeting steel framed roof at primary department and electrical installation to code. | 1 | TSU | Modern Waterproofing | 3 | Approval granted | 2026-01-12 | 2026-08-28 | 80% - 99% ; work in progress | Project is affected by challenges with material supply and periodic rainfall
15 |  | St. Ann | Hoolebury Primary and Infant |  | 69323475.45 | 8768015 | Damaged to timber framed roofs at classroom Block B, Canteen and Cottage and waterproofing membrane and windows at classroom Block A. Replacement of timber roofs at classroom Block B, Canteen and Cottage with reinforced concrete roof slab. Replacement of Waterproofing at Block A and windows and electrical installation to code. | 1 | TSU | Costley's Construction | 1 | Approval granted | 2026-01-05 | 2026-08-31 | 61% -79% ; work in progress | Project is affected by challenges with material supply and periodic rainfall
16 |  | St. Ann | Keith Primary and Infant |  | 28750300 | 8791914 | Damaged to timber roofs at classroom block B and canteen. Replacement of timber roof frame with metal- re-sheeting, ceiling and electrical installation to code. | 1 | TSU | Modern Waterproofing | 3 | Approval granted | 2026-01-12 | 2026-08-07 | 80% - 99% ; work in progress | Project is affected by challenges with material supply and periodic rainfall
17 |  | St. Ann | Lime Hall Primary and Infant | 93898500 |  |  | Repairs to roof and fence | 1 | NET | Archistruct Limited | 1 |  | 2025-12-19 |  | 21% - 40% ; work in progress | Project Percentage Completion: 30% Grade 1:50% Grade 2&3:50% Main Building: 50% Cottage:0% Fencing:0% Proposed Project Completion Date: TBD Project Status Works done in the week of the current period: Roof sheeting and ceiling in progress Works to be done is next period: Roof work to commence and be completed Issues:/Challenges: No Contract in place, Contractor is required to submit updated BQ.
18 |  | St. Ann | Lime Tree Gardens Primary and Infant |  | 69528200 |  | Damage to metal framed classroom blocks A and B. Re-sheeting, ceiling and electrical installation at Blocks A and B and electrical installation to code. | 1 | TSU | Archistruct Limited | 1 | Approval granted | 2026-01-20 | 2026-08-07 | Work Completed | Project is affected by challenges periodic rainfall
19 |  | St. Ann | Philadelphia Primary and Infant |  | 24049987 | 7333449.5 | Damaged to timber framed roof at classroom block and canteen. Replacement of timber roof frame with metal frame roof structure, re-sheeting, ceiling and electrical installation to code and electrical installation to code. | 1 | TSU | Modern Waterproofing | 3 | Approval granted | 2026-01-12 | 2026-08-21 | 80% - 99% ; work in progress | Project is affected by challenges with material supply and periodic rainfall
20 |  | St. Ann | Retirement Primary |  | 56883900 | 34568338 | Re-roofing of Classroom Block and Admin Department | 1 | NET | Dutch Construction | 2 | Approval granted | 2026-01-31 | 2026-07-30 | 80% - 99% ; work in progress | Project Percentage Completion: 80% Proposed Project Completion Date: August 2026 Project Status: Re-roofing of classroom and admin. Block done Issues:/Challenges: Variation No. 1 submitted, awaiting payment to complete
21 |  | St. Ann | Runaway Bay Primary and Infant |  | 33427651.7 | 7146092 | Damaged to timber framed roof at grade 5,6 and Special Ed. Classroom blocks and damage to section chain-link boundary fence. Replacement of timber roof at grades 5 and Special Ed. with reinforced concrete roof slab to code. Re-sheeting of timber roof at grade 6 block. Replace sections of chain-link fence with block wall and electrical installation to code. | 1 | TSU | Costley's Construction | 1 | Approval granted | 2026-01-05 | 2026-08-14 | Work Completed | Project is affected by challenges of periodic rainfall
22 |  | Trelawny | Falmouth Primary |  | 58025200 | 20551455.85 | Repair of roof of the administrative block and Grade 5 classrooms . | 1 | NET | ECJ | 2 | Approval granted | Feb 13, 1016 | 2026-08-12 | 61% -79% ; work in progress | """Project Percentage Completion: 65% Auditorium: 70% Canteen:90% Bathroom Block: 80% Sickbay:65% Chain-link Fencing:0% Proposed Project End Date: August 2026 Works done in the week of the current period: 1.Sick Bay: Tiling commence, wall rendering in progress 2. Patching of main building membrane complete 3. Bathroom finishes continue 4. Partition installation commenced 5. Auditorium: Walls painted 6. Canteen: Painting 90% Cert #2 $3,492,996.50 submitted May 22, 2026, paid June 5, 2026. Works to be done is next period: 1. Auditorium: complete painting 2. Bathroom finishes to be complete 3. Windows to be installed in auditorium 4. Partition installation to be complete Issues/ Challenges: Certificate #3 submitted for payment "
23 |  | St. Ann | Servite Primary |  | 22878672.3 | 17903244 | Damaged to timber framed roof at Admin, grade 5 blocks and canteen. Replacement of timber roof at Admin and grade 5 with reinforced concrete roof slab. Variation being prepared for approval for replacement of timber roof at canteen with reinforced concrete roof slab and electrical installation to code. | 1 | TSU | Modern Waterproofing | 3 | Approval granted | 2026-01-12 | 2026-08-14 | 80% - 99% ; work in progress | Project is affected by challenges of periodic rainfall and variation in scope of work
24 |  | St. Ann | St. Christopher School for the Deaf |  | 250732010.11 | 58270878.86 | Replacement of roofs to Classroom Blocks and Administration Department and Dormitory. Geeral repairs to facilities | 1 | NET | N.F Barnes Construction | 1 | Approval Granted | 2025-12-13 | 2026-06-11 | 61% -79% ; work in progress | Project Percentage Completion: 68% Proposed Project Completion Date: August 2026 Project Status: Works are being carried out on all 7 buildings slated for restoration. The contractor is requesting hand over of the Sagicor building on March 25, 2026. Inspection carried out to the Sagicor Building on April 28, 2026 found an excessive amount of outstanding works hence a reinspection will be required. Work has now started on the Teacher's Cottage and Block C. Erection of roof framing and construction of stiffeners and lintels are being carried out on Block D while painting, ceiling works and completion of roof to block B is in progress. Demolition of roof to block E is now in progress. Issues:/Challenges: The repair work to nogg walls of Block E may require a re-build instead of repair, Hence the contractor was asked to provide a quotation to carry out re-build.
25 |  | St. Ann | Sturge Town Primary |  | 74973800 | 52755927.5 | Re-roofing of Classroom Blocks and Administrative Department | 1 | NET | Dutch Construction | 2 | Approval Granted | 2025-12-29 | 2026-06-27 | Work Completed | Project Percentage Completion: 100% Proposed Project Completion Date: Project Status: All works under the contract have been completed. Only items of Defects are now to be carried out. Taking Over Certificate issued July 13, 2026 Issues:/Challenges: None
26 |  | St. Ann | Waltham Abbey Primary and Infant |  | 58533650 | 21462264.5 | Re-roofing of Classroom Blocks, Upgrading of electrical and Water Supply System | 1 | NET | ECJ | 3 | Approval Granted | 2026-01-05 | 2026-05-05 | 80% - 99% ; work in progress | Project Percentage Completion: 87% Proposed Project Completion Date: August 2026 Project Status: project is now approximately 80% overall with works currently being carried to the roof of two floor classroom block. Infant school: Roofing - 100% Ceiling - 95% Painting - 95% Toilet Block: Roofing - 98% Ceiling - 95% Painting - 90% Plumbing - 95% Classroom Block: Roofing - 100% Partitioning - 50% Painting - 90% Two Floor Classroom Block: Roofing - 100% Ceiling - 90% Painting - 70% Electrical - 50% Windows - 0% Issues:/Challenges: None"
27 |  | St. Ann | Watt Town Primary and Infant |  | 23995475.9 |  | Damaged to timber framed roof at Grade 1 Classroom Block, Infant Department and Administrative Department. Replacement of timber roof sheeting and ceiling at Infant Department. Replacement of sections of roofs at Grade1 and Admin Department and electrical installation to code. | 1 | TSU | Rhino Construction | 3 | Approval granted | 2026-01-20 | 2026-08-14 | 80% - 99% ; work in progress | Project is affected by challenges with material supply and periodic rainfall
28 |  | Trelawny | Albert Town Primary and Infant |  | 124717745 | 72926076.68 | Re-roofing of Classroom Blocks, Infant Department and upgrading of Electrical System | 1 | NET | Build-rite Construction | 1 | Approval granted | 2026-04-16 | 2026-10-15 | 61% -79% ; work in progress | Project Completion: 65% Project Status: Work ongoing
29 |  | Trelawny | Clark's Town Primary |  | 36213580 |  | Re-roofing of Grade 4 Classroom Block and renovation of Teacher Cottage | 1 | NET | Yardworks Construction | 1 |  |  |  | Work to Commence | Commencement letter was issued to the contractor 29/12/2025 The contract duration is 8 months. Contractor indicated work will commence August 7, 2026
30 |  | Trelawny | Granville Primary and Infant | 24232150 |  |  | Re-roofing of existing Classroom Blocks | 1 | NET | Marshall Construction | 1 |  |  |  | Contractor to be given site possession | Project re-tendered and new contractor in place
31 |  | Trelawny | Hague Primary and Infant |  | 216672653.33 |  | Re-roofing of Grade's 3, 4 & 5 Classroom Block to include Stairway, Linkway and Canteen Facility | 1 | NET | Rogers Land Development | 1 |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 0% completed Proposed Project Completion Date: Project Status: Contract documents to be prepared. Issues:/Challenges:
32 |  | Trelawny | Hampden Primary and Infant |  |  |  | Re-roofing of both Classroom Block Buildings, Infant School and Administrative Department, Water proofing to the bathroom block and general repairs | 1 | NET | Diverse Services and Construction Limited | 1 |  |  |  | Contractor to be given site possession | Project Percentage Completion: 0% Proposed Project Completion Date: TBD Project Status: Project was re-assigned to a contractor. Issues:/Challenges: None
33 |  | Trelawny | Hastings Primary and Infant |  | 39848000 | 5977200 | Re-roofing of Primary and Infant Department, Replacement of existing Drywall partitions for classrooms | 1 | NET | Marshall Construction | 1 | Approval granted | 2026-04-08 | 2026-10-07 | 51% - 60% ; work in progress | Project Percentage Completion: 60% Proposed Project Completion Date: The Infant Department and Primary School (August 31, 2026) & Grade 6 & Guidance Office (September 30, 2026). Project Status: Work remains ongoing. Issues:/Challenges: None
34 |  | Trelawny | First Hill Primary and Infant |  | 49430601.46 | 21650003.45 | Damaged to timber roof at student bathroom, cottage and security fencing. Replacement of timber roof with reinforced concrete roof slab to code. Replacement of chain-link security fencing and electrical installation to code. | 1 | TSU | Odel Allen | 2 | Approval granted | 2026-01-20 | 2026-08-21 | 80% - 99% ; work in progress | Project is affected by challenges of periodic rainfall
35 |  | Trelawny | Sawyers Primary and Infant |  | 21865193.5 | 2560524.45 | Damaged timber roof at student bathroom, cottage and security fencing. Replacement of timber roof with reinforced concrete roof slab to code. Replacement of chain-link security fencing. | 1 | TSU | Cambridge Trading Limited | 2 | Approval granted | 2026-01-20 | 2026-08-14 | 80% - 99% ; work in progress | Project is affected by challenges of periodic rainfall
36 |  | Trelawny | Stewart Town Primary and Infant |  | 46121800 | 22973985 | 1. Classrooms to be enclosed by erecting block wall along open space 2. Additional anchorage and minor repairs to roof | 1 | NET | ECJ | 2 | Approval Granted | 2026-02-04 | 2026-08-03 | 21% - 40% ; work in progress | "Project Percentage Completion: 40% Block wall installation- 50% Block wall rendering - 0% Block wall painting - 0% Restoration of walkway covering - 100% Minor repairs and reinforcement to roof - 0% Proposed Project Completion Date: August 2026 Issues:/Challenges: Work has halted as a Contract Addendum is being resolved to ensure payments can be made going forward. Progress completion will be adjusted upon confirmation of new scope."
37 |  | Trelawny | Ulster Spring Primary and Infant | 15867500 | 149010053.5 |  | Construction of gabion retaining wall, construction of perimeter fencing, and upgrading of the electrical system. Installation of waterproof membrane to Infant Department | 1 | NET | Diverse Services and Construction Limited | 1 |  |  |  | Contractor to be given site possession
38 |  | Trelawny | Bounty Hall Primary and Infant |  | 29521879.94 | 4789500 | Damaged timber roof at Principals Cottage, waterproofing membrane and windows at Classroom Block. Replacement of timber roof at cottage with reinforced concrete roof slab to code. Waterproofing of roof slab and replacement of windows . General electrical installation. | 1 | TSU | Brentwood Construction | 1 | Approval granted |  | 2026-08-14 | 61% -79% ; work in progress | Project is affected by challenges with material supply, periodic rainfall and logistics challenges with contractor
39 |  | Trelawny | Daniel Town Primary and Infant |  | 50801803.46 |  | Damage to metal framed classroom block, timber framed roof at student bathroom and cottage. Replacement of sheeting and ceiling at classroom block and student bathroom. Replacement of timber roof at cottage with reinforced concrete roof slab and electrical installation to code. | 1 | TSU | Odel Allen | 2 | Approval granted | 2026-01-20 | 2026-08-14 | 80% - 99% ; work in progress | Project is affected by challenges of periodic rainfall
40 |  | Trelawny | Salt Marsh Primary and Infant |  | 52927356.5 | 26390214.75 | Damaged to timber roof at classroom blocks A,B, Infant Department, cottage and security fence. Replacement of sheeting and ceiling at blocks A,B and Infant Department. Replacement of timber roof at cottage with reinforced concrete roof slab to code. Replacement of chain-link security fencing and electrical installation to code.. | 1 | TSU | Odel Allen | 2 | Approval granted | 2026-01-20 | 2026-08-14 | 80% - 99% ; work in progress | Project is affected by challenges of periodic rainfall
41 |  | Trelawny | Waldensia Primary and Infant |  | 34193350 | 31751407.19 | Re-roofing of Classroom Blocks to include Pest Control Treatment | 1 | NET | DAWAFA | 3 | Approval Granted | 2025-12-18 | 2026-02-16 | Work Completed | "Project Percentage Completion: 100% Proposed Project Completion Date: February 2026 Project Status: Taking Over Inspection Requested by the Contractor. A Site Visit is to be scheduled Issues:/Challenges: Retaining Wall Justification sent May 28, 2026, to procurement for processing "
42 |  | Trelawny | Unity Primary |  | 72229480 | 43191706.4 | Re-roofing and General Repairs to Classroom Blocks to include reinforcement of Security Fencing | 1 | NET | Marshalls | 1 | Approval Granted | 2026-04-16 | 2026-10-16 | 80% - 99% ; work in progress | Project Percentage Completion: 95% Project Status: Additional work to be addressed. Proposed Project Completion Date: August 2026 Issues:/Challenges: None
43 |  | Trelawny | Wakefield Primary and Infant |  | 70428859.96 | 31931516.49 | Damaged to timber roof at Admin, classroom blocks A,B and cottage. Replacement of sheeting and ceiling at Admin, blocks A,B. Replacement of timber roof at cottage with reinforced concrete roof slab and electrical installation to code. | 1 | TSU | Odel Allen | 2 | Approval granted | 2026-01-20 | 2026-08-21 | 80% - 99% ; work in progress | Project is affected by challenges of periodic rainfall
44 |  | Trelawny | Warsop Primary |  | 135529250 | 36634332.5 | Construction of Security Fencing and repairs to facilities | 1 | NET | Skymar Construction | 1 | Approval granted | 2026-03-12 | 2026-09-11 | 41% - 50% ; work in progress | "Project Percentage Completion: 50% Infant Department - 50% Multi - Purpose Building - 50% Canteen - 60% Chain-link Fence - Material on site Proposed Project Completion Date: August 31, 2026 Works done this week: Canteen Membrane installed Works to be done next week: Comments/Issues:/Challenges: Roofing materials not present onsite to carryout works."
45 |  | Trelawny | Wilson's Run Primary and Infant |  | 82130640 | 20978250 | Repairs to Cottages to include Upgrading of Electrical System | 1 | NET | Skymar Construction | 1 | Approval granted | 2026-03-12 | 2026-09-11 | 61% -79% ; work in progress | "Project Percentage Completion: 70% Infant Department - 50% Main Building - 50% Chain-link Fence - 100% Waterproofing - 100% Proposed Project Completion Date: August 31, 2026 Comments/Issues:/Challenges: Materials not present onsite to carryout works."
46 |  | St. Ann | St. Hilda's Diocesan High |  | 82061065 |  | The scope of works scheduled for restoration includes: Water Tank (Replace Roof), Principal's Cottage, Grade 7 Block and the Chemistry lab | 1 | NET | Morris Hill Limited | 1 |  | 2026-01-12 |  | 20% & Below ; work in progress | "Project Percentage Completion: 10% Proposed Project Completion Date: TBD Project Status: Teacher's Cottage 1. Place roof Sheeting 95% 2. Replace ceiling 100% 3. Tiling 10% 4. Electrical 0% 5. Plumbing Fixtures 0% 6. Kitchen Cupboards 0% Science Lab 1. Replace Roof 0% Issues:/Challenges: Contractor has not yet been given access to the Science Lab to commence work there."
47 |  | St. Ann | Aabuthnott Gallimore High |  | 45759402 | 31670452 | Damage to blocks B and C waterproofing membrane, sections of timber roof at block A, windows at block D and security fencing. Waterproofing to blocks B and C. Replacement of timber roof at section block A with reinforced concrete roof slab to code. Replacement of windows at Block D and construction of chain-link security fence and electrical installation to code. | 1 | TSU | Brentwood Construction | 1 | Approval granted | 2026-01-20 | 2026-08-14 | 80% - 99% ; work in progress | Project is affected by challenges of periodic rainfall
48 |  | St. Ann | Aboukir High |  | 41901715.9 | 13389310.56 | Damaged Admin Building, Foods Lab and canteen. Replacement of sheeting on metal roof frame and ceiling at Foods Lab and canteen and electrical installation to code. | 1 | TSU | Brentwood Construction | 1 | Approval granted | 2026-01-05 | 2026-08-07 | 51% - 60% ; work in progress | Project is affected by challenges of periodic rainfall and variation in scope of work
49 |  | St. Ann | Brown's Town High |  | 106986094 | 16652929.05 | 1. Replacement of existing roof sheeting to classroom block 2. Replacement of ceiling to existing classroom block 3. Replacement of Guttering to roofs 4. Repair of leaks to roofs | 1 | NET | Brentwood Construction | 1 | 2025-12-19 | 2026-01-28 | 2026-06-29 | 21% - 40% ; work in progress | "Project Percentage Completion: 30% Block A: 60% Block B and C window replacement: 0% Math Block Roof Repairs: 0% Auditorium Roof Repairs: 100% Greenhouse Replacement:0% Tuck Shop Roof Repairs: 100% Broiler and Layer Unit Roof Repair: 20% Fencing: 100% Proposed Project End Date: August 2026 Works done in the week of the current period : Farm: Concrete posts being cast for power supply Works to be done is next period : 1. Variation rates to be reviewed 2. Block A: Work to restart (roof, partitions) 3. Materials to be acquired for Math Room 4. Claim to be reviewed for Certificate preparation. Issues/ Challenges: Addendum to the Contract Required. Certificate #1 $29,331,156.76 prepared June 19, 2026."
50 |  | St. Ann | Discovery Bay High |  | 83301114.04 |  | Damaged to resource building used by Primary Department, Block B metal frame roof and chain-link fencing. Replacement of sheeting and ceiling to section of metal frame roof at Block B. Installation of chain-link fencing and electrical installation to code. | 1 | TSU | Costley's Construction | 1 | Approval granted | 2026-01-15 | 2026-08-28 | 21% - 40% ; work in progress | Project is affected by challenges of material supply, periodic rainfall and variation in scope of work
51 |  | St. Ann | Ferncourt High |  | 260145244.8 | 86313544.26 | Roof repairs to buildings, teachers’ cottages and poultry house. General repairs to facilities | 1 | NET | Skymar Construction | 1 | Approval granted | 2026-04-08 | 2026-10-07 | 41% - 50% ; work in progress | Project Percentage Completion: 47% Farming Area- 0% Auditorium - 100% Teachers' Cottage - 95% Principal's Cottage - 0% Sharon Kelly Block-0% Aubyn Haye Block-0% Oswald Fisher Block- 80% Ethyl Mullings Block-80% Graphics & Automation Building- 70% Timber Structure – Seventh Grade Block - 30% Curphey Hall Nursing Building- Design and Build Retaining Wall- 10% Fencing-0% Proposed Project End Date: July 20, 2026 Works done in the week of the current period : minor clean up 1. Teachers cottage 95% Complete 2. Graphics Building: nil 3. Grade 7 Block work continues 4. Class room 1: Ceiling/Roof Repairs continue 90% Complete Works to be done is next period : 1. :Minor finished required in teachers cottages 2. Graphic Building : Floor Finish and windows outstanding 3. Grade 7: Block work continue 4. Retaining Wall: Foundation work to commence 5. Class room 1: Ceiling/Roof Repairs continue Issues/ Challenges: Awaiting Addendum . Certificate #1 86,313,544.26 PAID
52 |  | St. Ann | Walkerswood Academy |  | 23992645 | 5682500 | Damaged to metal frame classroom blocks A, B and timber roof at Admin. Replacement of sheeting ceiling and block A and B and Admin and electrical installation to code. | 1 | TSU | Cambridge Trading Limited | 2 | Approval granted | 2026-01-20 | 2026-08-07 | 80% - 99% ; work in progress | Project is affected by challenges of periodic rainfall
53 |  | Trelawny | Cedric Titus High |  | 32017700 |  | Repairs to existing Teachers Cottages to include Upgrading of Electrical System | 1 | NET | Skymar | 1 | Approval granted | 2026-01-29 | 2026-07-28 | Work Completed | Project Percentage Completion: 100% Project Status: A taking-over certificate was issued to the contractor on July 13, 2026. Proposed Project Completion Date: Issues:/Challenges:
54 |  | Trelawny | Troy High |  | 13659120 |  | Upgrading of Water Supply and Catchment System | 1 | NET | J. Neil Construction | 3 | Approval granted | 2026-06-19 | 2026-09-18 | Work Completed | Project Percentage Completion: 100% Rainwater Installation - 100% Classroom Partition - 100% Window - 100% Chain-link Fence - 100% Actual Project Completion Date: June 31, 2026 Works done this week: Works to be done next week: Comments/Issues:/Challenges: Contract has been issued. Claim to be processed.
55 |  | Trelawny | Westwood High |  | 389223204.82 | 88710079.45 | "Construction of reinforced concrete slabs for the Teacher's Cottages, Visitors Area, Concrete water tanks Replacement of timber roof for Classrooms and TD Building Replacement of sheeting for Auditorium Renovation of Principal's Cottage" | 1 | NET | Pavecon Ltd. | 1 | Approval granted | 2026-02-19 | 2026-08-18 | 41% - 50% ; work in progress | "Project Percentage Completion: 50% Reroofing four classrooms - 20% Reroofing TD Building - 70% Reroofing auditorium - 100% Reroofing cottages - 70% Renovation of cottages - 30% Reroofing visitors area/hostel/6th form - 70% Restoration of Nurses station - 80% Renovation of Principal's Quarters - 50% Covering of water tanks - 20% Proposed Project Completion Date: August 2026 Issues:/Challenges: Contractor has been assigned a significant number of projects with several outstanding payments disrupting cash flow and slowing activity at several sites
56 |  | Trelawny | William Knibb Memorial High |  | 478912048.12 | 186579126.44 | Re-sheeting of classroom blocks, gazebo, chicken house, and construction of fencing | 1 | NET | Archistruct Limited | 1 | Approval granted | 2026-03-12 | 2026-09-11 | 80% - 99% ; work in progress | Project Percentage Completion: 82% Project Status: Ceiling works remain in progress across all designated areas, including the installation, taping, plastering, and painting of Plycem ceiling boards. Construction activities at the gazebo are ongoing, and works at the Teachers' Cottage continue to be carried out during this reporting period. Proposed Project Completion Date: August 15, 2026. Work Scheduled for Next Period: Commence the remaining painting works and complete works on the Teachers' Cottages. Issues:/Challenges:
57 |  | Trelawny | Holland High |  | 458017973.2 | 45801797.32 | Repairs to the roofing and ceiling on all blocks to include the administrative building, labs, staff room and repairs to the poultry house | 1 | NET | Buildrite | 1 | Approval granted | 2026-06-11 | 2026-12-10 | Work to Commence | Project Percentage Completion: 0% Proposed Project Completion Date: TBD Project Status: Work to commence on August 5, 2026. Mobilisation is paid. Issues:/Challenges:
58 |  | St. Ann | Marcus Garvey Technical (St. Ann's Bay) |  | 122665651 | 44151028.59 | Renovation to Industrial Arts Department and Poultry House | 1 | NET | N.F Barnes Construction | 1 | Approval granted | 2026-01-09 | 2026-06-30 | 80% - 99% ; work in progress | Project Percentage Completion: 95% Proposed Project Completion Date: August 2026 Project Status: All work under the contract for this project is now completed. Taking Over Inspection was carried out on July 22, 2026, and the Certificate is to be issued Issues:/Challenges:
|  |  | Marcus Garvey Technical (Mansfield) |  | 31854000 |  | Damaged to waterproofing membrane at Blocks A,B and C and chain-link fence. Replacement of waterproofing membrane to Blocks A, B and C. Installation of chain-link fencing. | 1 | TSU | Costley's Construction | 1 | Approval granted | 2026-01-05 | 2026-08-07 | Work Completed | Project is affected by challenges of periodic rainfall
57 |  | Trelawny | Muschett High |  | 262541050 |  | Roofing repairs to multiple buildings to include the admin department, water proofing of the concrete slabs, renovation to the teachers cottages and allied health centre | 1 | NET | Skymar Construction | 1 | Approval granted | 2026-02-12 | 2026-08-11 | 51% - 60% ; work in progress | Project Percentage Completion: 55% Proposed Project Completion Date: TBD Project Status: Work is ongoing Issues:/Challenges: None
[7 empty] | Installation of water harvesting & sanitation, water storage and pumps | 1 | DONOR | UNICEF
60 |  | St. Ann | Brown's Town Community College - Main Campus |  | 394313050 | 132571279.67 | Roof repairs including modification of roof to slab. Electrical work and general repairs to facilities | 1 | NET | Morris Hill Limited | 1 | Approval granted | 2026-01-26 | 2026-07-25 | 41% - 50% ; work in progress | "Project Percentage Completion: 50% Proposed Project Completion Date: TBD Project Status: Work is currently being carried out to the following buildings: N1 Building 1. Replace roof 100% 2. Painting 90% Swaby Building 1. Replace Roof 100% 2. Electrical 95% 3. Painting 90% Canteen 1. Replace Roof 100% 2. Painting 80% Arts Building 1. Replace Roof 100% 2. Painting 90% 3. Electrical 90% Computer Building 1. Replace roof 95% 2. Electrical 0% 2. Painting 0% Student's Affairs Building 1. Replace roof 95% 2. Electrical 0% 3. Painting 0% Issues:/Challenges: "
|  |  | Brown's Town Community College - Technical Campus |  |  |  |  | 1 | NET |  | 1 |  |  |  | 41% - 50% ; work in progress
60 | TOTAL |  |  | 133998150 | 5698474223.62 | 1470225468.73

## REGION 4
POST-HURRICANE ASSESSMENT DATA ― IMPACT OF HURRICANE MELISSA ON SCHOOLS' INFRASTRUCTURE
No of Schools | Region | Parish | Name of School | Preliminary Cost $ | Contract Sum $ | Expenditure to Date $ | Scope of Works | PRIORITY 1. Severely Damaged - may affect school reopening. 2. Moderately Damaged - Significant repairs. School can operate while repairs are done. 3. Minor Damage - school can operate while repairs are done. | Person Responsible (TSU , NET, JSIF , DONOR) | Name of Contractor Assigned | Contractor Grade | Projected Date of Procurement for PS Approval | Contract Start Date | Contract End Date | Status | Remarks
1 | 4 | St. James | Corinaldi Avenue Primary |  | 104263300 | 36721109 | Repairs to roofs, ceiling and gutters for Grades 2, 3 and 4 buildings to be replaced. Repairs to electrical system, water storage facility and security post as per Standard Building Code | 1 | NET | Brothers Concept | 1 | Approval granted | 2026-04-23 | 2026-10-22 | 61% -79% ; work in progress | Project Percentage Completion: 65% Proposed Project Completion Date: August 28, 2026 Project Status: Project on Track Issues:/Challenges: Funding
2 |  | St. James | Cornwall College | 356426567.5 |  |  | Repairs to lower school library, staffroom, classroom and science lab and roof. Repairs to upper school science building, staffroom, Grades 10 & 11 buildings. Roof repairs to Auditorium & Canteen Building. Fencing, repairs to block wall near the playfield. Replacement of damage windows and doors as per Standard Building Code | 1 | NET | Brothers Concept | 1 |  |  |  | 21% - 40% ; work in progress | Project Percentage Completion: 40% Proposed Project Completion Date: November 2026 Project Status: Issues:/Challenges: Awaiting payments for other projects and issuance of contract for this project.
3 |  | St. James | Green Pond High | 100000000 |  |  | Repairs to sewer system, windows and doors and canteen. Repairs to bathrooms and corridor roofing. Roof, ceiling & gutter repairs, windows, electrical, repairs to holding area, security post repairs, sanitation, water storage, as per Standard Building Code | 1 | DONOR | [5 empty] | 20% & Below ; work in progress | Donor - Sagicor
4 |  | St. James | Montego Bay High |  | 114336600 |  | Repairs to roof on old stone building and a timber-framed building as per Standard Building Code | 1 | NET | RSJ | 2 | Approval granted |  |  | 41% - 50% ; work in progress | Project Percentage Completion: 44% Proposed Project Completion Date: October 15, 2026 Project Status: Works ongoing Issues:/Challenges:
5 |  | St. James | Montego Bay Infant |  | 112303500 |  | Roof of Principal office, canteen and Staffroom, lower class building and auditorium roofs are damaged. Installation of windows and doors, and repairs to stonewall boundary as per Standard Building Code | 1 | NET | Construction 365 Company Limited | 1 | Approval granted |  |  | 80% - 99% ; work in progress | Project Percentage Completion: 80% Proposed Project Completion Date: November 21, 2026 Project Status: Works ongoing Issues:/Challenges:
6 |  | St. James | Mount Salem Primary and Infant |  | 147721875 |  | Roof repairs to main classroom block as per Standard Building Code | 1 | NET | C&D Construction | 1 |  |  |  | Work to Commence | Contractor will mobilise to commence work
7 |  | St. James | St. James High |  | 132893000 |  | Roof repairs on admin building, electrical repairs/supply, windows and doors as per Standard Building Code | 1 | NET | RSJ Construction Company Limited | 2 | Approval granted |  |  | 41% - 50% ; work in progress | Project Percentage Completion: 42% Proposed Project Completion Date: November 2026 Project Status: Issues:/Challenges: None
8 |  | St. James | Barracks Road Primary | 5000000 |  |  | Repairs to windows and electrical system to main classroom block as per Standard Building Code | 1 | TSU | [5 empty] | 61% -79% ; work in progress | UNICEF
9 |  | St. James | Green Pond Primary and Infant |  | 34177172 |  | Roof repairs to classroom buildings, canteen and corridors, repairs / modification of suspended ceiling, electrical repairs | 1 | TSU | VM Construction & Haulage | 2 | Approval granted | 2026-02-14 | 2026-09-04 | 80% - 99% ; work in progress | Work in progress
10 |  | St. James | Buckingham Primary and Infant | 75000000 |  |  | Roof repairs to lower school, canteen and classrooms. Repairs to damaged upper school buildings as per Standard Building Code | 1 | NET | Pavecon | 1 |  |  |  | Contractor to be given site possession | "Project Percentage Completion: 0% Proposed Project Completion Date: To be determined pending issuance of commencement letter Project Status: Awaiting contractors submission Issues:/Challenges: None "Awaiting revised submission from contractor before letter of commencement can be issued.
11 |  | St. James | Goodwill Primary and Infant |  | 100127350 |  | Roof, ceiling, electrical, waterproofing, toilets and replacement of water tanks . Repairs to the library and the Infant department as per Standard Building Code | 1 | NET | CA Quality | 1 | Approval granted | 2026-04-16 | 2026-10-15 | 20% & Below ; work in progress | Project Percentage Completion: 15% Proposed Project Completion Date: October 15, 2026 Project Status: Issues:/Challenges: Awaiting payment
12 |  | St. James | John Rollins Success Primary |  | 35522900 |  | Replacement of roof sheeting of main classroom building. Construction of security fence and guardhouse as per Standard Building Code | 1 | NET | Pavecon | 1 |  |  |  | Work to Commence | Project Percentage Completion: 0% Proposed Project Completion Date: Project Status: Issues:/Challenges: Design and Build project
13 |  | St. James | John's Hall Primary | 150000000 |  |  | Repairs to roof and structure. Repairs to electrical supply, construction of retaining wall as per Standard Building Code | 1 | NET | CA Quality | 1 |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 5% Proposed Project Completion Date: Project Status: Temporary classrooms 1. Excavate Foundation 100% 2. Cast Foundation 100% 3. Timber walling 50% Preparation of Design and working drawings 1. Preliminary Designs 10% 2. Working Drawings 05% 3. Municipal Approval 0% Reconstruction of Classroom and Administrative Block 1. Setting Out 0% 2. Excavation of Foundation 0% Issues:/Challenges:
14 |  | St. James | Mount Zion Primary and Infant |  | 191720978.84 |  | Reconstruction of toilet block and roof repairs to main classroom building as per Standard Building Code | 1 | NET | Construction Solutions Limited |  | Approval granted |  |  | Work to Commence | Project Percentage Completion: 0 Proposed Project Completion Date: Project Status: Work to commence pending payment of mobilization Issues:/Challenges: Contractor awaiting payment for mobilization
15 |  | St. James | Somerton Primary and Infant | 70000000 |  |  | Roof repairs and window replacement | 1 | NET | S&G |  |  |  |  | Contractor to be given site possession | Project Percentage Completion: 0 Proposed Project Completion Date: To be determined pending issuance of commencement letter Project Status: Technical team to review. Issues:/Challenges:
16 |  | St. James | Spot Valley High |  | 73803000 | 11070450 | Repairs to roof, electrical system and gutter replacement to main building as per Standard Building Code | 1 | NET | Monticon Limited | 1 | Approval granted |  |  | 80% - 99% ; work in progress | Project Percentage Completion: 80% Proposed Project Completion Date: August 28, 2026 Project Status: Issues:/Challenges: The contractor has formally submitted a claim for payment. This claim is currently undergoing internal review and has not yet been disbursed
17 |  | St. James | Sudbury Primary and Infant | 25000000 | 27938000 |  | Roof repairs, electrical repairs and replacement of doors, windows and cupboard | 1 | NET | Marlon Turner Construction | 1 |  |  |  | Work to Commence | Project Percentage Completion: 0% Proposed Project Completion Date: Project Status: Work to commence pending issuance of contract document Issues:/Challenges: Contractor awaiting contract issuance
18 |  | St. James | Adelphi Primary | 25000000 |  |  | Repairs to roof and roof members and electrical system to main classroom block as per Standard Building Code | 1 | TSU | C & D Construction and Engineering Limited |  | 2026-03-17 |  |  | Contractor to be given site possession | Contractor already on site for MoE security fencing project. Recommendation to undertake hurricane repairs as well. QS completed pre tender estimate for pricing by July 9, 2026
19 |  | St. James | Barrett Town Primary and Infant |  | 30267285 |  | Repairs to roof, ceiling, windows and doors, sanitation and siding of building of main classroom block as per Standard Building Code | 1 | TSU | Tropical Metal Products Limited | 1 | Approval granted | 2026-02-11 | 2026-05-07 | 80% - 99% ; work in progress | Variation order to be completed for variation - termite treatment
20 |  | St. James | Dumfries Primary |  | 14027637 |  | Repairs to roof, electrical system, fencing and water storage to main classroom block as per Standard Building Code | 1 | TSU | Tropical Metal Products Limited | 1 | Approval granted | February 11, 2026 | 2026-05-07 | 80% - 99% ; work in progress | Practical completion. Payment to be submitted to TSU by June 4, 2026
21 |  | St. James | Irwin High |  | 33000000 |  | Repairs to roof, electrical system and water supply to block B and C as per Standard Building Code | 1 | TSU | V M Construction & Haulage |  | Approval granted | 2026-01-24 | 2026-09-04 | 80% - 99% ; work in progress | Work in progress; gutters and metal hollow section frame being sourced
22 |  | St. James | Irwin Primary |  | 21430000 | 10095300 | Repairs to roof, ceiling and electrical system to Block 2 as per Standard Building Code | 1 | TSU | V M Construction & Haulage | 3 | Approval granted | 2026-01-23 | 2026-09-04 | 80% - 99% ; work in progress | Work in progress; gutters and metal hollow section frame being sourced. Variation order to be prepared for approval
23 |  | St. James | Lottery Primary and Infant |  | 21430000 |  | Repairs to roof, electrical system and water storage to school buildings (3) as per Standard Building Code | 1 | TSU | THLC Company Limited | 2 | 2026-03-24 |  |  | Contractor to be given site possession | QS assigned. Estimate reviewed for submission to contractor via GoJEP by June 5, 2026
24 |  | St. James | Bogue Hill Primary and Infant | 25000000 |  |  | Repairs to roof for infant department as per Standard Building Code | 1 | DONOR | [5 empty] | Work Completed | Work completed December by Donor - Canadian Trades Professionals and JDF
|  |  |  | 16674500 |  |  | Repairs to roof for infant department as per Standard Building Code | 1 | NET | Yardworks Construction |  |  |  |  | Contractor to be given site possession
25 |  | St. James | Catherine Hall Primary and Infant |  | 127740135.37 |  | Repairs to damaged canteen. Roof repairs to the kitchen, waterproofing of roof and window replacement as per Standard Building Code | 1 | NET | Brothers Concept & Solutions Limited | 1 | Approval granted |  |  | 51% - 60% ; work in progress | Project Percentage Completion: 51% Proposed Project Completion Date: December 18, 2026 Project Status: Issues:/Challenges: Funding
26 |  | St. James | Herbert Morris Technical |  | 562597880 | 49208210 | Roof, ceiling and gutters repairs and replacement, electrical repairs. Replacement of windows and doors, canteen and auxiliary building repairs as per Standard Building Code | 1 | NET | Costley Construction | 1 | Approval granted | 2026-01-12 | 2026-07-11 | 41% - 50% ; work in progress | Project Percentage Completion: 42% Proposed Project Completion Date: Project Status: Issues:/Challenges: Adendum to contract was issued. Contractor can now expect payment for works already done
27 |  | St. James | Tower Hill Primary and Infant | 55000000 |  |  | Roof repairs and electrical repairs | 1 | NET | CA Quality | 1 |  |  |  | Contractor to be given site possession | Project Percentage Completion: 0% Proposed Project Completion Date: Project Status: Awaiting contractors submission to finalize issuance of commencement letter Issues:/Challenges: Awaiting contractors submission
28 |  | St. James | Granville Primary and Infant |  | 29225229 |  | Major repairs to roof system, windows and doors, sanitation, metal staircase and siding of building to canteen and classroom block. Repairs to roof for infant department as per Standard Building Code | 1 | TSU | Tropical Metal Products Limited | 1 | Approval granted | 2026-02-14 | 2026-09-04 | 80% - 99% ; work in progress | Work in progress
29 |  | St. James | Howard Cooke Primary |  | 23526900 |  | Waterproofing of slab roofs. Replacement of roofs. Electrical repairs. Repairs to sections of perimeter wall / fencing. Clearing of mud clogged drains, Replacement of doors. Canteen repairs, Sanitation repairs to main classroom and office as per Standard Building Code | 1 | TSU | Marken Construction Company Limited | 3 | Approval granted | 2026-03-24 | 2026-09-04 | 80% - 99% ; work in progress | Wok in progress ( variation for the fencing to be submitted)
30 |  | St. James | Chetwood Memorial Primary |  | 23526900 |  | Repairs to Canteen, two classrooms and part of Grade 2 block. Replacement of Grade three classroom windows | 1 | DONOR | Canadian Trades Professionals and JDF |  |  |  |  | Work Completed | Project Percentage Completion: 100% Project Status: Project completed-Donor initiative
|  |  |  | 30000000 |  |  | Repair of Grade 2 classroom roof | 1 | NET | Brothers Concept |  |  |  |  | Contractor to be given site possession
31 |  | St. James | Flankers Primary and Infant |  | 70658775.37 |  | Toilet block repairs, roof repairs, associated electrical repairs | 1 | NET | Brothers Concept | 1 | Approval granted |  |  | 41% - 50% ; work in progress | Project Percentage Completion: 45% Proposed Project Completion Date: December 18, 2026 Project Status: Works ongoing at a slow pace. Issues:/Challenges: Contractor awaiting payments
32 |  | St. James | Mount Alvernia High |  | 177968965 |  | Repairs to roofs, ceiling, and gutters on buildings . Repairs to fence and windows | 1 | NET | Costly Construction | 1 | Approval granted | 2026-01-12 | 2026-07-11 | 41% - 50% ; work in progress | Project Percentage Completion: 48% Proposed Project Completion Date: Project Status: Works delayed Issues:/Challenges:
33 |  | St. James | Anchovy High |  | 120285650 | 47140642.65 | CAMPUS 2 - Significant roof replacement on buildings - classrooms, toilets, sickbay, computer room, fence repairs, water storage CAMPUS 1 - Roof replacement & ceiling installation on Auditorium building. Roof replacement in book room. Other roof replacement on cottage building, classroom. Fence repairs | 1 | NET | Build Management Technology & Logistic | 2 | Approval granted | ` |  | 80% - 99% ; work in progress | "Project Percentage Completion: 80% Proposed Project Completion Date: August 31, 2026 Project Status: Works delayed Issues:/Challenges: Roofing activities has encountered delays due to a shortage of essential materials, specifically purlins and sheeting.
34 |  | St. James | Anchovy Primary |  | 174675554.9 | 47140642.65 | Re-roofing. Roof, ceiling, and electrical. (Recommending slab) | 1 | NET | Diverse Services & Construction Limited |  | Approval granted |  |  | 80% - 99% ; work in progress | Project Percentage Completion: 88% Proposed Project Completion Date: September 17, 2026 Project Status: Works delayed Issues:/Challenges: Payment
35 |  | St. James | Cambridge High |  | 317308190.2 |  | Fencing, electrical, water tanks, sanitation, cottage flats | 1 | NET | Build- Rite Construction | 1 | Approval granted |  |  | 41% - 50% ; work in progress | Project Percentage Completion: 50% Proposed Project Completion Date: Project Status: Payment delayed until payment is finalized Issues:/Challenges: Payment of claim
36 |  | St. James | Cambridge Infant |  | 74963600 | 11244450 | Replace destroyed timber building. Fencing. Electrical. General repairs | 1 | NET | Build- Rite Construction | 1 | Approval granted |  |  | 80% - 99% ; work in progress | Project Percentage Completion: 85% Proposed Project Completion Date: September 5, 2026 Project Status: Works delayed Issues:/Challenges: Payment issues
37 |  | St. James | Cambridge Primary |  | 125499000 |  | Roof, ceiling & gutters replacement, | 1 | NET | Marlon Turner Construction |  |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 18% Proposed Project Completion Date: Project Status: work is ongoing Issues:/Challenges: Awaiting contract issuance
38 |  | St. James | Catadupa Primary |  | 64251628.1 | 25062007.7 | Roof repairs to the main building, computer room, Grade 6 classroom block. | 1 | NET | Diverse Services & Construction Ltd | 1 | Approval granted |  |  | 80% - 99% ; work in progress | Project Percentage Completion: 95% Proposed Project Completion Date: September 17, 2026 Project Status: Taking over Certificate to be issued Issues:/Challenges:
39 |  | St. James | Chatsworth Primary and Infant |  | 56524006 | 27445576.8 | Roof, Roof members, electrical, water storage, windows and doors, external erosion, repairs to sanitation | 1 | NET | Diverse Services & Construction Ltd | 1 | Approval granted |  |  | 80% - 99% ; work in progress | Project Percentage Completion: 90% Proposed Project Completion Date: August 15, 2026 Project Status: Taking over certificate to be issued Issues:/Challenges: None
40 |  | St. James | Garlands Primary |  | 182212339.13 |  | Re-roofing of Timber building, guard house and cottage and replacement of water tanks | 1 | NET | Brothers Concept | 1 | Approval granted |  |  | Work to Commence | Project Percentage Completion: 0% Proposed Project Completion Date: TBD Project Status: Issues:/Challenges: Contractor awaiting payment for other projects to commence works at this site
41 |  | St. James | Lethe Primary and Infant | 165970230.66 |  |  | Replacement of roof and clean mud from classrooms. Replace timber buildings at Infant Department | 1 | NET | CA Quality | 1 |  |  |  | Contractor to be given site possession | Project Percentage Completion: 0% Proposed Project Completion Date: TBD Project Status: Issues:/Challenges: Awaiting contractor submission
42 |  | St. James | Mount Carey Baptist Infant |  | 82681787 |  | Repairs to roof, ceiling, gutters, fencing, electrical and classroom | 1 | NET | Monticon | 1 | Approval granted |  |  | 61% -79% ; work in progress | Project Percentage Completion: 61% Proposed Project Completion Date: September 30, 2026 Project Status: Works ongoing Issues:/Challenges:
43 |  | St. James | Vaughansfield Primary and Infant |  | 53890000 |  | repairs- Roof, Roof members, electrical, water storage, windows and doors | 1 | NET | Sylvester |  |  |  |  | Work to Commence | Project Percentage Completion: 0% Proposed Project Completion Date: To be determined Project Status: Work to commence Issues:/Challenges:
44 |  | St. James | Maldon High |  | 26844100 |  | Roof repairs to classroom, tuck shop, cottage and eating area; electrical repairs and painting as per Standard Building Code | 1 | TSU | D.R. Foote Construction Co. Ltd | 1 | 2026-01-16 | 2026-01-23 | 2026-08-28 | 80% - 99% ; work in progress | Variation order being completed for repair to cottage building and damaged section of block wall
45 |  | St. James | Maldon Primary |  | 38354497 |  | Roof and water pipes repairs to main classroom block as per Standard Building Code | 1 | TSU | Tropical Metal Products Limited | 1 | Approval granted | 2026-02-28 | 2026-09-11 | 61% -79% ; work in progress | Work challenge - difficulties due to nature of work while school is in session
46 |  | St. James | Mount Horeb Primary and Infant |  | 29031100 |  | Repairs to roof and electrical system to main classroom block as per Standard Building Code | 1 | TSU | D R Foote Construction Company Limited | 1 | Approval granted | 2026-01-23 | 2026-04-22 | 80% - 99% ; work in progress | Practical Completion.
47 |  | St. James | Niagara Primary and Infant |  | 14295400 | 17393850 | Repairs to roof and electrical system to main Primary School building as per Standard Building Code | 1 | TSU | V M Construction & Haulage |  | Approval granted | 2026-01-23 | 2026-04-22 | 80% - 99% ; work in progress | Practical Completion.
48 |  | St. James | Orange Hill Primary and Infant |  | 40106190 | 13251000 | Repairs to roof, windows and doors, electrical system and water harvesting to main classroom building as per Standard Building Code | 1 | TSU | Cambridge Trading Limited | 2 | Approval granted | 2026-02-02 | 2026-05-18 | 80% - 99% ; work in progress | Practical Completion. Defects being addressed
49 |  | St. James | Roehampton Primary |  |  |  | Repairs to roof, water storage and electrical system to main classroom building as per Standard Building Code | 1 | TSU | Tropical Metal Products Limited | 2 | 2026-03-24 |  |  | Contractor to be given site possession | QS assigned. Estimate reviewed for submission to contractor voia GoJEP by June 25, 2026
50 |  | St. James | Springfield Primary and Infant |  | 49620124 |  | Waterproofing of roof slab, window replacement, water storage, chain-link fence to main classroom building as per Standard Building Code | 1 | TSU | Modern Waterproofing & Construction | 1 | Approval granted | 2026-01-29 | 2026-04-30 | 80% - 99% ; work in progress | Practical Completion. Defects being addressed
51 |  | Hanover | Askenish Primary and Infant |  | 188827125 |  | Roof, ceiling, gutters and associated electrical | 1 | NET | NF Barnes |  | Approval granted | 2026-05-22 | 2026-11-21 | 21% - 40% ; work in progress | Project Percentage Completion: 25% Proposed Project Completion Date: TBD Project Status: Classroom Block 1. Replace roof and ceiling 50% 2. Electrical Repairs 0% 3. Painting 0% Administrative Block 1. Repair roof 0% 2. Provide Toilet Facility 0% 3. Electrical 0% 4. Painting 0% Teachers Cottage 1. Demolish Existing Roof 100% 2. Replace roof 0% Issues:/Challenges:
52 |  | Hanover | Clifton Primary and Infant |  | 91031700 | 18110400.8 | Roof, ceiling, gutters and associated electrical and fencing | 1 | NET | NF Barnes | 1 | Approval granted | 2026-05-27 | 2026-11-26 | 20% & Below ; work in progress | Project Percentage Completion: 10% Proposed Project Completion Date: Project Status: Administrative, Classroom and Kitchen Block 1. Replace Timber Roof 0% 2. Cast slabs 100% 3. Electrical 0% 4. Painting 0% Infant Block 1. Repair Roof 0% Issues:/Challenges:
53 |  | Hanover | Cove Primary |  | 49239520 | 10111097.5 | Roof, ceiling, gutters and associated electrical and window and doors | 1 | NET | NF Barnes | 1 | Approval granted |  |  | 20% & Below ; work in progress | Project Percentage Completion: 05% Proposed Project Completion Date: Project Status: Principal's Cottage 1. Demolish Existing Roof 100% 2. Replace roof 05% Issues:/Challenges: The initial scope included repairs to the Administrative and Classroom Block, however this aspect of the repair work was being carried by Sandals Resort
54 |  | Hanover | Green Island High |  | 49239520 |  | Waterproofing of roof, Metal Works, Windows and doors, structural reinforcements To make repairs and install roof slab to construction build To make repairs and install roof slab to Agri Room To make repairs and install roof slab to teachers cottage To make repairs to poultry house and install timber roof To make repairs to nursery and install timber roofing Waterproofing membrane to be installed to roofing slabs | 1 | NET | Dukes Electrical and Building Solutions Limited | 2 | Approval granted |  | 3 months | 51% - 60% ; work in progress | Project Percentage Completion: 60% Poultry House - 75% Construction Classroom - 95% Agri Classroom - 95% Slaughter House - 20% Cottage - 30% Proposed Project Completion Date: August 31, 2026 Works done this week: Poultry House - Diamond Grate mesh installed Construction Classroom - Window Jambs rendered Agri Classroom - Electrical works Slaughter House - Column footings and columns cast Cottage - Column footings and column cast Works to be done next week: Cottage slab decking to be installed to receive steel, MEP and concrete works Comments/Issues:/Challenges:
55 |  | Hanover | Rusea's High |  | 153908858 |  | Campus 1 Replace roof of Grade 11 block, 4 Teacher's cottages buildings, and Tuckshop. Auditorium- replace doors gone and roof repairs. Campus 2 Roof repairs for a sections of main building. Roof replacements for the entire section of building that houses the computer lab and the tuckshop. Roof replacement for the canteen and sections of the roof on the Industrial Arts building and Grade 8 building. Repairs to Students' restrooms, and guidance department. | 1 | NET | J & H Construction | 1 | Approval granted | 2026-01-26 | 2026-07-25 | 61% -79% ; work in progress | Project Percentage Completion: 75% 7 & 8 Block (Brick) - 85% Block 7 & 8 T1-11 Building - 50% Block A/Computer Lab - 100% Gazebo (Campus 1) - 0% Container Tuck Shop (Campus 1) - 100% Industrial Block - 75%Grade Bathroom (Male and Female) - 100% Canteen (Campus 2) - 90% Teacher Room - 90% Old Fort Building - 100% Overall Demolition - 95% Proposed Project Completion Date: October 31, 2026 Works done this week: 7&8 Block (Brick building roofing) - 85% Old Fort Building (roofing) - 100% Works to be done next week: Comments/Issues:/Challenges: Contractor to provide costing for variations items identified.
56 |  | Hanover | Cacoon Primary and Infant |  | 15888037 | 13238037 | Roof repairs, waterproofing of slab roofs, restoration of wall, chain-link fencing to main classroom building as per Standard Building Code | 1 | TSU | Cambridge Trading Limited | 2 | Approval granted | 2026-02-10 | 2026-05-06 | 80% - 99% ; work in progress | Practical Completion. Defects being addressed
57 |  | Hanover | Cave Valley Primary and Infant |  | 29324000 |  | Major replacement and repairs on all buildings – roof sheeting & members, blocking boards, sarking. Replacement of roof drainage system, termite treatment. Repairs to electrical system – supply and lighting arrestor and associated painting to main classroom building as per Standard Building Code | 1 | TSU | THLC Company Limited | 2 | Approval granted | 2026-03-31 | 2026-09-04 | 80% - 99% ; work in progress | School have requested for work to be continued during the summer holidays based on the level of disruption to daily operation.
58 |  | Hanover | Chambers Pen Primary |  | 16004311 |  | Repairs to roof of canteen, electrical system and fence as per Standard Building Code | 1 | TSU | THLC Company Limited | 2 | Approval Granted | 2026-03-02 | 2026-09-04 | 61% -79% ; work in progress | Work in progress
59 |  | Hanover | Church Hill Primary |  |  |  | Repairs to electrical supply and distribution, roof repairs and fence repairs to main classroom building as per Standard Building Code | 1 | TSU | Build Management Technology & Logistic |  | 2026-03-24 |  |  | Contractor to be given site possession | QS assigned. Estimate reviewed for submission to contractor voia GoJEP by June 25, 2026
60 |  | Hanover | Esher Primary | 15000000 |  |  | Repairs to roof, windows and electrical system to main classroom building as per Standard Building Code | 1 | TSU | Marken Construction Company Limited | 3 | 2026-03-24 |  |  | Contractor to be given site possession | QS assigned. Estimate reviewed for submission to contractor voia GoJEP by July 9, 2026
61 |  | Hanover | Lucea Infant |  | 29690620 | 10718750 | Major repairs to roofing system, roof drainage, electrical system to main classroom building as per Standard Building Code | 1 | TSU | Modern Waterproofing & Construction | 1 | Approval granted | 2026-01-29 | 2026-09-11 | 61% -79% ; work in progress | Sourcing material - metal hollow sections
62 |  | Hanover | Lucea Primary |  |  |  | Repairs to roof and roof members, waterproofing of concrete slab, electrical system, windows and doors to buildings 1 and 2 as per Standard Building Code | 1 | TSU | Modern Waterproofing & Construction | 3 | 2026-03-24 |  |  | Contractor to be given site possession | QS assigned. Estimate reviewed for submission to contractor voia GoJEP by July 9, 2026
63 |  | Hanover | Pell River Primary |  | 13639800 |  | The decorative blocks needs to remove to replace with windows as it cannot withstand heavy rainfalls and hurricane seasons. The canteen is leaking. The wire that takes electricity to the tank and bathroom is down. Grade 5 and 6 classroom roof are damaged and Grade 1and2 are leaking as per Standard Building Code | 1 | TSU | V M Construction & Haulage |  | Approval granted | 2026-01-23 | 2026-09-04 | 80% - 99% ; work in progress | Material availability is a challenge - Alu-stell C - Channel
64 |  | Hanover | Bethel Primary |  | 113287564.73 |  | Grade 1 (Rebuild), Grade 1,2 & 3 Roofing and Electrical work | 1 | NET | Quality Plus Contracting Company Limited |  | Approval granted |  |  | 20% & Below ; work in progress | Project Percentage Completion: 0% Contractor to mobilize within the next two weeks Preliminaries - Grade 1 (Rebuild) - Submission made to parish council. Awaiting approval Grade 1,2 & 3 Roofing - Works to commence Electrical - Proposed Project Completion Date: January 31, 2027 Works done this week: Works to be done next week: Comments/Issues:/Challenges: Contractor did not commence works as the contract was not issued.
65 |  | Hanover | Brownsville Primary | 70000000 | 123232623.08 |  | Major roof replacement on steel framed buildings, repairs to toilet building, electrical repairs | 1 | NET | Roger Land Development |  |  |  |  | Contractor to be given site possession | Contractor reassigned
66 |  | Hanover | Claremont Primary and Infant | 51390250 | 52568450 |  | Repairs to roof of Infant department and fencing | 1 | NET | NF Barnes | 1 |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 4% Preliminaries - 15% Demolition - 10% Roofing - 5% Fencing - Painting - Electrical - Proposed Project Completion Date: October 31, 2026 Works done this week: Works to be done next week: Comments/Issues:/Challenges: No works took place this week as the Carpenter was not able to be present onsite due to a family emergency. Works are expected to resume next Tuesday
67 |  | Hanover | Gurney's Mount Primary and Infant | 51390250 | 67413885 |  | Replace roof, doors and windows | 1 | NET | Cenitech | 1 |  |  |  | Work to Commence | Project Percentage Completion: 0% Contractor has committed to commence works on the 28th of July. Proposed Project Completion Date: October 31, 2026 Works done this week: Works to be done next week: Comments/Issues:/Challenges: No contract has been issued. Contractor awaiting contracts to commence works.
68 |  | Hanover | Hopewell High |  | 67413885 |  | Roof repairs ( including corridors, two classrooms, goat pen, and receptacle). | 1 | DONOR | [5 empty] | 20% & Below ; work in progress | Donor - Sagicor
69 |  | Hanover | Knockalva Technical High | 480176717.95 |  |  | Roof replacement on buildings, window replacement, door replacement, fencing repairs | 1 | NET | Brothers Concept |  |  |  |  | Work to Commence | Awaiting contract issuance
70 |  | Hanover | Merlene Ottey High |  | 64548300.3 |  | To make General roofing repairs to Blocks: A1, A2, B, C, D, E1, E2, F, L, G and M Electrical works | 1 | NET | S&G Construction | 1 |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 5% Blocks M1 - Blocks A1 and A2 - Block B - Block D - Block C and E1 - Ridge Vent - 40% Block E2 - Ridge Vent - 40% Computer Lab - Block F Block L Greenhouse - Proposed Project Completion Date: January 31, 2027 Works done this week: Carpentry works to ridge vent is underway. Works to be done next week: Comments/Issues:/Challenges: Incorrect roofing materials were procured for installation. Contractor has been instructed to remove those materials already installed and to procure the correct materials (sheeting and ridge flashing)
71 |  | Hanover | Mount Hannah Primary | 68077485 |  |  | Roof , ceiling, gutter and electrical | 1 | NET | Proven Construction |  |  |  |  | 61% -79% ; work in progress | Project Percentage Completion: 75% Proposed Project Completion Date: TBD Project Status: Main Block- Roofing completed, joinery works to doors works and tiling works ongoing 2. External Works- all external works completed 3. Gazebo- Reconstruction of gazebo complete 4.. Canteen- Stripping of ceiling bed complete Issues:/Challenges:
72 |  | Hanover | Mount Ward Primary | 55000000 | 68066050 | 10209907.5 | Recommendation: Replace damaged roof with concrete slab. Establish steel water storage tank and support stand | 1 | NET | Monticon | 1 |  |  |  | Work to Commence | Project Percentage Completion: 0% Contractor has committed to begin works on 3/8/2026 Proposed Project Completion Date: December 31, 2026 Works done this week: Works to be done next week: Comments/Issues:/Challenges: The contractors mobilization claim has been processed for payment, however, there is no contract in place.
73 |  | Hanover | Pondside Primary | 20000000 | 64548300.3 |  | Waterproofing, linkway, windows, doors | 1 | NET | Construction 365 Company Limited | 1 |  |  |  | Contractor to be given site possession | Project Percentage Completion: 0 Proposed Project Completion Date: Project Status: The donor has committed to make repairs to windows and doors, Issues:/Challenges: The scope of works for this project includes windows and doors, waterproofing and roofing works to the linkway. The scope is quite small, therefore, these items will be addressed by donor.
74 |  | Hanover | Watford Hill Primary | 45000000 | 58285800 | 6534150.19 | Repairs to roof and gutters of the main building with the computer lab. 3 blade window to be replaced, 2 double doors to be replaced. 2- Double doors to be replaced. | 1 | NET | Marlon Turner Construction |  | Approval granted | 2026-04-23 | 2026-10-22 | 80% - 99% ; work in progress | Project Percentage Completion: 85% Infant Department - 100% Pavillion - 100% Kitchen - 100% Main Building Roofing - 100% Main Building painting - 90% Fencing - 25% Windows and doors - Guttering Electrical Proposed Project Completion Date: August 2026 Works done this week: Fencing Doors and windows are being fabricated offsite, to be delivered Works to be done next week: Comments/Issues:/Challenges: Contractor submitted 2nd claim/variations
75 |  | Hanover | Cacoon Castle Primary and Infant |  | 24118455 |  | Roof and ceiling repairs, waterproofing of slab roofs, electrical repairs and fence repairs to main classroom building as per Standard Building Code | 1 | TSU | Cambridge Trading Limited | 2 | Approval granted | 2026-02-10 | 2026-05-06 | 80% - 99% ; work in progress | Practical completion - variation order for windows and internal repairs to canteen
76 |  | Hanover | Chester Castle Primary and Infant |  |  |  | Repairs to roof, fencing and electrical system to main classroom building as per Standard Building Code | 1 | TSU | Maxwell Construction Company Limited | 2 | Approval granted |  | 2026-09-04 | 80% - 99% ; work in progress | Work in progress
77 |  | Hanover | Jericho Primary and Infant | 4000000 |  |  | Repairs to roof, water storage and windows to main classroom building as per Standard Building Code | 1 | TSU | Marshall Construction Company Limited | 1 | 2026-03-24 |  |  | Contractor to be given site possession | QS assigned. Estimate reviewed for submission to contractor voia GoJEP by July 9, 2026
78 |  | Hanover | Maryland Primary and Infant | 25000000 |  |  | Repairs to roof and roof members and sanitation to Primary school and Infant Department as per Standard Building Code | 1 | TSU | Marken Construction Company Limited | 3 | 2026-03-24 |  |  | Contractor to be given site possession | QS assigned. Estimate reviewed for submission to contractor voia GoJEP by July 9, 2026
79 |  | Hanover | Mount Peto Primary | 15000000 |  |  | Renovation of the canteen block and water supply, roof repairs to main classroom block as per Standard Building Code | 1 | TSU | H T Roofing & Construction Limited |  | 2026-03-24 |  |  | Contractor to be given site possession | QS assigned. Estimate reviewed for submission to contractor voia GoJEP by July 9, 2026
80 |  | Hanover | Sandy Bay Primary |  | 29649600 |  | Repairs to roof and electrical system to office building, classroom and admin block and cottage as per Standard Building Code | 1 | TSU | THLC Company Limited | 2 | Approval granted | 2026-01-30 | 2026-05-18 | 80% - 99% ; work in progress | Practical completion
81 |  | Hanover | Success Primary and Infant |  | 23235500 | 21234000 | Repairs to roof and roof members and electrical system to main classroom block and infant department as per Standard Building Code | 1 | TSU | D R Foote Construction Company Limited | 1 | Approval granted | 2026-02-17 | 2026-05-18 | 80% - 99% ; work in progress | Variation order being prepared for repairs to infant department Availability of roof sheeting material is a challenge. Logistics also a challenge while school is in session Practical completion
82 |  | Westmoreland | Mount Airy Primary and Infant | 45000000 |  |  | Roof repairs, building repairs, water supply, electrical | 1 | NET | Pavecon |  |  |  |  | Contractor to be given site possession | A meeting was held with the designer to review draft submission.
83 |  | Westmoreland | Paul Island Primary and Infant | 70000000 |  |  | Roof, electrical, fencing, windows | 1 | NET | Pavecon | 1 |  |  |  | Contractor to be given site possession | A meeting was held with the designer to review draft submission.
84 |  | Westmoreland | Strawberry Primary and Infant | 25245170 | 80459170 |  | Repairs to roof and electrical system, windows and fencing | 1 | NET | Pavecon | 1 |  |  |  | 61% -79% ; work in progress | Works commenced March 2026 Overall Project Percentage: 65% Progress: 1 Completion of painting to the interior girls’ and boys’ restrooms on the primary school 2 Completion of painting to the interior and ceiling of the infant school; classrooms. 3 Completion of the laying and fixing of gutters and downpipes at infant school. Upcoming Events: 1 Installation of 1# entrance door to Infant School. 2 Clearing of remaining rubble in Infant School. 3 Installation of remaining gutters and downpipes to Primary School building. 4 Continued renovations to fencing on Primary School. Issues: 1 The main issue is the availability of required materials at this point. Resolution: 1 A larger number of suppliers are being engaged for availability."
85 |  | Westmoreland | Blauwearie Primary and Infant | 40000000 |  |  | Repairs to roof and electrical system | 1 | NET | C& D Construction | 1 |  |  |  | Contractor to be given site possession | Recommended to NET for construction drawings, municipal approval and quantity surveyor
86 |  | Westmoreland | Broughton Primary | 40000000 | 97524896 |  | Repairs to roof and electrical system to main classroom block as per Standard Building Code | 1 | TSU | Geecho Construction | 1 | Approval granted |  | 2026-09-04 | 80% - 99% ; work in progress | Work in progress
87 |  | Westmoreland | Friendship Primary and Infant |  | 81965511.08 |  | Repairs to roofs, fencing, windows, doors, cottage, electrical system to main classroom block as per Standard Building Code | 1 | TSU | Marshall Construction Company Limited | 1 | Approval granted | 2026-02-15 | 2026-09-11 | 80% - 99% ; work in progress | Work in progress
88 |  | Westmoreland | Grange Hill High | 118947900 |  |  | PHASE 1 - Electrical repairs, water supply repairs to re-open school. PHASE 2 - Cottage & Greenhouse rehabilitation | 1 | NET | Build Management Technology & Logistic | 1 |  |  |  | Contractor to be given site possession
89 |  | Westmoreland | Grange Hill Primary |  | 73929240 |  | Repairs to roof and members, hardcourt, and electrical system to all 9 classroom blocks as per Standard Building Code | 1 | TSU | Build Management Technology & Logistic | 2 | Approval granted |  | 2026-09-11 | 61% -79% ; work in progress | Material on site. Work to commence by start of July 2026 due to current school operation
90 |  | Westmoreland | Little Bay Primary and Infant |  | 44557650 |  | Repairs to roof, fencing and electrical system to main classroom block as per Standard Building Code | 1 | TSU | K & R and Associates | 1 | Approval granted | 2026-03-26 | 2026-10-02 | 20% & Below ; work in progress | Material on site. Work to commence by start of July 2026 due to current school operation
91 |  | Westmoreland | Little London Primary and Infant | 30000000 |  |  | Waterproofing of slab roof, other roof repairs, replacement of damaged safety rails to main classroom block as per Standard Building Code | 1 | TSU | HT Roofing & Construction Limited | 3 | 2026-03-24 |  |  | Contractor to be given site possession | QS assigned. Estimate reviewed for submission to contractor voia GoJEP by July 9, 2026
92 |  | Westmoreland | Moreland Hill Primary and Infant | 35000000 |  |  | Repairs to roof, fencing and electrical system to main classroom block as per Standard Building Code | 1 | TSU |  |  | Approval Granted |  |  | Contractor to be given site possession | QS assigned. Estimate reviewed for submission to contractor voia GoJEP by July 9, 2026
93 |  | Westmoreland | Mount Grace Primary and Junior High | 25000000 |  |  | Roof repairs, building repairs, water supply, electrical - Grades 1,4 & 6. Erosion near playfield | 1 | NET | K and R and Associates |  | 2026-03-25 |  |  | Contractor to be given site possession | Recommended to NET for structural design, construction drawings, municipal approval and quantity surveyor
94 |  | Westmoreland | Peggy Barry Primary and Infant |  | 32571902 |  | Major roof replacement and repairs on building; waterproofing of roof and associated masonry repairs; repairs to electrical system – supply and lighting; major repairs to kitchen area,; window and door replacement; repairs to sanitary building and associated painting to main classroom block as per Standard Building Code | 1 | TSU | Cambridge Trading Limited | 2 | Approval Granted | 2026-04-02 | 2026-09-11 | 61% -79% ; work in progress | Material on site. Work to commence by start of week ending June 26, 2026 due to current school operation
95 |  | Westmoreland | Revival Primary |  |  |  | Repairs to roof of administrative block and staffroom and repairs to windows of grade 3 block as per Standard Building Code | 1 | TSU | Build Management |  | 2026-03-25 |  |  | Contractor to be given site possession | QS assigned. Estimate reviewed for submission to contractor voia GoJEP by July 9, 2026
96 |  | Westmoreland | Sheffield Primary |  | 23784000 | 14585000 | Repairs to canteen, waterproofing and electrical system to main classroom block as per Standard Building Code | 1 | TSU | J Niel Construction Limited | 3 | Approval Granted | 2/206/2026 | 2026-05-31 | 80% - 99% ; work in progress | Practical Completion
97 |  | Westmoreland | St. Paul's Primary |  | 23887500 |  | Repairs to sanitation, roof and electrical system to main classroom block as per Standard Building Code | 1 | TSU | J Niel Construction Limited | 3 | Approval granted | 2/206/2026 | 2026-05-31 | 80% - 99% ; work in progress | Practical Completion
98 |  | Westmoreland | Townhead Primary and Infant |  | 69016000 |  | Repairs to roof, fence and electrical system to main classroom block as per Standard Building Code | 1 | TSU | Yardworks Construction Company Limited | 1 |  |  | 2026-10-02 | 20% & Below ; work in progress | Material on site. Work to commence by start of week ending June 26, 2026 due to current school operation
99 |  | Westmoreland | Culloden Infant | 100000000 |  |  | Rehabilitation of Classroom 7 and external works, such as upgrading the water supply and installing perimeter fencing. | 1 | DONOR | Accu-rate Builders Incorporated |  |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 0% Proposed Project Completion Date: January 15, 2027 Project Status: Contractor issued a commencement notice on July 15, 2026 Issues:/Challenges: Contractor instructed to prioritise construction of canteen facility at Kings Primary
|  |  |  | 71810693 |  |  | Construction of two classrooms and sanitary facilities for students and staff | 1 | NET | Howard Construction |  |  |  |  | Work to Commence | Project Percentage Completion: 0% Proposed Project Completion Date: January 15, 2027 Project Status: Contractor issued a commencement notice on July 15, 2026 Issues:/Challenges: Contractor instructed to prioritise construction of canteen facility at Kings Primary
100 |  | Westmoreland | Kings Primary and Infant |  |  |  | Construction of Kitchen and canteen, 4 classrooms and sanitary facilities, along with external works to include fencing, retaining wall and driveway | 1 | NET | Howard Construction |  |  |  |  | 20% & Below ; work in progress | Works commenced July 22, 2026 Overall Project Percentage: 5% Progress: 1. Works for the proposed canteen and classroom block have commenced. 2. Demolition of the existing building has been completed. 3. Setting out of the proposed buildings is currently underway. Upcoming Events: 1. Removal of the affected section of the timber shed is required urgently to prevent delays to the project schedule. Issues: N/A Resolution: N/A
|  |  |  | 72068665 |  |  | Infant Dept collapsed. Grades 1and2 have a column left standing, Grade 4, 5, 6, library, computer room, principal office, canteen etc have most of the roofing torn off. All wiring, perimeter fence are on the ground. Windows and roof are missing and roofing damaged, tanks blown off and missing. | 1 | DONOR | NET and Sandals Foundation 50/50 funding |  |  |  |  | 61% -79% ; work in progress | Donor Initiative- Approximately 90% of primary and 50% of infant block completed.
101 |  | Westmoreland | Bethel Town Primary | 80000000 | 457840000 |  | Re-roofing of Main Block, Construction of classroom block, kitchen canteen and staff facilities along with boundary fence Construction of an infant department | 1 | NET | Chins Construction |  | 2026-01-09 |  |  | Work to Commence | Project Percentage Completion: 0% Contractor to mobilize within the next two weeks Preliminaries - Grade 1 (Rebuild) - Submission made to parish council. Awaiting approval Grade 1,2 & 3 Roofing - Works to commence Electrical - Proposed Project Completion Date: January 31, 2027 Works done this week: Works to be done next week: Comments/Issues:/Challenges: Contractor did not commence works as the contract was not issued.
102 |  | Westmoreland | Darliston Primary |  | 126772850 | 10958386.25 | All roof and fence destroyed, bathroom needs repair | 1 | NET | D.R. Foote Construction Co. Ltd | 1 |  | 2025-12-12 | 2026-06-10 | 21% - 40% ; work in progress | Project Percentage Completion: 25% Proposed Project Completion Date: December 31, 2026 Project Status: Tuckshop – 40% Principal Office Block – 40% Classroom Block – 60% Canteen – 40% Rest Room – 95% Fencing – 30% Issues:/Challenges: ● Payment delays ● Works are progressing slowly. ● Repair works may not be completed in time for next school year.
103 |  | Westmoreland | Little London High |  |  |  | Waterproofing of roof, major repairs to holding area, roof repairs and replacement | 1 | DONOR |  |  | 2026-01-12 |  |  | 80% - 99% ; work in progress | Donor- Sagicor
104 |  | Westmoreland | Content Primary and Infant |  | 81165100 | 25814660 | Classroom destroyed. Construction of 3 classrooms. Roof repairs, other repairs | 1 | NET | Chins Construction |  |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 20% Proposed Project Completion Date: December 31, 2026 Project Status: Principal Cottage – 50% Classroom Block – 50% Admin Block – 0% Rest Room – 0% Infant Block – 0% Issues:/Challenges: ● Payment delays ● Works are progressing slowly. ● Repair works may not be completed in time for next school year.
105 |  | Westmoreland | Maud McLeod High |  | 193727300 | 30405805 | Replacement of the roof frame with a similar using improved anchorage to the roof frame and restoration of the waterproof membrane where damaged, as indicated in the assessment report. | 1 | NET | D.R. Foote Construction Co. Ltd | 1 |  | 2025-12-19 | 2026-03-19 | 61% -79% ; work in progress | Project Percentage Completion: 65% Proposed Project Completion Date: October 31, 2026 Project Status: Sixth Form Block – 70% Ancillary Area – 80% Tuck-shop – 70% Agriculture Area – 50% Principal Cottage – 80% Teachers Cottage – 20% PE Department – 0% Auto mechanic – 70% Issues:/Challenges: Payment delays. ● Contractor was instructed to place on focus on the occupied teachers cottage and auto mechanic building. ● Request adjustments to timber framing of chicken coup. ● Repair works may not be completed in time for next school year.
106 |  | Westmoreland | Petersfield Primary and Infant |  | 263375246.41 | 26375246.41 | Total re-roofing and structural reinforcement needed. | 1 | NET | Archistrust | 1 |  |  |  | 20% & Below ; work in progress | Contractor has slowed down works due to payment of claims that are outstanding
107 |  | Westmoreland | Retrieve Primary | 35000000 |  |  | Repairs to roof, fence and electrical system and rebuild toilet building | 1 | NET | Pavecon | 1 | 2026-01-09 |  |  | Contractor to be given site possession | Bids received July 14, 2026 and is being reviewed
108 |  | Westmoreland | Seaford Town Primary and Infant | 80000000 | 334014000 |  | "Demolition of the existing derelict structure. Renovation and reroofing of the existing Administration and Kitchen Block. Construction of new facilities comprising: Six (6) classrooms; A Resource Room; and A Wellness Facility." | 1 | NET | Pavecon | 1 |  |  |  | Work to Commence | Project Percentage Completion: 0 Proposed Project Completion Date: Project Status: "Designs and BQ received Designs accepted to be circulated with stakeholders BQ submitted June 8, 2026 - to finalise the review of BQ, recommendation for LOA submitted to the Procurement Unit, A contract to be drafted to facilitate the execution of works" Issues:/Challenges:
109 |  | Westmoreland | St. John's Infant | 30000000 | 282066650 |  | Repairs to electrical supply, water storage, roof and roof members and windows and doors replacement | 1 | NET | Pavecon | 1 | 2026-01-19 |  |  | Work to Commence | Project Percentage Completion:% Proposed Project Completion Date: Project Status: Designs completed. Contractor mobilizing team to commence works in August 2026 Issues:/Challenges: Contractor awaiting contract to generate payment to undertake the works
110 |  | Westmoreland | St. Leonard's Primary | 25000000 |  |  | new canteen, roof, elect water storage | 1 | NET | Pavecon | 1 |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 10% Proposed Project Completion Date: Project Status: Works are ongoing on the structural reinforcement of columns of the existing classroom block Design for the slab and canteen completed Issues:/Challenges: Contractor awaiting contract to generate payment to undertake the works
111 |  | Westmoreland | Ashton Primary |  | 55496038 |  | Repairs to roof, electrical system, cupboards, windows and doors and floor finish to main classroom block as per Standard Building Code | 1 | TSU | RSJ Construction Company Limited | 2 | Approval granted | 2026-02-19 | 2026-09-11 | 61% -79% ; work in progress | Work start affected by material unavailability and weather
112 |  | Westmoreland | Beaufort Primary |  | 23956629 |  | Repairs to roof, roof members, windows and doors, water storage, fencing, cupboards and electrical system to main classroom block as per Standard Building Code | 1 | TSU | J Niel Construction Limited | 3 | Approval granted |  | 2026-09-11 | 61% -79% ; work in progress | Work in progress
[7 empty] | Installation of water harvesting & sanitation, water storage and pumps | 1 | DONOR | UNICEF
113 |  | Westmoreland | Belmont Academy |  | 74693553 |  | Waterproofing of roof slab, Roof repairs, electrical repairs, doors, windows, fencing and cottage repairs to main classroom block as per Standard Building Code | 1 | TSU | Maxwell Construction Company Limited | 2 | Approval granted | 2025-12-29 | Extended to April 17, 2026 | 80% - 99% ; work in progress | Practical completion. Defects being addressed
114 |  | Westmoreland | Carmel Primary and Infant |  | 30186264 |  | Repairs to roof, windows and demonstration board, chain-link fence, electrical system, sanitation and access roadway to main classroom block as per Standard Building Code | 1 | TSU | Maxwell Construction Company Limited | 2 | Approval granted | 2025-12-29 | 2026-03-11 | 80% - 99% ; work in progress | Practical completion. Defects being addressed
115 |  | Westmoreland | Dundee Primary and Infant |  |  |  | Repairs to roof and electrical system to main classroom block as per Standard Building Code | 1 | TSU | Marken Construction Company Limited | 3 | 2026-03-20 |  |  | Contractor to be given site possession | QS assigned. Estimate reviewed for submission to contractor voia GoJEP by July 9, 2026
116 |  | Westmoreland | Enfield Primary and Infant | 59749840 |  |  | Repairs to roof and electrical system to main classroom block as per Standard Building Code | 1 | TSU | RSJ Construction Company Limited | 2 | 2026-03-20 |  | 2026-09-11 | 51% - 60% ; work in progress | Work in progress
117 |  | Westmoreland | Holly Hill Primary and Infant |  | 58432280 |  | Repairs to roof and members, hardcourt, and electrical system to main classroom block as per Standard Building Code | 1 | TSU | D.R. Foote Construction Company Limited | 1 | Approval Granted | 2026-02-20 | 2026-09-18 | 51% - 60% ; work in progress | Work in progress
118 |  | Westmoreland | Kentucky Primary and Infant |  | 72100048 |  | Repairs to roof and roof members, electrical system, cottage, fencing and water supply to main classroom block as per Standard Building Code | 1 | TSU | Geecho Construction | 1 | Approval granted |  |  | Work Completed | Work in progress
119 |  | Westmoreland | Kew Park Primary and Infant | 20000000 |  |  | Repairs to roof and members, hardcourt, and electrical system to main classroom block as per Standard Building Code | 1 | TSU | Marshall Construction Company Limited |  |  |  |  | Work Completed | QS assigned. Estimate reviewed for submission to contractor voia GoJEP by July 9, 2026
120 |  | Westmoreland | Mearnsville Primary and Infant | 8000000 |  |  | Repairs to roof, electrical system and water storage | 1 | DONOR | Cenitech | 1 | 2026-02-27 |  |  | Contractor to be given site possession | Passement was done During week of July 20, 2026 Contractor submitted bid July 28, 2026
121 |  | Westmoreland | Mount Hermon Primary and Infant |  | 84399500 |  | Repairs to roof, fencing, electrical and water supply to main classroom block as per Standard Building Code | 1 | TSU | Yardworks Construction Company Limited | 1 | Approval Granted | 2026-02-19 | 2026-09-11 | 61% -79% ; work in progress | Work in progress
122 |  | Westmoreland | New Hope Primary |  | 60498970 |  | Repairs to roof, associated electrical repairs and sanitation to main classroom block as per Standard Building Code | 1 | TSU | Maxwell Construction Limited Company | 2 | Approval Granted |  | 2026-09-18 | 61% -79% ; work in progress | Work in progress
123 |  | Westmoreland | New Roads Primary |  | 23988400 |  | Waterproofing to roof, roof repairs and electrical system to main classroom block as per Standard Building Code | 1 | TSU | Marken Construction Company Limited | 3 | Approval Granted | 2026-03-16 | 2026-09-11 | 21% - 40% ; work in progress | Work in progress
124 |  | Westmoreland | New Works Primary and Infant |  | 12594305 |  | Major repairs to roof system, windows and doors, sanitation and electrical to main classroom block as per Standard Building Code | 1 | TSU | Maxwell Construction Limited | 2 | 2026-03-24 |  | 2026-09-18 | 61% -79% ; work in progress | Work in progress
125 |  | Westmoreland | Salem Primary |  | 67671934 |  | Repairs to water storage and windows and doors and access roadway to main classroom block as per Standard Building Code | 1 | TSU | RSJ Construction Co Ltd | 2 | Approval granted | 2026-02-25 | 2026-09-18 | 61% -79% ; work in progress | Work in progress
126 |  | Westmoreland | Savanna-La-Mar Inclusive Academy | 10000000 |  |  | Roof repair and fencing | 1 | DONOR |  |  | 2026-01-06 |  |  | Work Completed | Rock House Foundation
127 |  | Westmoreland | Cokes View Primary | 60000000 |  |  | Classrooms destroyed. Construction of 3 classrooms. Roof repairs, other repairs | 1 | NET | Quality Plus Contracting | 1 |  |  |  | Work to Commence | Project Percentage Completion: 0% Proposed Project Completion Date: July, 2026 Project Status: Designs completed Issues:/Challenges: Contract to be issued to facilitate commencement of works
128 |  | Westmoreland | Frome Technical High |  | 87395450 |  | Roof replacement, Gutters, Fencing, Repairs to piggery, windows, door and associated electrical | 1 | NET | Build Management Technology & Logistic | 2 |  | 2026-01-12 | 2026-07-11 | 20% & Below ; work in progress | Project Percentage Completion: 5% Proposed Project Completion Date: December 31, 2026 Project Status: Stripping of damaged roofing from piggery Issues:/Challenges: Contractor delay in executing the works. Contractor's limited cash flow is impacting the progress of the works to be undertaken
129 |  | Westmoreland | Godfrey Stewart High | 87395450 | 556670794 |  | Waterproofing of roof, window and door replacement, roof replacement on buildings, fence repairs, construction of classroom | 1 | NET | S&G Construction | 1 |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 10% Proposed Project Completion Date: Project Status: Removal of damaged roof membrane Commence installation of Temporary facilities Demolition of derelict buildings Issues:/Challenges: Contractor delay in executing the works. Challenges with access being restricted by the school's administration Contractor has advance works on multiple other projects with limited compensation due to outstanding contracts.
130 |  | Westmoreland | Llandilo School of Special Education (Campus 1 -Westmoreland) |  | 136094491 | 18690573.9 | Roof, gutters, electrical | 1 | NET | Build rite |  |  |  |  | 21% - 40% ; work in progress | Project Percentage Completion: 21% Proposed Project Completion Date: TBD Project Status: Completed installation of the new timber roof and industrial sheeting to the Information Technology Building. 2 Completed painting of the sarking within the Information Technology Building. Completed painting of the internal walls within the Information Technology Building. 3 Completed repairs to the water damaged partition wall, which was identified outside of the original scope of works. Completed approximately 50% of the drywall partition installation within the computer laboratory. 4 Completed approximately 80% of the electrical installation works within the Information Technology Building. 5 Completed fabrication of reinforcement steel for the Main Block belt beam. Completed fabrication of formwork for the Main Block belt beam in preparation for reinforced concrete roof slab works. Issues:/Challenges: The Main Block remains occupied and operational, limiting access for demolition and roof replacement activities. Construction activities must be executed in phases to accommodate ongoing school operations and ensure the safety of students and staff. Additional remedial works were required to address water damaged partition walls that were outside the original scope of works alongside painting the external walls of the IT building 2 Delays were experienced in the receipt of the executed contract and mobilization payment, which adversely affected the Contractor's planned financial structure and early project execution strategy.
131 |  | Westmoreland | Manning's High |  | 638180231.67 | 36024075.34 | The approved scope of works includes complete reroofing of all facilities that sustained roof damage, including the construction of reinforced concrete slab roofs to the Prescott and Science Blocks, application of waterproofing membranes to existing concrete slabs, and execution of general repair works. | 1 | NET | C&D Construction | 1 |  | 2025-12-08 | 2026-08-05 | 61% -79% ; work in progress | Works commenced December 17, 2025 Overall Project Percentage: 71 % Progress: 1. Physics Lab: • Completed rendering/rough casing on the interior walls. • Executed additional electrical rough-in works. 2. Screeding: • Completed screeding on the top level and lower-level sections. 3. Physics Lab: • Finalize all remaining works, including painting and finishing touches 4. Electrical Room: • Complete ongoing works, including main line installations. 5.Art/Block Building & Electrical Substation: • Commencing scheduled works, including additional site preparation and structural/electrical setup. Upcoming Events: 1. Material & Logistics Requirements: Site Clearance: Demolish and clear a small section of the art block/building to facilitate the delivery, positioning, and storage of incoming project materials. 2. Technical Block (Purlins): Installation of angle iron brackets to prepare for the purlins; final installation of the purlins will proceed as soon as the materials arrive on-site. Issues: N/A Resolution: N/A
132 |  | Westmoreland | Petersfield High |  | 263752464.14 |  | Roof completely damage and electrical wires destroyed | 1 | NET | M&M Construction | 1 |  |  |  | 20% & Below ; work in progress
133 |  | Westmoreland | Petersville Primary | 75000000 | 144337312.54 |  | Repairs to roof and electrical system | 1 | NET | Marshall Construction Company Limited | 1 | 2026-01-16 |  |  | 20% & Below ; work in progress | Works commenced, May 5, 2025 Overall Project Percentage: 3% Progress: 1 Demolition of roof, ceilings, doors, kitchen, tiles torn down partitions, etc 2 Cutting down of Trees and brush 3 Demotion and removal of wall partitions 4 Cart away of debris Upcoming Events: 1 Installation of Roofing 2 Installation of ceiling 3 Installation of wall partitions 4 Installation of fencing Issues: 1. N/A Resolution: 1. N/A
134 |  | Westmoreland | Sir Clifford Campbell Primary |  | 99651245 |  | All 4 buildings have roof damage. The new roof on the upstairs building is partially gone. 3 classrooms were impacted. That roof fell on the class beside it. The Canadian model is damaged. Classrooms, kitchen and office impacted. Doors are broken, some locks are spoilt | 1 | NET | Pavecon | 1 |  |  |  | 20% & Below ; work in progress | Project Percentage Completion:10% Proposed Project Completion Date: Project Status: Roof to two-storey block being cast with reinforced concrete Issues:/Challenges: Contractor awaiting contract to generate payment to undertake the works
135 |  | Westmoreland | Unity Primary and Infant | 30000000 | 998610246.2 |  | Construction of 8 new classroom block and sanitary facility. Reconstruction of the Auditorium and 10 classroom. General renovation to existing facilities | 1 | NET | Pavecon | 1 |  |  |  | 20% & Below ; work in progress | Works commenced March 2026 Overall Project Percentage: 8% Progress: 1 Continued demolition of walls to classroom block and making good for concrete roof slab. Upcoming Events: 1 Continued demolition of walls to classroom block and making good for concrete roof slab and removal of debris. Issues:/Challenges: Contractor awaiting contract to generate payment to undertake the works
136 |  | Westmoreland | Williamsfield Primary and Infant | 30000000 |  |  | Roof repairs. General renovation of facilities including doors at the main office and Guidance Counsellor's Office, water tanks. Infant Department - roof repairs. Re-construction of Security Post. | 1 | NET | Pavecon | 1 |  |  |  | 20% & Below ; work in progress | Roof repairs to Infant block completed
137 |  | Westmoreland | Caledonia Primary and Infant |  | 23943429 |  | Major repairs and replacement to roof system - sheeting, frame, capping, gutters, associated painting, partition replacement, electrical repairs, masonry repairs, repairs to water storage system, repairs to security fencing, repairs to sanitation, replacement of defective doors, floor repairs to main classroom block as per Standard Building Code | 1 | TSU | Marken Construction Company Limited | 3 | Approval granted | 2026-03-21 | 2026-09-11 | 80% - 99% ; work in progress | Work in progress
138 |  | Westmoreland | Cornwall Mountain Primary and Infant | 100000000 | 23975100 |  | Repairs to roof and electrical system to main classroom block as per Standard Building Code | 1 | TSU | HT Roofing & Construction Limited | 3 | Approval granted | 2026-02-06 | 2026-09-04 | 80% - 99% ; work in progress | Work in progress
139 |  | Westmoreland | Ferris Primary |  | 23800000 |  | Roof replacement and repairs, fencing repairs, other repairs to building to main classroom block as per Standard Building Code | 1 | TSU | HT Roofing & Construction Limited | 3 | Approval granted | 2026-02-19 | 2026-05-28 | 80% - 99% ; work in progress | Practical Completion
140 |  | Westmoreland | George's Plain Primary and Infant |  | 79174750 |  | Electrical supply and distribution, roof repairs, structural repairs, fencing, windows to main classroom block as per Standard Building Code | 1 | TSU | Marshall Construction Company Limited | 1 | Approval granted | 2026-02-15 | 2026-09-04 | 80% - 99% ; work in progress | Work in progress
141 |  | Westmoreland | Haddo Primary and Infant |  | 42777000 | 16944800 | Repairs to roof and members, hardcourt, and electrical system to main classroom block as per Standard Building Code | 1 | TSU | D.R. Foote Construction Company Limited | 1 | Approval Granted | 2026-02-27 | 2026-10-04 | 20% & Below ; work in progress | Work to commence by week ending June 26, 2026 based on school operations
142 |  | Westmoreland | Porter's Mountain Primary |  | 23759530 |  | Replacement of roof and electrical repairs to main classroom block as per Standard Building Code | 1 | TSU | J Niel Construction Limited | 2 | Approval granted | 2026-02-23 | 2026-05-23 | 80% - 99% ; work in progress | Practical completion attained
143 |  | Westmoreland | Savanna-La-Mar Infant |  | 33406200 |  | Repairs to roof, ceiling, electrical, fencing to main classroom block as per Standard Building Code | 1 | TSU | Yardworks Construction Company Limited | 2 | Approval granted |  | 2026-10-02 | 20% & Below ; work in progress | Work in Progress
144 |  | Westmoreland | Savanna-La-Mar Primary |  | 93971280 |  | Repairs to roof, ceiling, associated electrical system and fencing of main classroom building as per Standard Building Code | 1 | TSU | Geecho Construction | 1 | Approval granted |  | 2026-10-02 | 41% - 50% ; work in progress | Work started. Logistics being addressed for movement of heavy equipment via adjacent Sav Infant and NWA properties
145 |  | St. James | Llandilo School of Special Education (Campus 3 - St. James) | 25000000 |  |  | Minor roof repairs, ceiling, flood damage to partition wall (moulds), electrical repairs and inspection/reconnection, collapsed security/safety wall near canal to main classroom building as per Standard Building Code | 1 | NET | Build rite |  |  |  |  | Contractor to be given site possession
146 |  | Hanover | Llandilo School of Special Education (Campus 2 - Hanover) | 20000000 |  |  | Roof, electrical, gutters, fencing to main classroom building as per Standard Building Code | 1 | NET | Build rite |  |  |  |  | Contractor to be given site possession
147 |  | Hanover | Knockalva Polytechnic College | 771360604.55 |  |  | General Repairs to: Farm managers house Chemistry, Physics and Biology Labs Computer Lab Library and Resource Centre Gazebo Kitchen Administration Girls and Boys Dormitory Health Centre Engineering Dept. Agro Processing Building Cottage 1-4 Principals Cottage Vice Principal Cottage Guest Cottage Farming Units Solar System Electrical | 1 | NET | Brothers Concepts | 1 |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 2% Kitchen - 25% Slab Cast, Tiles Hacked up Cottage Demo - 80% Principal and V. Principal cottage demolition - 80% Boys Dormitory Demo - 80% Scaffolding to boys dorm erected. Proposed Project Completion Date: January 31, 2027 Works done this week: Demolition of tiles and windows/door jambs to the Principals and vice principals cottages Comments/Issues:/Challenges: An additional 4 workmen have been added to the team, so currently there are 9 workmen onsite.
148 |  | St. James | Montego Bay Community College | 332167374.28 | 388973450.15 |  | Repairs to two campuses in St James and Westmoreland - roof replacement, roof repairs, waterproofing of roof slabs, window repairs as per Standard Building Code | 1 | NET | Brothers Concepts |  |  |  |  | 21% - 40% ; work in progress | Works ongoing
149 |  | St. James | Sam Sharpe Teachers' College | 70000000 |  |  | Replacement and or major repairs to all roofs, ceiling & guttering. Windows, doors, electrical repairs as per Standard Building Code | 1 | [6 empty] | works in progress | School undertaking the work
149 | TOTAL |  |  | 4620851697.94 | 11543060363.51 | 565728128.69

## REGION 5
POST-HURRICANE ASSESSMENT DATA ― IMPACT OF HURRICANE MELISSA ON SCHOOLS' INFRASTRUCTURE
No of Schools | Region | Parish | Name of School | Preliminary Cost $ | Contract Sum $ | Expenditure to Date $ | Scope of Works | PRIORITY 1. Severely Damaged - may affect school reopening. 2. Moderately Damaged - Significant repairs. School can operate while repairs are done. 3. Minor Damage - school can operate while repairs are done. | Person Responsible (TSU , NET, JSIF , DONOR) | Name of Contractor Assigned | Contractor Grade | Projected Date of Procurement for PS Approval | Contract Start date | Contract End Date | Status | Remarks
1 | 5 | St. Elizabeth | Middlesex Infant | 17854500 |  |  | 1. Minor roof and ceiling repairs 2. Restoration of fencing throughout school | 1 | NET | Maxwell Construction | 2 |  |  |  | Contractor to be given site possession | Project Percentage Completion: 0% Procurement - Contractor has been unresponsive to finalizing BQ as requested. Procurement to update way forward. Proposed Project Completion Date: TBD Issues:/Challenges: School is in dire need of fence being addressed.
2 |  | St. Elizabeth | Accompong Primary and Infant |  |  |  | Repairs to roof of main classroom block as per Standard Building Code | 1 | DONOR | [5 empty] | Work Completed | DONOR ALREADY EXECUTED REPAIRS-PROJECT COMPLETED
3 |  | St. Elizabeth | Beersheba Primary |  | 100364249.5 | 21416608.17 | Re-roofing works and repairs to ceiling of main classroom block as per Standard Building Code | 1 | NET | Build -Rite | 1 |  |  |  | 41% - 50% ; work in progress | Works commenced March 16, 2026 Overall Project Percentage: 50% Progress: 1 Roof sheeting installation (section #1) complete 100% Upcoming Events: 1. Persistent rainfall 2. Availability of skilled labour within the community due to the increased demand resulting in majority sourcing and importation of skilled labour from outside the parish to undertake the works Resolution:
4 |  | St. Elizabeth | Carisbrook Primary and Infant | 113385476 | 151980473.54 |  | Re-roofing works to include sarking to roof of main classroom block and re-roofing and ceiling repairs to single storey classroom block as per Standard Building Code | 1 | NET | Build -Rite | 1 |  |  |  | 20% & Below ; work in progress | Works commenced on April 20, 2026 Overall Project Percentage: 20% Progress: 1 Installation of roof slab to tuck shop: complete 100% Upcoming Events: 1. Availability of skilled labour within the community 4 2. Availability of housing accommodations in and around the area Resolution:
5 |  | St. Elizabeth | Clapham Primary and Infant |  | 46258240 | 46420279.2 | Re-roofing and repair works to include sarking to roof of main classroom block , Bathroom and Infant Department as per Standard Building Code | 1 | TSU | Southern Contracting Company | 1 | Approval granted | 2025-12-29 | 2026-03-10 | Work Completed | Part payment amounting to $20,133,010.00 submitted to Project Accounts for processing
6 |  | St. Elizabeth | Elderslie Primary and Infant |  | 74771850 | 53579938.28 | Repairs to roof of administration block. Roof repairs of Grades 1-3 Block as per Standard Building Code | 1 | NET | Maxwell Construction Limited | 2 | Approval granted | 2026-02-02 | 2026-08-01 | 80% - 99% ; work in progress | Project Percentage Completion: 97% Proposed Project Completion Date: August 28, 2026 Project Status: All Roofs and primary Learning space fixed. 100% Additional works on the school compound including a wall for safety and Covered Walkway 100% Issues:/Challenges:
7 |  | St. Elizabeth | Ginger Hill Primary | 68509111 | 124632320 |  | Repairs to roof of classroom block and Administrative Block as per Standard Building Code | 1 | NET | Cenitech | 1 | Approval granted | 2026-06-11 | 2026-12-10 | 41% - 50% ; work in progress | Project Percentage Completion: 50% Replacement of timber roofs - 100% Replacement of roof slab - 15% Renovation to bathroom - 10% Renovation to Canteen - 10% Proposed Project Completion Date: TBD Issues:/Challenges: Contractor pace has slowed significantly due to cash flow constraints. Awaiting processing of first payment.
8 |  | St. Elizabeth | Glen Stuart Primary, Infant and Special Education | 120591900 | 134300100 |  | Re-roofing and repairs to two (2) storey administration block (Block A), Block B and Re-roofing and repairs to Infant Department as per Standard Building Code | 1 | NET | FSC | 2 | Approval granted |  |  | 61% -79% ; work in progress | Works commenced, February 9, 2026 Overall Project Percentage: 69 % Progress: 1. Re-roofing of Grade 4 Block 2. Re-roofing of Grade 5 Block 3. Re-roofing of Grade 6 Block 4. Re-roofing of Infant Department Upcoming Events: N/A Issues: 1. No payments disbursed Resolution: 1. Contract finalization in progress
9 |  | St. Elizabeth | Holland Primary |  | 23982240 | 21885850 | Installation of water harvesting & sanitation, water storage and water pumps | 1 | TSU | J. Neil Construction | 3 | Approval granted | 2026-01-26 | 2026-08-27 | 80% - 99% ; work in progress | Part payment made; Completion to works delayed by severe weather.
10 |  | St. Elizabeth | Kilmarnock Primary and Infant | 104935551.1 |  |  | To repair damaged roof sections on block A - C. To apply waterproofing to administration block. The construction of a concrete base for water tanks. The construction of a perimeter fence as per Standard Building Code | 1 | NET | Roger Land Development | 1 |  |  |  | Contractor to be given site possession | Project Percentage Completion: 0% Proposed Project Completion Date: January 20, 2027 Project Status: Letter of commencement issued on July 20, 2026 Issues:/Challenges: Works on starting on time.
11 |  | St. Elizabeth | Lacovia Primary and Infant |  | 35717885 | 14877438.96 | Replacement of Admin Building and Bathroom roofs(previously timber framed) with reinforced concrete slabs as per Standard Building Code | 1 | NET | Howard Construction | 2 | Approval granted | 2026-02-19 | 2026-09-18 | 80% - 99% ; work in progress | Project Percentage Completion: 90% Reroofing of Admin Office - 100% Electrical works for Admin Office - 100% Plumbing works for Admin Office - 90% Floor restoration for Admin Office - 100% Reinstallation of Countertops and cabinets - 80% Reroofing of Student Bathroom - 100% Electrical works for Student Bathroom - 100% Plumbing works for Student Bathroom - 100% Proposed Project Completion Date: August 2026 Comments/Issues:/Challenges: The replacement of cabinets and counters was not initially scoped therefore the overall percentage was adjusted and confirmation of Taking Over deferred
12 |  | St. Elizabeth | Merrywood Primary |  | 53216000 |  | Re-roofing and ceiling repairs to Block A as per Standard Building Code | 1 | NET | Chins Construction | 1 |  |  |  | 61% -79% ; work in progress | Project Percentage Completion: 64% Reroofing of Block A - 100% Reroofing of Block B - 100% Reroofing of Cottage - 100% Electrical installation in Cottage - 30% Plumbing installation in Cottage - 0% Wall Finishes for Cottage - 10% Proposed Project Completion Date: August 2026 Comments/Issues:/Challenges: Contractor has halted works waiting for contract to be able to process first payment. Cash Flow has been disrupted by outstanding claims across all projects.
13 |  | St. Elizabeth | Retirement Primary and Infant |  | 26514000 | 12231500 | Repairs to roof of main classroom block as per Standard Building Code | 1 | TSU | K&R Associates | 2 | Approval granted | 2026-02-02 | 2026-03-31 | Work Completed | Request for Addition Funding for works not measured & Follow-on Contract for internal works.
14 |  | St. Elizabeth | Springfield Primary | 124640000 |  |  | To repair damaged roofs and ceiling repairs to administrative block, two (2) Classroom Blocks, Industrial Arts Block. To waterproof Block G & F. Repair 5 cottages. Re-construct perimeter fencing as per Standard Building Code | 1 | NET | J&H Construction | 1 | Approval granted | 2026-01-05 | 2026-07-04 | 61% -79% ; work in progress | Project Percentage Completion: 65% Proposed Project Completion Date: January 31, 2027 Project Status: Roofing – 100% Ceiling – 100% ECC Block – 0% Rest Room – 0% Walkway – 0% JPS Re-connection – 0% Issues:/Challenges: • A contract is not in place. • The contractor appears to have withdrawn his team from the site. • Delays in reestablishing the JPS connection. • The expansion of the existing bathroom facilities instead of rebuilding the previous bathrooms. • Work has not started on the infant school. • Repair works may not be completed in time for next school year.
15 |  | St. Elizabeth | Lewisville High |  | 689893620 | 162688499.2 | Re-roofing and ceiling repairs to administrative block, two (2) Classroom Blocks, Industrial Arts Block as per Standard Building Code | 1 | NET | Southern Contracting Company Limited | 1 | Approval granted | 2026-01-22 | 2026-07-22 | 51% - 60% ; work in progress | Project Percentage Completion: 60% Proposed Project Completion Date: December 31, 2026 Project Status: Block A – 80% Block B – 80% Block C – 80% Block D – 50% Block E – 90% Block F – 10% Block G – 10% Literacy Cafe – 10% Security Post and Covered Entrance – 95% Teachers Cottage 1 – 70% Teachers Cottage 2 – 70% Teachers Cottage 3 – 70% Teachers Cottage 4 – 70% Principals Cottage – 70% External Works (Link-ways) – 50% External Works (Perimeter Fence) – 50% External Works (Lightning Protection System) – 0% External Works (Signage) – 0% Issues:/Challenges: ●Significant scope creep, most of which has resulted in delays. ●Costing for additional changes. ●Request that all focus be placed on functional areas. ●Repair works may not be completed in time for next school year.
16 |  | St. Elizabeth | Bogue Primary and Infant | 49323492 | 51434830 |  | Re-roofing and repairs to ceiling of main classroom block to include fencing repairs as per Standard Building Code | 1 | NET | Cenitech | 1 |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 12% Proposed Project Completion Date: August 2026 Project Status Works done in the week of the current period: Roof demolition complete. roof framing work commence Temporary Classroom completed for Summer activities Works to be done is next period: Roof framing to continue. Challenges/Issues: nil
17 |  | St. Elizabeth | Burnt Savannah Primary | 40000000 |  |  | Replacement of roof sheeting and framing across entire school property inclusive of classrooms and offices as per Standard Building Code | 1 | NET | Yardworks | 1 |  |  |  | Work to Commence | Project Percentage Completion: 0% Contractor stripped roof and indicated materials have been ordered Reroofing of Admin Office - 0% Electrical for Admin Office - 0% Reroofing of Grade 5&6 - 0% Electrical for Grade 5&6 - 0% Reroofing of Grade 4 - 0% Restoration of temporary Grade 4 structure - 0% Electrical for Grade 4 - 0% Reroofing of Grade 1 - 0% Restoration of temporary Grade 1 structure - 0% Electrical for Grade 1 - 0% Proposed Project Completion Date: TBD Comments/Issues:/Challenges: Contractor has been mobilised. Substantial works to be confirmed
18 |  | St. Elizabeth | Marie Cole Memorial Primary |  | 15218000 |  | Repairs to roof and electrical system of main classroom block as per Standard Building Code | 1 | TSU | Maxwell Construction Limited | 2 | Approval granted | 2026-01-09 | 2026-03-09 | Work Completed
19 |  | St. Elizabeth | Park Mountain Primary and Infant |  | 159713733.52 | 56534083.86 | Repairs to roof for primary and infant department. Revamp of infant department bathroom as per Standard Building Code | 1 | NET | Proven Construction | 1 |  |  |  | 61% -79% ; work in progress | Contractor has notified the suspension of works effective July 3, 2026, pending finalisation of contract and outstanding payment
20 |  | St. Elizabeth | Quickstep Primary |  |  |  | Re-roofing and ceiling repairs to Main Classroom Block and Student Bathroom Block as per Standard Building Code | 1 | NET | C&D Construction | 1 |  |  |  | Contractor to be given site possession | Project Percentage Completion: 0% Proposed Project Completion Date: Project Status: Issues:/Challenges: BQ checked and corrections made for Contractor acceptance 28-07-2026.
21 |  | St. Elizabeth | Roses Valley Primary and Infant |  | 67455400 |  | Re-roofing and ceiling repairs, wall replacement to Main Classroom Block. Re-roof Block A and B. Re-roof Canteen as per Standard Building Code | 1 | NET | Chins Construction | 1 |  |  |  | 51% - 60% ; work in progress | Project Percentage Completion: 57% Classroom A:100% Classroom B and Library: 99% Main Classroom Block: 40% Canteen: 0% Proposed Project End Date: September 2026 Works done in the week of the current period: 1. Main Block: Roof structure in progress 2. Classroom A&B: Resheeting (one sheet and fascia outstanding) and ceiling complete 98% complete Works to be done is next period: 1. Main Block: Resheeting Issues/ Challenges: Contractor ceased work. Contract Outstanding. Certificate #1 prepared $ $20,699,702.00 May 14, 2026. material availability"
22 |  | St. Elizabeth | Thornton Primary and Infant |  | 74260500 |  | Re-roofing and repairs to ceiling of main classroom block and Administrative Block and Roofing repairs to Infant Department as per Standard Building Code | 1 | NET | Maxwell Construction Limited | 2 |  |  |  | 80% - 99% ; work in progress | Project Percentage Completion: 88% Reroof Infant: 100% Reroof Canteen/Library Block: 90% Reroof Staff Room/Class Block/Guidance: 80% Guttering: 90% Epoxy Floor: TBC Proposed Project Completion Date: August 17, 2026 Works done in the week of the current period: 1. Window installation completed 2. Partition commenced in classroom Works to be done is next period: Library: paint Guidance: paint General electrical work to commence Epoxy Floor Finish in the identified classroom. Issues/Challenge: Contractor Claim outstanding. Variation identified at infant block to be rectified. Awaiting Cost Proposal
23 |  | St. Elizabeth | St. Elizabeth Technical High |  | 73205890 | 57519048.7 | Roof repairs to classroom block | 1 | NET | Southern Contracting |  | Approval granted | 2026-02-02 | August 1, 2026 | Work Completed | Phase 1 Completed
[5 empty] | 310986764 | 57519048.7 | Roof repairs and general repairs to facilities | 1 | NET | Pavecon | 1 | Approval granted | 2025-11-18 | 2026-05-17 | 51% - 60% ; work in progress | "Project Percentage Completion: 55% Proposed Project Completion Date: August 2026 Project Status: Meeting held with Contractor July 8, 2026 to clarify workforce and progress. Justification for assessments required to support the water run-off challenges at the school submitted. Works done in the week of the current period: 1. Male Dorm: Tiling in progress, bathroom tiles continue, painting commenced 2. Female Dorm: Membrane completed. Painting in progress. Window installation complete 3. Grade 11 Block: Sheeting complete. Electrical first fix in progress. Wall construction as recommended by the Engineer commenced. Partitions commence. Doors installed 4. Admin block(unfinished building): Plumbing fixtures and window and door installation 90% complete, grill wok 90% complete 5. Teachers Cottage : nil 6. Media Building: Priming internal walls commence, 7. Principal Cottage: Work commenced. Roof framing in place, sheeting commence 8. Industrial Block: Sheeting 90% complete 9. Grade 9: Roof cleared for screeding 10. Bus Shed: 100% Works to be done is next period: 1. Male Dorm: Tiling in progress, window installation, clean up. 2. Female Dorm: Ceiling rendering to be completed, tiling to commence 3. Admin block(unfinished building):Outstanding doors (2 No.), Fixtures and membrane 4. Teachers Cottage: Section of roof/ceiling to be rectified, minimal painting works 5. Preparations: Sheeting to progress 6. Media Building: Rendering continues 7. Pavilion: Electrical 8. Playfield: Lights 9. Boundary Wall: Additional weep holes to be included. Issues:/Challenges: Work force and flow . No intermediary doors in partitions at Grade 11 Block. Contractor advised it is requirement by our standards and Fire.
24 |  | St. Elizabeth | Sydney Pagon STEM Academy |  | 654929435.83 | 147689511.72 | Re-roofing and ceiling repairs to Grade 7 Classroom Block, Auditorium, Staff Room Block, Guidance Laboratory, staff flatlets, male and female student dormitories as per Standard Building Code | 1 | NET | Denron Engineering | 1 | Approval granted | 2026-02-26 | 2026-08-25 | 41% - 50% ; work in progress | Project Percentage Completion: 48% Proposed Project End Date: August 2026 Project Status: Works done in the week of the current period: 1. Female Dorm#1: Clean up. 2. Female Dorm #2&#3: Sheeting complete 3. Male Dorm#1: Finishes in progress 4. Male Dorm 3&4: Sheeting complete. 5. Common House:100% Complete 5. Teachers Cottagex2 : Roof Complete (Sheeting commenced). 6. Teachers Flat#2. Form work removed, dressing on outside commenced, electrical work commence 7. Tractor House: Boxed eaves complete 8. B No. 2 roof to commence 9 Piggery: Sheeting and purlins 85% complete. Electrical work in progress 10. Staff Room: form removed. rendering in progress 11. Link Way @ Staff Room: rendering in progress 12. Walkway @ Staff Room: rendering in progress 13. Science Block: ceiling in progress 14. Generator Room: 100% 15. E-Learning/Computer Lab: Ceiling and electrical complete Works to be done is next period: 1. Grade 7 Block: ceiling work to commence, door jams to be rectified 2. Female Dorm #2&#3: Fascia Board, fascia cap, ceiling and doors Female #1- Waterproofing to commence, lattice at transom to be installed 3. Male Dorm #1: Final painting and clean up Male Dorm 3&4: Termite Treatment, Doors installation. ceiling and doors to commence 4. Teachers Cottage: Ceiling work to commence 5. Tractor House: Office Ceiling to commence 7. Boiler Room NO. 1 -added meshwork to commence 8. Boiler Room: No. 2 Roof work to progress 9. Piggery: Sheeting in progress. Continued electrical 10. Dairy House: Electrical work to be completed. 11. Science Block: Fascia board and ceiling to be complete 12. Horticulture: Ceiling work to be complete 13.Guardhouse: works in progress 14. Machine Shop: Ceiling to commence 15.Ancillary Room: Ceiling ,fascia board, boxed eaves to be complete Issues:/Challenges: Delays in the fabrication of purlins. Certificate #2 $74,397,929.60 PAID work coordination to improve. The school hosts campers and 2 female dorms will be occupied and work ceased temporarily.
25 |  | St. Elizabeth | Ballards Valley Primary |  | 24147380 | 21194620 | Re-roofing and renovation of Grade 1 & 6 blocks and student bathroom as per Standard Building Code | 1 | TSU | Southern Contracting Company | 1 | Approval granted | 2025-12-29 | 2026-08-21 | Work Completed | Part payment made; Final payment documents being prepared.
26 |  | St. Elizabeth | Brinkley Primary and Infant |  | 68276510 | 18303126.8 | Replacement of classroom block roof with reinforced concrete slab roofing inclusive of structural modification to columns and beams to support new roof system as per Standard Building Code | 1 | NET | Southern Contracting Company | 1 | Approval granted | 2026-03-24 | 2026-09-23 | 80% - 99% ; work in progress | Project Percentage Completion: 85% Foundation - 100% Columns - 100% Beams - 100% Electrical works - 80% Windows and doors- 100% Ramp & railings - 90% Roof waterproofing - 85% Wall finishes - 90% Floor Finishes(Epoxy) - 90% Proposed Project Completion Date: August 2026 Comments/Issues:/Challenges:
27 |  | St. Elizabeth | Mayfield Primary and Infant |  | 22200000 |  | Roof repair to Grades 4-6 Classroom Block, lifting of membrane to two storey classroom block. Roof repairs to the infant department as per Standard Building Code | 1 | DONOR | [5 empty] | 80% - 99% ; work in progress | Project Percentage Completion: 99% Proposed Project Completion Date: Project Status: Cosmetic defects to be completed Issues:/Challenges:
28 |  | St. Elizabeth | Hampton School |  | 163301686 | 81831882.9 | Replacement of roofing and restoration of electrics, fixtures and finishes at Dorms, Admin, Science Labs, Art Room, Home Econ Lab and minor repairs to several areas across the school as per Standard Building Code | 1 | NET | Denron Engineering | 1 | Approval granted | 2025-12-01 | 2026-06-15 | 51% - 60% ; work in progress | Project Percentage Completion: 55% Reroofing of Dorms - 100% Repainting Dorms - 100% Replace doors and windows at Dorms - 100% Reroofing Labs - 100% Installation of Ceiling in Labs - 90% Electrical works in Labs - 100% Replacement of doors at Labs - 100% Construction of linkway cover along Lab corridor - 90% Reroofing of Art Room - 100% Electrical works in Art Room - 70% Finishes in Art Room - 70% Reroofing at Home Econ Lab - 20% Electrical works Home Econ Lab - 0% Renovation of Home Econ Lab - 0% Reroofing at Admin Building - 0% Electrical works Admin Building - 0% Roof repairs to Laundry room - 0% Ceiling replacement for Laundry room - 0% Minor repairs across school - 10% Proposed Project Completion Date: August 2026 Comments/Issues:/Challenges: A laundry room attached to the Dorm facilities was identified in July 2026 and now added to the scope of works for roof and ceiling repairs
29 |  | St. Elizabeth | Munro College |  | 137743857.34 | 44241490.64 | Replacement of roof with reinforced concrete slab and renovation to Coke Building Replacement of roof to Biology Lab Repair of Guidance Office ceiling and minor repair to roof Repair of water tank covers at Hostel Facility as per Standard Building Code | 1 | NET | Denron Engineering | 1 | Approval granted | 2025-12-01 | 2026-06-16 | 61% -79% ; work in progress | Project Percentage Completion: 75% Replacement of Roof on Coke Building - 100% Installation of ceiling on Coke Building - 90% Installation of classroom wall partitions on Coke Building - 90% Electrical works for Coke Building - 100% Finishing of classroom wall partitions on Coke Building - 50% Replacement of windows and doors on Coke Building - 100% Replacement of Biology Lab Roof - 100% Installation of ceiling in Biology Labs - 100% Restoration of Biology Labs fixtures and finishes - 20% Resheeting and frame repair of water tanks at Hostel - 100% Replacement of ceiling at Guidance Office - 100% Proposed Project Completion Date: August 2026 Comments/Issues:/Challenges:
30 |  | St. Elizabeth | Sandy Bank Infant | 20000000 |  |  | Repairs to damaged roof of main classroom block as per Standard Building Code | 1 | NET | Maxwell Construction | 2 | 2026-01-05 |  |  | Contractor to be given site possession | Project Percentage Completion: 0% Procurement/Donor - Design & Build engagement or Donor support to be initiated Proposed Project Completion Date: TBD Issues:/Challenges: Structural defects were noted by the initial site visit
31 |  | St. Elizabeth | Black River Primary and Infant |  | 564829194.56 |  | Repairs to roof of main classroom blocks as per Standard Building Code. Replacement of windows and doors, repairs to sanitary block and fencing. | 1 | NET | Proven Construction | 1 | Approval granted | 2026-02-18 | 2026-08-17 | 61% -79% ; work in progress | Contractor has notified suspension of works effective July 3, 2026 pending finalization of contract and outstanding payment. Contractor has now provided relevant insurance to finalise contract, which will be issued the first week of August
32 |  | St. Elizabeth | Brompton Primary |  | 168080714 | 39379922.98 | Reconstruction of the Infant Block, repair damaged roofs on all the affected buildings at the primary school. Construction of a reinforced roof slab on the canteen block as per Standard Building Code | 1 | NET | HDB Construction | 1 | Approval granted | 2026-02-10 | 2026-08-09 | 21% - 40% ; work in progress | Project Percentage Completion: 40% Proposed Project Completion Date: December 31, 2026 Project Status: Infant Block – 50% Library – 10% Rest Room – 10% Building A – 30% Building B – 10% Building C – 0% Canteen – 40% Issues:/Challenges: • Payment delays. • The contractor's progress is very slow in general. • Additional items of work were added to the scope. • Repair works may not be completed in time for next school year.
33 |  | St. Elizabeth | Crawford Primary and Infant | 49380988 | 52130988 | 9774882.15 | Re-roofing repairs to single-storey classroom block and replacement of windows to administrative block as per Standard Building Code | 1 | NET | Build Rite | 2 | Originally assigned to T.S.U. Re-assigned to N.E.T | 2026-03-23 | 2026-09-22 | 51% - 60% ; work in progress | Works commenced on March 23, 2026 Overall Project Percentage: 60% Progress: 1 Installation of roof slab to tuck shop: on-going 90% 1 Persistent rainfall 3 Availability of skilled labour within the community ; 2. Availability of housing accommodations in and around the area Resolution:
34 |  | St. Elizabeth | Fullerswood Primary and Infant |  | 57454455.5 |  | Re-roofing repairs to Infant department, Principals Office Main building and Restrooms. Removal of damaged whiteboard and Installation of new white boards. Replace doors installation of chain-link fence and gate, painting and electrical works as per Standard Building Code | 1 | NET | HDB Construction | 1 | Approval granted | 2026-02-11 | 2026-08-10 | 21% - 40% ; work in progress | Project Percentage Completion: 35% as of July 24, 2026. Project Status: Re-sheeting of the Infant Department is to commence; 1st coat of painting of the bathroom completed; fencing works have commenced. Proposed Project Completion Date: September 3 2026 Issues:/Challenges: Labour shortage has impacted the work pace.
35 |  | St. Elizabeth | Fyffes Pen Primary and Infant |  | 304767100 |  | Repairs to damaged roof of main classroom block of Primary School and roof repairs to the Infant Department as per Standard Building Code | 1 | NET | Southern Contracting Company | 1 |  |  |  | 21% - 40% ; work in progress | Works commenced May 2026 Overall Project Percentage: 24% Progress: 1 Formwork for belting in Block A 100% completed. 2 Casting of Belting in Block A 95% completed 3 Formwork to cross beam Block A 100% completed. 4 Flashing of masonry block walls in Block A 50% completed. 5 Formwork& support to suspended slab Block A 60% completed Upcoming Events: 1 Fix slab reinforcement of 20mm corrugated steel Block A. 2 Fix slab reinforcement of 13mm corrugated steel Block A 3 Demolish existing building Infant department. 4 Pour 150mm suspended concrete slab Block A Issues: 1 As per discussion with the Principal, the furniture and other items were not fully removed from the Basic school to be relocated to the finished food for the poor building. As a result, demolition has been delayed pending full evacuation of the area. Resolution: 1 Building will be fully vacated by Friday the 24th of July 2026 to allow demolition to proceed.
36 |  | St. Elizabeth | Geneva Primary |  | 20358500 |  | Re-roofing and ceiling repairs to main classroom block to include structural steel repair works as per Standard Building Code | 1 | TSU | Maxwell Construction Limited | 2 | Approval granted | 2026-01-09 | 2026-03-09 | Work Completed
37 |  | St. Elizabeth | Hopewell Primary |  |  |  | Re-roofing and ceiling repairs to the two (2) storey main classroom block and repairs to roof of student bathroom block as per Standard Building Code | 1 | DONOR | Clare Lionel Foundation |  |  |  |  | 41% - 50% ; work in progress | Project Percentage Completion: 48% as of July 24, 2026. Project Status: Work is being executed by the Donor. Proposed Project Completion Date: TBD Issues:/Challenges:
38 |  | St. Elizabeth | Middle Quarters Primary |  | 125619901 | 25822165.54 | Repairs to roof of the Infant and Primary Department and student bathroom as per Standard Building Code | 1 | NET | HDB Construction | 1 | Approval granted | 2026-02-09 | 2026-08-08 | 21% - 40% ; work in progress | Project Percentage Completion: 30% Proposed Project Completion Date: December 31, 2026 Project Status: Block A – 80% Block B– 0% Block C – 0% Bathroom – 90% Fencing – 50% Issues:/Challenges: • Payment delays. • The contractor's progress is very slow in general. • Existing nag building is to be demolished and a new building constructed in it s place. • Repair works may not be completed in time for next school year.
39 |  | St. Elizabeth | Mountainside Primary |  | 48260618 |  | Repairs to roof of main classroom as per Standard Building Code | 1 | TSU | Southern Contracting Company | 1 | 2026-08-03 | 6 weeks | 2026-09-15 | Contractor to be given site possession | Awaiting approval Memo from TSU
40 |  | St. Elizabeth | Newcombe Valley Primary |  | 31285550 | 14934300 | Re-roofing and ceiling repairs to the main classroom block as per Standard Building Code | 1 | TSU | Maxwell Construction Limited | 2 | Approval granted | 2026-01-09 | 2026-03-09 | Work Completed | Part Payment made
41 |  | St. Elizabeth | Parottee Primary |  | 84984000 | 56534083.86 | Re-roofing and ceiling repairs to the main classroom block and student bathroom as per Standard Building Code | 1 | NET | K& R & Associates |  |  | 2026-03-09 | 2026-09-08 | 61% -79% ; work in progress | Works commenced March 9, 2026 Overall Project Percentage: 70% Progress: 1. All roofs (main building, bathroom, and library) are 100% complete. 2 Library floor demolished and cast. 3 Preparation of areas and painting of ceilings and metal members. 4 Installation of partition framing for classrooms is complete. 5 Installation of partition cladding for classrooms is complete. 6 Installation of wall cladding for classrooms is complete. 7 Installation of ceilings to office and kitchen areas is 80% complete. 8 Electrical installation for all areas (classrooms, library, and bathroom) is 75% complete. Upcoming Events: 1. Continue electrical installation. 2. Installation of ceilings to the Principal's office and kitchen areas. 3. Cleaning of internal areas to allow painting to continue. 4. Assessment of bathroom for plumbing works. 5. Assessment of sick bay for renovation. Issues: 1 The works are currently assessed at 70% completion, and it is evident that significant resources have been expended to achieve this result. We are therefore requesting, once again, that urgency be applied to the honouring of submitted certificates. Resolution: 1. Expedited payment for the works detailed in Certificate No. 1 would be sufficient to address this matter.
42 |  | St. Elizabeth | Pondside Primary | 145511033.19 |  |  | Replacement of classroom block roof with reinforced concrete slab roofing inclusive of structural modification to columns and beams to support new roof system as per Standard Building Code | 1 | NET | J&H Construction | 1 | Approval granted | 2026-01-26 | 2026-07-25 | 21% - 40% ; work in progress | Project Percentage Completion: 30% Project Status: Slab to be poured on Block A, awaiting the concrete from the supplier. Formwork for columns and beams is ongoing at Block B. Proposed Project Completion Date: September 30, 2026 Issues:/Challenges: Work was delayed with the pouring of the concrete due to technical malfunctions of the supplier. Delayed submission of contract documents has resulted in delayed claims.
43 |  | St. Elizabeth | Sandy Bank Primary |  |  |  | Re-roofing and ceiling repairs to administrative block as per Standard Building Code | 1 | DONOR | [5 empty] | 80% - 99% ; work in progress | German Government. Donor to execute the project
44 |  | St. Elizabeth | Slipe Leased Primary and Infant |  | 115162175 |  | Re-roofing of existing classroom blocks for Grades 1-4, installation of partitions, and replacement of the classroom block for Grades 5-6 roof with reinforced concrete slab roofing, inclusive of structural modification to columns and beams to support the new roof system, electrical works, installation of fencing to the Infant Department as per Standard Building Code | 1 | NET | chins Equipment & rental | 1 | Approval granted | 2026-02-09 | 2026-08-08 | 21% - 40% ; work in progress | Project Percentage Completion: 40% Project Status: Continuation of formwork installation to columns on the Grade 6 Block and for the Infant Department; continuation of reinforcement installation to the concrete slab. Proposed Project Completion Date: August 2026 (Infant Department), September 2026 (Grade 6 Block) Issues:/Challenges: None
45 |  | St. Elizabeth | Black River High | 355540306 | 368884926 | 39879080 | Re-roofing and electrical repairs of Classroom Blocks, nurses' station, guidance department, administrative office, canteen/tuck, auditorium. Reconstruction of abattoir, reconstruction of the external fencing as per Standard Building Code | 1 | NET | Pavecon | 1 |  |  |  | 20% & Below ; work in progress | Overall Project Percentage: 8% Progress: 1. Auditorium- Roof and Interior cleanup works – 100% 2. Library and Administrative Building- Removal of Waterproof Membrane from Roof Slab – 100% 3. Cafeteria- Removal of Waterproof Membrane from Roof Slab – 100% 4. Block D- Removal of Waterproof Membrane from Roof Slab – 100% 5. Block F- Removal of Waterproof Membrane from Roof Slab – 100% 6. Block C- Removal of Waterproof Membrane from Roof Slab – 80% 7. Block A- Removal of Waterproof Membrane from Roof Slab – 80% • Removal of damaged existing Timber framed Roof system – 80% Upcoming Events: 1. Complete clean up and removal of waterproof membrane debris on Rotary Roof 2. Construct Ring beam around Auditorium to level of Brickwork 3. Commence Structural steelwork for Auditorium 4. Commence Foundation works for the Wall and Security Room 5. Block A changed to concrete slab – steel pipe scaffolding works to commence Issues: 1. Supply chain issues continue to be a major challenge especially relating to roofing supplies and, more recently, cement. 2. Delays are also due to awaiting Engineer drawings for Slab, Guard house and Abattoir. Resolution: No resolutions noted
46 |  | Manchester | Ferguson Primary and Infant | 5000000 | 22686976 | 8971750 | Re-roofing and ceiling repairs to the main two (2) storey classroom block as per Standard Building Code | 1 | TSU | Velka Construction | 3 | Approval granted | 2026-01-19 | 2026-03-09 | Work Completed | Part payment made. Final payment documents submitted.
47 |  | Manchester | Grove Town Primary and Infant |  | 40272440 | 12841420 | Re-roofing & renovation work to main classroom block as per Standard Building Code | 1 | TSU | Southern Contracting Company | 1 | Approval granted | 2026-01-12 | 2026-03-10 | Work Completed | Second payment made; Completion to works delayed by severe weather.
48 |  | Manchester | Bishop Gibson High |  | 28767346.07 |  | Roofing and ceiling repairs to the Annex Block (Block C), Administrative Block (Block A) and Block B as per Standard Building Code | 1 | TSU | Denron Engineering | 1 | Approval granted | 2026-02-02 | 2026-04-29 | Work Completed | Second payment made. Final payment documents being prepared.
49 |  | Manchester | Manchester High |  | 91425000 | 52938319.7 | Re-roofing and ceiling repairs to third form classroom block, sixth form and second form classroom blocks as per Standard Building Code | 1 | NET | Pavecon | 1 | Approval granted | 2025-12-01 | 2026-06-01 | 80% - 99% ; work in progress | Works completed Taking over inspection of renovated facilities is being scheduled for W/E July 31, 2026
50 |  | Manchester | Comfort Hall Primary and Infant |  | 23798100 | 13668208 | Re-roofing & renovation work to main classroom block as per Standard Building Code | 1 | TSU | J. Neil Construction | 3 | Approval granted | 2026-01-12 | 2026-03-10 | Work Completed | Second payment submitted; Completion to works delayed by severe weather.
51 |  | Manchester | New Green Primary and Infant |  | 36019410 |  | Re-roofing and ceiling repairs to Blocks A and B | 1 | TSU | Dutch Construction Limited | 3 | Approval granted | 2026-02-11 | 2026-03-24 | Work Completed | Part payment made. Completion to works delayed by severe weather.
52 |  | Manchester | St. Paul's Primary and Infant |  | 22850000.12 | 19287755.52 | Re-roofing and ceiling repairs to the main classroom block as per Standard Building Code | 1 | TSU | Cambridge Trading Limited | 3 | Approval granted | 2026-01-12 | 2026-03-10 | Work Completed | Part payment made. Final payment documents being prepared.
53 |  | Manchester | Mile Gully High |  | 41050060 | 15853190 | Re-roofing & ceiling repairs to the main two (2) storey classroom block and Grade 9 Classroom block as per Standard Building Code | 1 | TSU | Southern Contracting Company | 1 | Approval granted | 2026-01-12 | 2026-03-10 | Work Completed | Second payment submitted; Completion to works delayed by severe weather.
54 |  | Manchester | Bryce Primary | 26131000 | 47194350 | 34025210.5 | Re-roofing and ceiling repairs to the two (2) storey lightweight administrative block to include structural repairs. Re-roofing and ceiling repairs to Block D to include structural repairs as per Standard Building Code | 1 | NET | Cenitech | 1 | Approval granted | 2026-04-08 | 2026-11-07 | Work Completed | Work completed
55 |  | Manchester | Chantilly Primary and Infant |  | 55034035 |  | Grade 5/6 Block is to be demolished and replaced by a new building . Modification of sections of the main classroom block to provide space for guidance councillor, sick bay and additional classroom as per Standard Building Code | 1 | NET | K& R & Associates | 1 | Approval granted | 2026-07-29 | 2027-01-01 | 20% & Below ; work in progress | Project Percentage Completion: 2% Proposed Project Completion Date: January 31, 2027 Comments/Issues/Challenges: Schematic designs have been prepared and circulated to key stakeholders; stakeholder feedback is required by July 31, 2026. Letter of Award/contract documents are still to be issued to the Contractor
56 |  | Manchester | Christiana Moravian Primary and Infant |  | 18646860 | 17046860 | Re-roofing and ceiling repairs to the two (2) storey administrative block as per Standard Building Code | 1 | TSU | Duke's Electrical and Building Solution | 2 | Approval granted | 2025-12-29 | 2026-02-24 | Work Completed | Part payment made amounting to $13,634,905.00. Final payment documents submitted.
57 |  | Manchester | Craighead Primary |  | 23229700 | 11857300 | Re-roofing & ceiling repairs to main classroom block and Canadian-style block as per Standard Building Code | 1 | TSU | Duke's Electrical and Building Solution | 2 | Approval granted | 2025-12-29 | 2026-02-24 | Work Completed | Part payment made amounting to $11,857,300.00; Final payment document being prepared.
58 |  | Manchester | Mizpah Primary |  | 22975995 | 12215500 | Roofing and ceiling repairs to the main classroom block as per Standard Building Code | 1 | TSU | Velka Construction | 3 | Approval granted | 2026-01-09 | 2026-03-09 | Work Completed | Part payment made; Final payment document being prepared.
59 |  | Manchester | Pike Primary and Infant |  | 53748500 | 25242928.33 | Re-roofing and electrical repairs of classroom block as per Standard Building Code | 1 | NET | Slyvester Enterprise | 1 | Approval granted | 2026-03-23 | 2026-09-22 | 61% -79% ; work in progress | Project Percentage Completion: 65% Resheeting :100% Electrical: 60% Painting: 30% Proposed Project Completion Date: August 2026 Works done in the week of the current perd : Door installation to commence. Painting and electrical work in progress. Works to be done is next period :electrical work complete, painting to complete and door installation to complete Issues:/Challenges: progress slow, contractor advised this needs improvement
60 |  | Manchester | Robins Hall Primary and Infant | 37917420 |  |  | Re-roofing and ceiling repairs to the Infant Department as per Standard Building Code | 1 | NET | Dwight's Construction | 1 |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 1% Proposed Project Completion Date: TBD Project Status: Demolition started and halted due no contract Issues:/Challenges: Documents still outstanding for contractor. No contract in place
61 |  | Manchester | Holmwood Technical High |  | 367429570.08 | 84704725.25 | Re-sheeting and associated electrical repairs of auditorium, administrative block, Jordan block, Industrial/ Technical block and rebuilding of Barnes Hall and the dormitory facilities as per Standard Building Code | 1 | NET | C&D Construction | 1 | Approval granted | 2026-02-10 | 2026-08-09 | 41% - 50% ; work in progress | Project Percentage Completion: 50% Proposed Project End Date: July 2026 Works done in the week of the current period: 1. Auditorium: Electrical 2. Admin Block: Ceiling work in progress 3.Technical Block: Purlins being welded and bolted. 4. Certificate #2 $31,623,792.12 PAID Works to be done in next period: 1. Auditorium : Fans to be installed, fascia board to installed and painted, electrical 2. Administrative Block: Ceiling work in progress 3. Revised Work Schedule to be submitted by Contractor 4.Technical Block: Work in progress Issues/ Challenges: Admin Ridge joints to be sealed. Site organisation to be addressed. Ply- Cem/ Material shortage. Certificate #3 $31,076,758.56 submitted July 17, 2026 **Electrical Upgrade: Justification submitted to procurement and awaiting update.** **Design and Build: Feedback from Contractor to be received-Note sent July 2026 to the Contractor (meeting to be set with stakeholders subsequently) Contractor will complete the required Surveyor's ID Report**
63 |  | Manchester | Knox Community College (Cobbla Campus) |  | 336884425 |  | Repairs to 17 buildings on the campus in 2 phases [Domes, Administration Block, Engineering (TD), Electrical Technology Dept, Mechanical & Construction, Sporting Pavillion, Canteen/Auditorium] as per Standard Building Code | 1 | NET | Lottis Project Limited |  |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 11% Canteen/Auditorium 70% - has been temporary halted, awaiting completion of electrical infrastructure upgrades being undertaken separately by the College. Mechanical & Construction and Administration Blocks - 10%. Demolition work on roofs is practically complete Proposed Project Completion Date: Project Status: Contract issued on June 17, 2026. Work which had been stalled for weeks has now been resumed Issues:/Challenges: Issue of contractors awaiting contract document has now been resolved
62 | TOTAL |  |  | 1278720777.29 | 5754021858.98 | 1228205803.71

## REGION 6
POST-HURRICANE ASSESSMENT DATA ― IMPACT OF HURRICANE MELISSA ON SCHOOLS' INFRASTRUCTURE
No of Schools | Region | Parish | Name of School | Preliminary Cost $ | Contract Sum $ | Expenditure to Date $ | Scope of Works | PRIORITY 1. Severely Damaged - may affect school reopening. 2. Moderately Damaged - Significant repairs. School can operate while repairs are done. 3. Minor Damage - school can operate while repairs are done. | Person Responsible (TSU , NET, JSIF , DONOR) | Name of Contractor Assigned | Contractor Grade | Projected Date of Procurement for PS Approval | Contract Start Date | Contract End Date | Status | Remarks
1 | 6 | St. Catherine | Top Hill Primary |  | 47256565 |  | Repairs to the following facilities: Main Classroom Block Grades 5/6 Classroom Kitchen Corridor, Bathroom External Works: - collapsed pit slab - construct wall at Infant Department As per Standard Building Code | 1 | NET | Dwight's Construction | 1 |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 5% Main Classroom Block -0% Grades 5/6 Classroom - 20% Kitchen - 5% Corridor, Bathroom - - 0% External Works - 0% - collapsed pit slab - construct wall at Infant Dept Proposed Project Completion Date: Comments/Issues:/Challenges: Work is resumed on July 27, 2026
2 |  | St. Catherine | Rosemount Primary and Infant |  | 42947500 | 16060800 | Emergency Waterproofing of Reinforced Concrete Roofs: Canteen Block and Administrative Block as per Standard Building Code | 1 | TSU | Dukes Electrical & Construction | 2 | Approval granted | 2026-01-12 | 2026-07-17 | 80% - 99% ; work in progress | Final account to be prepared
3 |  | St. Catherine | McGrath High |  | 70693036 |  | Waterproofing of the administrative block and Re-sheeting of Roofs at Canteen Block, Construction of roof Slab at Principal Block, Repairs to Metal Tank & Chain-link Fence as per Standard Building Code | 1 | TSU | Cambridge Trading Limited | 3 | 2026-01-27 | 2026-02-16 | 2026-08-14 | 51% - 60% ; work in progress | Work in progress
4 |  | St. Catherine | Southborough Primary |  | 27996000 | 24370875 | Proposed Emergency Waterproofing of Blocks 1-4 Reinforced Concrete Roofs as per Standard Building Code | 1 | TSU | Duke's Electrical & Building Solutions | 2 | 2026-01-27 | 2026-02-16 | 2026-05-15 | 80% - 99% ; work in progress | Final account to be prepared
5 |  | St. Catherine | Dinthill Technical High |  | 52947890 |  | Proposed Re-Sheeting of Roofs: Engineering Block, Grade 8 Block, Block N, Classroom Gazebo, Agriculture block and Replacement of windows of Administration Block as per Standard Building Code | 1 | TSU | Tropical Metal Products Ltd. | 1 | Approval granted | 2026-01-23 | 2026-04-20 | 80% - 99% ; work in progress | Final account to be prepared
6 |  | St. Catherine | The Enid Bennett High |  | 45223504 |  | Removal of raw sewage from septic tank & Absorption pit as per Standard Building Code | 1 | TSU | THLC | 2 | 2026-01-27 | 2026-02-16 | 2026-05-15 | 80% - 99% ; work in progress | Final account to be prepared
7 |  | St. Catherine | Marlie Hill Primary and Infant | 40000000 |  |  | Construction of retaining wall on boundary of school premises adjacent to parochial road as per Standard Building Code | 1 | NET | M&M Construction | 1 |  |  |  | Contractor to be given site possession | Project Percentage Completion: 0% Proposed Project Completion Date: Comments/Issues:/Challenges: Contractor's bid submitted in June 2026 is being assessed Land Survey to be undertaken & NWA engaged to assist
8 |  | St. Catherine | Garden Hill Primary and Infant |  | 23080660 | 9047200 | Repairs to Roofs of Administrative and Canteen Block as per Standard Building Code | 1 | TSU | HT Roofing & Construction Limited | 3 | Approval granted | 2026-01-12 | 2026-04-10 | 80% - 99% ; work in progress | Final account to be prepared
9 |  | St. Catherine | Ginger Ridge Primary |  | 23032450 | 15312950 | Proposed Re-Sheeting & Waterproofing of Roofs as per Standard Building Code | 1 | TSU | HT Roofing & Construction Limited | 3 | Approval granted | 2026-01-20 | 2026-04-17 | 80% - 99% ; work in progress | Final account to be prepared
10 |  | St. Catherine | Guys Hill Primary | $94,700,000 Phase 1: $37,500,000 |  |  | Repairs to roofs on 3 buildings Phase 1 Reinforced concrete block Steel frame building Phase 2 Replacement of main classroom block with nog walls as per Standard Building Code | 1 | NET | Build Rite Construction |  |  |  |  | Contractor to be given site possession | Project Percentage Completion: 0% Proposed Project Completion Date: Comments/Issues:/Challenges: Joint site visit by representative of NET, MoE/TSU, MoE/Reg 6 took place on July 17, 2026. Decision taken to proceed with repairs to concrete and steel framed blocks and postpone replacement of main classroom block pending the guidance of MoE on the size of the new facilities
11 |  | St. Catherine | Hamwalk Primary and Infant |  | 59150750 | 25316250 | Repairs to roofs of Canteen Block, Administrative Block, Auditorium Block as per Standard Building Code | 1 | TSU | Geeho Consultant & Construction Limited |  | 2026-01-27 | 2026-02-16 | 2026-05-15 | 80% - 99% ; work in progress | Final account to be prepared
12 |  | St. Catherine | Redwood Primary |  | 12466601 |  | Repairs to roof of Library Block as per Standard Building Code | 1 | TSU | J'Neil Construction | 3 | Approval granted | 2026-01-12 | 2026-04-10 | 80% - 99% ; work in progress | Final account to be prepared
13 |  | St. Catherine | Gregory Park Primary |  | 23994862 |  | Re-Sheeting of Administrative Roof Block as per Standard Building Code | 1 | TSU | HT Roofing & Construction Limited | 3 | Approval granted | 2026-01-15 | 2026-03-13 | 80% - 99% ; work in progress | Final account to be prepared
14 |  | St. Catherine | Naggo Head Primary |  | 48064542 | 12783413 | Waterproofing and Re-sheeting of Roofs, Repairs to Student Sanitary Facilities & Construction of Corridor Way as per Standard Building Code | 1 | TSU | Duke's Electrical & Construction | 2 | Approval granted | 2026-01-26 | 2026-04-24 | 80% - 99% ; work in progress | Final account to be prepared
14 | TOTAL |  |  | 40000000 | 476854360 | 102891488

## REGION 7
POST-HURRICANE ASSESSMENT DATA ― IMPACT OF HURRICANE MELISSA ON SCHOOLS' INFRASTRUCTURE
No of Schools | Region | Parish | Name of School | Preliminary Cost $ | Contract Sum $ | Expenditure to Date $ | Scope of Works | PRIORITY 1. Severely Damaged - may affect school reopening. 2. Moderately Damaged - Significant repairs. School can operate while repairs are done. 3. Minor Damage - school can operate while repairs are done. | Person Responsible (TSU , NET, JSIF , DONOR) | Name of Contractor Assigned | Contractor Grade | Projected Date of Procurement for PS Approval | Contract Start Date | Contract End Date | Status | Remarks
1 | 7 | Clarendon | Central High |  | 131252956.53 |  | Repairs to 4 blocks: Dormitory Grade 9 Grade 10 Administration Block As per Standard Building Code | 1 | NET | Chins Construction | 1 | Approval granted | 2026-02-04 | 2026-08-03 | 20% & Below ; work in progress | Project Percentage Completion: 5% Proposed Project Completion Date: Comments/Issues:/Challenges: Work started on the Dormitory and Grade 9 blocks but was suspended because of financial reasons. Work is expected to resume by July 31, 2026 .
2 |  | Clarendon | Alphansus Davis High (Spalding High) |  | 166627650 | 16560578.94 | Roof repairs for 5 facilities: * Water tank roof (wood to concrete) * Roof of Administration Bldg * Poultry House * CAPE Block * Agricultural Science Block As per Standard Building Code | 1 | NET | Lottis Projects | 1 | Approval granted | 2026-01-26 | 2026-07-25 | 20% & Below ; work in progress | Project Percentage Completion: 10% Water Tank - 100% Admin Bldg - hording, 50% ; roof, 0% Poultry House - 90% CAPE & Agricultural Blocks - Schematic designs sent to stakeholders for feedback Proposed Project Completion Date: May 31, 2026 Comments/Issues:/Challenges: Contractor slipping behind schedule. Remedy: Weekly virtual meeting to track progress
3 |  | Clarendon | Edwin Allen High |  | 270112200 | 31708171.83 | Repairs to 14 blocks/bldgs.: * Gr 7 Block * Gr 8 Bldg * Agricultural Block * Guidance Councillor * Chemical Storeroom * Staffroom * Agriculture Classroom * Administration Block * Science Block/Block D * Block E * Old Auditorium * Auditorium Kitchen * Tuck Shop #1 As per Standard Building Code | 1 | NET | Chins Equipment & Rental | 1 | Approval granted | 2026-01-17 | 2026-07-16 | 51% - 60% ; work in progress | Project Percentage Completion: 60% Proposed Project Completion Date: August 31, 2026 Comments/Issues:/Challenges: Contractor is moving expeditiously to complete works before the start of the new school year in September 2026
4 |  | Clarendon | Knox College | 100000000 | 319957457 |  | Repairs to 8 blocks/bldgs.: Phase 1 Nurses' Station Hostel Science Block Phase 2 Lewis Davidson Hall Library/Computer Lab Barbara Jones Auditorium Phase 3 Maintenance Office/Basketball Shed Humanities Block As per Standard Building Code | 1 | NET | Lottis Projects | 1 | Approval granted | 2026-01-26 | 2026-07-25 | 21% - 40% ; work in progress | Project Percentage Completion: 21% Phase 1 is currently in progress: Nurses' Station - 30%; Hostel - 50%; Science Block - 5% (demolition practically complete) Proposed Project Completion Date: Comments/Issues:/Challenges:
5 |  | Clarendon | Anderson Town Primary and Infant |  | 28596397 | 29789175 | Renovation of Classroom Blocks to include Electrical Upgrading, Tiling and Pest Control Treatment as per Standard Building Code | 1 | TSU | Britalex Construction | 2 | Approval granted | 2025-12-31 | 2026-03-06 | Work Completed | Final account submitted
6 |  | Clarendon | Bunkers Hill Primary and Infant |  | 23962229 | 13972310 | Repairs to Roof of Classroom Blocks to include upgrading of Electrical System as per Standard Building Code | 1 | TSU | HT Roofing & Construction Limited | 3 | Approval granted | 2025-12-28 | 2026-08-07 | 80% - 99% ; work in progress | Payment amounting to a sum of $13,972,360.00 submitted to Project Accounts
7 |  | Clarendon | Trout Hall Primary and Infant |  | 12132009 | 10470943 | Repairs to Roof of Classroom Blocks, Cottages and Upgrading of Electrical System s per Standard Building Code | 1 | TSU | J. Niel Construction | 3 | Approval granted | 2025-12-28 | 2026-03-10 | Work Completed | Final account submitted
8 |  | Clarendon | Clarendon College |  | 330439440 |  | Repairs to 10 blocks/bldgs: Tuckshop Tuckshop Storage Home Economic Lab Principal's Cottage Auditorium Computer Lab Staff Room #1, 1st/2nd Form Block Admin Bldg Gym/Dormitory As per Standard Building Code | 1 | NET | Southern Contracting Com Ltd. | 1 | Approval granted | 2026-06-22 | 2026-12-21 | 21% - 40% ; work in progress | Project Percentage Completion: 21% Home Econ Lab - 85%; Admin Block - 50%; Grades 7/8 Block - 5%; Demolition - 90 Proposed Project Completion Date: Comments/Issues:/Challenges:
9 |  | Clarendon | Knox Community College |  | 200095550 |  | Repairs to 7 blocks/bldgs: Phase 1 Computer Lab/Staffroom, Canteen/Operations & Management Office Education & Liberal Studies Bldg Phase 2 Registry Bldg Maths Dept, Villa 1 Villa 2 As per Standard Building Code | 1 | NET | Skymar |  |  |  |  | Work to Commence | Project Percentage Completion: 0% Proposed Project Completion Date: Comments/Issues:/Challenges: The contractor initially assigned was issued a letter to commence the works in January 2026. The firm withdrew from the project in June 2026 without executing any site activities. The newly assigned contractor submitted a bid on July 13, 2026; a Letter of Award is to be issued
10 |  | Clarendon | Main Ridge Primary |  | 11361490 | 8254990 | Repairs to Roofs of Classroom Blocks to include Upgrading of Electrical System as per Standard Building Code | 1 | TSU | J. Niel Construction | 3 | Approval granted | 2025-12-28 | 2026-02-09 | Work Completed | Payment amounting to sum of $8,254,990.00 submitted to Project Accounts. Final account being prepared, defects Identified and being corrected
11 |  | Clarendon | Windsor School of Special Education- Denbigh |  | 5909900 | 5435100 | Repairs to Roof of Classroom Blocks to include Upgrading of Electrical System as per Standard Building Code | 1 | TSU | Lesclar Synergy Co-Company Limited | 3 | Approval granted | 2025-12-28 | 2026-08-14 | 80% - 99% ; work in progress | Variation Order #1 approved by the PS. - Additional work to be commenced by July 10. 2026.
11 | TOTAL |  |  | 100000000 | 1500447278.53 | 116191268.77

## Sheet21 (hidden)
Apple |  | 12
Banana |  | 2
Orange |  | 5
Pear |  | 7
Mango |  | 6
Mango | #NAME?
Apple
#NAME?
Math | 1 | Math
English | 2 | English
Math | 3 | Science
Science | 4
English | 5
Apple, Banana, Orange, Pear, Mango |  | 5.00