## SUMMARY
PRIORITY 1 SUMMARY
REGION | PARISH | NUMBER OF SCHOOLS IN EACH PARISH | TOTAL NUMBER OF SCHOOLS | TOTAL NUMBER OF WORKS IN PROGRESS | TOTAL NUMBER OF CONTRACTS BEING MOBILSED | TOTAL NUMBER OF CONTRACTS TO BE GIVEN SITE POSSESSION | TOTAL NUMBER OF SCHOOLS COMPLETED BY TSU/ NET | TOTAL NUMBER OF WORKS TO BE DONE BY DONORS | TOTAL NUMBER OF SCHOOLS COMPLETED BY DONORS | TOTAL NUMBER OF SCHOOLS CONTRACTORS ARE ASSIGNED TO | PRELIMINARY COST ($) | CONTRACT COST($) | EXPENDITURE TO DATE ($)
1 | St. Andrew | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 308 | 0 | 5955700 | 0
| Kingston | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
2 | St. Mary | 9 | 10 | 5 | 0 | 2 | 2 | 1 | 0 |  | 90000000 | 328400516 | 220880758
| St. Thomas | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| Portland | 1 |  | 1 | 0 | 0 | 0 | 0 | 0
3 | St. Ann | 35 | 61 | 26 | 0 | 0 | 11 | 0 | 0 |  | 292190664.4 | 5874294263.62 | 1556395192.09
| Trelawny | 26 |  | 16 | 1 | 1 | 8 | 0 | 0
4 | Westmoreland | 64 | 150 | 49 | 3 | 9 | 4 | 5 | 1 |  | 3405791063.66 | 12295010166.81 | 1174161484.65
| St. James | 53 |  | 42 | 6 | 6 | 1 | 2 | 2
| Hanover | 33 |  | 27 | 1 | 4 | 1 | 1 | 0
5 | Manchester | 17 | 61 | 5 | 0 | 0 | 12 | 0 | 0 |  | 371478471.1 | 6796922103.25 | 1725814594.96
| St. Elizabeth | 44 |  | 34 | 0 | 4 | 7 | 4 | 1
6 | St. Catherine | 14 | 14 | 9 | 0 | 2 | 3 | 0 | 0 |  | 40000000 | 429597795 | 102891488
7 | Clarendon | 11 | 11 | 6 | 0 | 0 | 5 | 0 | 0 |  | 430439400 | 1500447278.53 | 246415975.56
TOTAL |  | 308 | 308 | 220 | 11 | 28 | 55 | 13 | 4 | 308 | 4629899599.16 | 27230627823.21 | 5026559493.26
17

## REGION 1
POST-HURRICANE ASSESSMENT DATA ― IMPACT OF HURRICANE MELISSA ON SCHOOLS' INFRASTRUCTURE
No of Schools | Region | Parish | Name of School | Preliminary Cost $ | Contract Sum $ | Expenditure to Date $ | Scope of Works | PRIORITY 1. Severely Damaged - may affect school reopening. 2. Moderately Damaged - Significant repairs. School can operate while repairs are done. 3. Minor Damage - school can operate while repairs are done. | Person Responsible (TSU , NET, JSIF , DONOR) | Name of Contractor Assigned | Contractor Grade | Projected Date of Procurement for PS Approval | Contract Start Date | Contract End Date | Status | Remarks
1 | 1 | St. Andrew | Allman Hill Primary and Infant |  | 5955700 |  | Replacement of roof sheeting and boarding on Infant Block as per Standard Building Code | 1 | TSU | Jamlutions Company Limited | 4 |  | 2026-02-11 | 2026-03-31 | Work Completed | Part payment amounting to $2,052750.00 submitted to TSU for processing
1 | TOTAL |  |  | 0 | 5955700 | 0

## REGION 2
POST-HURRICANE ASSESSMENT DATA ― IMPACT OF HURRICANE MELISSA ON SCHOOLS' INFRASTRUCTURE
No of Schools | Region | Parish | Name of School | Preliminary Cost $ | Contract Sum $ | Expenditure to Date $ | Scope of Works | PRIORITY 1. Severely Damaged - may affect school reopening. 2. Moderately Damaged - Significant repairs. School can operate while repairs are done. 3. Minor Damage - school can operate while repairs are done. | Person Responsible (TSU , NET, JSIF , DONOR) | Name of Contractor Assigned | Contractor Grade | Projected Date of Procurement for PS Approval | Contract Start Date | Contract End Date | Status | Remarks
1 |  | Portland | Comfort Castle Primary and Infant |  | 70846600 | 33956379 | Replacement of the damaged timber roof to include electrical upgrading for the Primary Block as per Standard Building Code | 1 | NET | THLC | 2 | Approval Granted | April 23, 2026 | October 20, 2026 | 95% - 99% ; practical completion | Project Percentage Completion: 95% Proposed Project Completion Date: October 2026 Practical Completion inspection scheduled for September 22, 2026. Project Status: Auditorium & Kitchen Roofing - 100% Electrical - 95% Painting - 90% Admin. & Classroom Bldg. Roofing - 100% Doors - 90% Electrical - 90% Painting - 90% Infant Bldg. Plumbing - 100% Roof Sheeting(cut tail) - 0% Electrical - 25% Ceiling - 80 % Issues:/Challenges: Graduation and exam activities impacted works.
2 |  | St. Mary | Baxters Mountain Primary | 35000000 |  |  | Repairs to damaged Timber Roof of NOG Classroom Block as per Standard Building Code | 1 | NET | Wadmar Construction | 2 |  |  |  | Contractor to be given site possession | Rebuild proposed as the structure which sustained damages from the hurricane is of a nog type construction. It currently houses classroom (divided into two areas) and administrative facilities. The building is also showing signs of deterioration to its walls and roof members. Based on the type of structure and its present state (structural failure) it is not recommended or considered feasible that the damages sustained to the roof be repaired. A set of our school standards have been sent to the contractor for them to revise their proposed designs and estimate for a new structure to house the current facilities. School flagged as a small school and cost for replacement did not indicate value for money. A Containerised solution is being explored and to be transferred from Chantilly (which is closing). Delivery of containerised solution scheduled by October 2026.
3 |  | St. Mary | Devon Pen Primary and Infant |  | 42219000 | 45015000 | Construction of Retaining Wall as per Standard Building Code | 1 | TSU | Macon Construction System Limited | 1 - Civil Engineering Works | Approval granted | Jan 16, 2026 | June 5, 2026 | Work Completed
4 |  | St. Mary | Richmond Primary and Infant |  | 30160530 | 10873580 | Repairs to Cottage used as Infant Department to include construction of a retaining wall as per Standard Building Code | 1 | TSU | Miller's Electric & Construction Limited | 2 | Approval granted | Jan 9, 2026 | October 31, 2026 | 61% -79% ; work in progress | The projected end date has not been finalized - extension of time request being assessed
5 |  | St. Mary | St. Mary Technical High | 55000000 |  |  | Replacement of severely damaged Sixth Form Block as per Standard Building Code | 1 | NET | Dwight Construction | 1 |  |  |  | Contractor to be given site possession | Design & Build Project. Commencement letter. issued and design in progress for the replacement classrooms. A design and Build contract is to be finalized.
6 |  | St. Mary | Highgate Primary |  | 23202900 | 9526870 | Replacement of roof to grade one classroom block and the female sanitation block as per Standard Building Code | 1 | TSU | Art Waterproofing Ltd. | 3 | Approval granted | Mar 27, 2026 | September 15, 2026 | 95% - 99% ; practical completion
7 |  | St. Mary | Port Maria Primary |  | 28492960 | 14142520 | Repairs to roof of Grade 2 Classroom Block to include repairs to roofs of Container Buildings as per Standard Building Code | 1 | TSU | Diverse Services and Construction Limited | 1 | Approval granted | Jan 7, 2026 | September 4, 2026 | 95% - 99% ; practical completion | The projected end date has not been finalized - extension of time request being assessed
[7 empty] | Establishment of Special Education Unit | 1 | DONOR | [5 empty] | Contractor to be given site possession | Formal Agreement between Digicel and MoESYI being finalised by both parties
8 |  | St. Mary | St. Mary High |  | 39262000 | 36679100 | Replacement of damaged roofing to Music Room Building, Industrial Arts Building and Block B as per Standard Building Code | 1 | TSU | Morris Hill Limited | 1 | Approval granted | Jan 13, 2026 | September 4, 2026 | 95% - 99% ; practical completion | The projected end date has not been finalized - extension of time request being assessed
9 |  | St. Mary | Retreat Primary |  | 39279430 | 25045145 | Repairs to damaged roofs of Block A, B & C as per Standard Building Code | 1 | TSU | Modern Waterproofing & Construction | 1 - Roofing | Approval granted | Jan 7, 2026 | September 30, 2026 | 95% - 99% ; practical completion | The projected end date has not been finalized - extension of time request being assessed
10 |  | St. Mary | Wycliffe Martin High (Previously Brimmer Vale High) |  | 54937096 | 45642164 | Repairs to damaged roofing of Canteen, Storeroom, Auditorium, Guidance Department and Industrial Arts Block as per Standard Building Code | 1 | TSU | Tropical Metal Products Limited | 1 - Roofing | Approval granted | Jan 8, 2026 | May 6, 2026 | Work Completed
10 | TOTAL |  |  | 90000000 | 328400516 | 220880758

## REGION 3
POST-HURRICANE ASSESSMENT DATA ― IMPACT OF HURRICANE MELISSA ON SCHOOLS' INFRASTRUCTURE
No of Schools | Region | Parish | Name of School | Preliminary Cost $ | Contract Sum $ | Expenditure to Date $ | Scope of Works | PRIORITY 1. Severely Damaged - may affect school reopening. 2. Moderately Damaged - Significant repairs. School can operate while repairs are done. 3. Minor Damage - school can operate while repairs are done. | Person Responsible (TSU , NET, JSIF , DONOR) | Name of Contractor Assigned | Contractor Grade | Projected Date of Procurement for PS Approval | Contract Start Date | Contract End Date | Status | Remarks
1 |  | St. Ann | Brown's Town Model Infant |  | 20804475.5 | 12164775.5 | Re-construction of 150mm concrete block wall boundary fence with chain-link fence on top. | 1 | TSU | Rhino Construction | 3 | Approval granted | 2026-01-20 | 2026-09-04 | 80% - 94% ; work in progress
2 |  | St. Ann | Alderton Primary and Infant |  | 23945300 | 10841080 | Roof repairs at Admin block, classroom, and cottage, security fence and electrical system. Re-sheeting and replacement of timber roof frame members and installation at ceiling Admin Block, classroom, and replacement of timber roof frame at cottage with reinforced concrete roof slab. Re-construction of security chain-link fence and electrical installation to code.. | 1 | TSU | Bruce's Development and Consultants | 3 | Approval granted | 2026-01-12 | 2026-09-05 | 61% -79% ; work in progress | Project is affected by challenges with material supply and periodic rainfall
3 |  | St. Ann | Irons Mountain Primary and Infant |  | 117280823.72 | 29331156.76 | Roof repairs and general repairs to facilities | 1 | NET | Dwight's Construction | 1 | Approval granted | 2025-12-08 | 2026-10-30 | 41% - 50% ; work in progress | Project Percentage Completion: 42% Canteen: 20% Block A: 100 % Block B: 20% Proposed Project Completion Date: October 2026 Works done this Week: 1.Canteen: Block work continued 2. Block B: Block work continued Works to be done next week: 1. Canteen: Block work to continue 2. Block B: Block work to continue Issues/Challenges: Addendum to the Contract being completed by Legal based on additional scope of works. Contractor submitted signed pages for the addendum on August 4, 2026 and Revised Letter of Bid and BQ submitted on August 7, 2026 . Certificate #1 $29,331,156.76 PAID. School will be ready by October 2026
4 |  | St. Ann | Parry Town Primary and Infant |  | 43557994 | 29805207.25 | Damage to timber framed roofs at classroom and sanitary facilities. Re-sheeting and replacement of timber roof members and installation of ceiling and electrical installation to code.. | 1 | TSU | Archistruct Limited | 1 | Approval granted | 2026-01-20 | 2026-09-04 | Work Completed | Final account is being prepared for the main project and approval is granted for a follow-on contract to commence by the end of September
5 |  | St. Ann | Edgehill School of Special Education |  | 183018111 | 37506040 | 1. An extension of 3 additional classrooms and sanitary facilities 2. Repair roof, ceiling and associated works of the Administrative Building 3. Repair roof and associated works on Home Economics Building | 1 | NET | Dutch Construction | 2 | Approval granted | 2026-05-06 | 2026-11-05 | 61% -79% ; work in progress | Project Percentage Completion: 70% Proposed Project Completion Date: November 2026 Temporary classrooms 100% Admin. Block - Roofing - 100% Ceiling - 100% Partition - 100% Electrical - 100% Painting 100% Doors - 100% Windows - 100% Classroom Block Ditto above Extension Fdn. Exca. - 100% Steelwork to Fdn. 100% Substructure Blockwork - 100% Substructure Col. - 100% Ground Floor Blockwork - 100% Ground Floor Columns - 95% Ground floor rendering - 50% First Floor Decking - 90% Steelwork to First Floor Decking - 50%
6 |  | St. Ann | Beecher Town Primary and Infant |  | 49841903.46 |  | Damage to timber framed roofs at classroom and cottage. Re-sheeting and replacement of timber roof members and installation of ceiling of classroom and cottage with reinforced concrete roof slab and electrical installation to code. | 1 | TSU | Archistruct Limited | 1 | Approval granted | 2026-01-20 | 2026-09-15 | 80% - 94% ; work in progress | Project is affected by challenges with material supply and periodic rainfall
7 |  | St. Ann | Alva Primary and Infant |  | 23845430 |  | Damage to timber framed roof at classroom block. Replacement with steel frame roof structure with ceiling and sheeting and general electrical installation and electrical installation to code. | 1 | TSU | Monna Construction Limited | 3 | Approval granted | 2026-08-28 | 2026-09-04 | 80% - 94% ; work in progress | Project is affected by challenges with material supply and periodic rainfall
8 |  | St. Ann | Bethany Primary |  | 23989333.86 | 15595758.62 | Damage to timber framed roofs at grade 5 classroom and cottage. Replacement of damage timber roofs at admin block, classroom, and cottage with reinforced concrete roof slab and electrical installation to code. | 1 | TSU | Monna Construction Limited | 3 | Approval granted | 2026-01-12 | 2026-09-04 | Work Completed | Final account is being prepared
9 |  | St. Ann | Brown's Town Primary |  | 50869200 | 28457214 | Repairs to hurricane damaged facilities and re-construction of collapsed boundary fence. | 1 | NET | N.F Barnes Construction | 1 | Approval granted | 2025-12-14 | 2026-03-14 | 80% - 94% ; work in progress | Overall completion is approx. 92% Roof sheeting to classroom block completed and ceiling works 95%. Repairs to roof leak and ceiling boards on other classroom blocks are ongoing. Also approval of quotation to address issues from the fire department has been issued to the contractor. This status will not impact the reopening of school
10 |  | St. Ann | Cascade Primary and Infant |  | 101631568.09 |  | Replacement of roofing to Grade 1 & 2 Classroom Blocks, Student Bathrooms, Repairs to Sanitary Facilities & Security Fencing | 1 | NET | Archistruct Limited | 1 | Approval granted | 2026-03-24 | 2026-09-23 | 80% - 94% ; work in progress | "Project Percentage Completion: 90% 1.Fencing 100% 2. Roof Repairs 100% 3. Boundary Wall 100% Proposed Project End Date: June 2026 Works done in the week of the current period: 1.Painting 100% 2. Electrical 100% Works to be done is next period: 1.Receive drawings for the bathroom on building one 2. Receive the variation cost proposal. 3.Guttering to commence 4. Install windows Issues/ Challenges: Design and Build Contract to be in place for Infant School-Certificate #1 PAID $34,895,391.82." The contractor shared the design for the infant building & feedback was provided. A meeting will be held with the contractor to review designs with the aim of submitting to the Municipality.
11 |  | St. Ann | Higgins Land Primary and Infant |  | 23988950 |  | Damage to steel framed roofs at Block A and B classroom and timber for of cottage. Replacement of sheeting and ceiling at blocks A and B. Replacement of defective timber roof at cottage with reinforced concrete roof slab and electrical installation to code. | 1 | TSU | Bruces Development | 3 | Approval granted | 2026-01-12 | 2026-08-28 | 80% - 94% ; work in progress
12 |  | St. Ann | Bamboo Primary |  | 74962770 | 71965706 | Roof repairs for classroom block. Replace roof of the kitchen, canteen and the lower school bathroom. | 1 | NET | Dutch Construction Limited | 1 | Approval granted | 2025-12-27 | 2026-06-25 | Work Completed | Project Completed
13 |  | St. Ann | Free Hill Primary and Infant |  | 112979301 | 53061343.9 | Re-roofing of Grade 6 Classroom Block, Kitchen, Sanitary Facilities, Infant Department, Staff Cottage and repairs to Security Fencing | 1 | NET | N.F Barnes Construction | 1 | Approval granted | 2025-12-19 | 2026-06-17 | 95% - 99% ; practical completion | "Project Percentage Completion: 95% Proposed Project End Date: July 2026 Works done in the week of the current period : 1. Teachers' cottage in progress 2. Timber Information Building in progress Works to be done is next period: TBD Issues/ Challenges: IT Room, not operational. outstanding work required. Continuous moulding in the canteen(Contractor advised) Variation #1 approved for $8,685,732.50 Certificate #2 $3,833,545.90 submitted May 8, 2026 PAID"" Taking Over Certificate pending."
14 |  | St. Ann | Discovery Bay Primary and Infant |  | 37663416 |  | Damage to timber framed roofs at infant department and computer lab and steel framed roof at primary department. Replacement of timber framed roofs at Infant Department and Computer Lab with reinforced concrete roof slab and re-sheeting steel framed roof at primary department and electrical installation to code. | 1 | TSU | Modern Waterproofing | 3 | Approval granted | 2026-01-12 | 2026-09-04 | Work Completed | Final account is being prepared
15 |  | St. Ann | Hoolebury Primary and Infant |  | 69323475.45 | 8768015 | Damaged to timber framed roofs at classroom Block B, Canteen and Cottage and waterproofing membrane and windows at classroom Block A. Replacement of timber roofs at classroom Block B, Canteen and Cottage with reinforced concrete roof slab. Replacement of Waterproofing at Block A and windows and electrical installation to code. | 1 | TSU | Costley's Construction | 1 | Approval granted | 2026-01-05 | 2026-09-25 | 80% - 94% ; work in progress | Project is affected by challenges with material supply and periodic rainfall
16 |  | St. Ann | Keith Primary and Infant |  | 28750300 | 8791914 | Damaged to timber roofs at classroom block B and canteen. Replacement of timber roof frame with metal- re-sheeting, ceiling and electrical installation to code. | 1 | TSU | Modern Waterproofing | 3 | Approval granted | 2026-01-12 | 2026-09-04 | Work Completed | Final account is being prepared
17 |  | St. Ann | Lime Hall Primary and Infant | 93898500 |  |  | Repairs to roof and fence | 1 | NET | Archistruct Limited | 1 |  | 2025-12-19 |  | 51% - 60% ; work in progress | Project Percentage Completion: 55% Grade 1:100% Grade 2&3:100% Main Building: 85% Cottage:15% Fencing:100% Proposed Project Completion Date: TBD Project Status Works done in the week of the current period: . Painting works remain outstanding completed Grade 1&2: Painting and electrical works completed Cottage: Repair work in progress Works to be done is next period: Main Building: Painting works to be completed • Painting and installation of doors and kitchen cupboards. • Ventilation/window vent works. • Guttering. Issues:/Challenges: No Contract in place, Contractor is required to submit updated BQ. Security issue has occurred on-site involving the police, virtual meeting (31-7-26) with the Contractor and School to come to understanding and see way forward. Main building to be completed by September 13, 2026
18 |  | St. Ann | Lime Tree Gardens Primary and Infant |  | 69528200 |  | Damage to metal framed classroom blocks A and B. Re-sheeting, ceiling and electrical installation at Blocks A and B and electrical installation to code. | 1 | TSU | Archistruct Limited | 1 | Approval granted | 2026-01-20 | 2026-08-07 | Work Completed | Final account is being prepared for the main project and approval is granted for a follow-on contract to commence by the end of September
19 |  | St. Ann | Philadelphia Primary and Infant |  | 24049987 | 7333449.5 | Damaged to timber framed roof at classroom block and canteen. Replacement of timber roof frame with metal frame roof structure, re-sheeting, ceiling and electrical installation to code and electrical installation to code. | 1 | TSU | Modern Waterproofing | 3 | Approval granted | 2026-01-12 | 2026-09-18 | 80% - 94% ; work in progress | Project is affected by challenges with material supply and periodic rainfall
20 |  | St. Ann | Retirement Primary |  | 56883900 | 34568338 | Re-roofing of Classroom Block and Admin Department | 1 | NET | Dutch Construction | 2 | Approval granted | 2026-01-31 | 2026-10-01 | 95% - 99% ; practical completion | Project Percentage Completion: 95% Proposed Project Completion Date: October 1, 2026 (EOT approved for 01/10/2026 Site assessment scheduled for September 23, 2026, to verify practical completion. Issues:/Challenges: None
21 |  | St. Ann | Runaway Bay Primary and Infant |  | 33427651.7 | 7146092 | Damaged to timber framed roof at grade 5,6 and Special Ed. Classroom blocks and damage to section chain-link boundary fence. Replacement of timber roof at grades 5 and Special Ed. with reinforced concrete roof slab to code. Re-sheeting of timber roof at grade 6 block. Replace sections of chain-link fence with block wall and electrical installation to code. | 1 | TSU | Costley's Construction | 1 | Approval granted | 2026-01-05 | 2026-08-14 | Work Completed | Final account is being prepared
22 |  | Trelawny | Falmouth Primary |  | 58025200 | 28148113.85 | Repair of roof of the administrative block and Grade 5 classrooms . | 1 | NET | ECJ | 2 | Approval granted | 2016-02-13 | September 30, 2026 | 80% - 94% ; work in progress | "Project Percentage Completion: 90% Auditorium: 95% Canteen:95% Bathroom Block: 100% Sickbay:95% Chain-link Fencing:25% Proposed Project End Date: September 30, 2026 (EOT to be drafted for extension of time) Works done in the week of the current period: 1. Sick Bay: Painting to continue 2. Partition installation in progress 3. Canteen: Electrical in progress 4. Auditorium: Electrical in progress, doors and window installation 95% Works to be done is next period: 1. Auditorium: electrical continues 2. Partition installation to continue 3. Sick Bay: Painting to continue 4. Fencing: Installation to commence Issues/ Challenges: Cert #3 $7,596,658.00 PAID
23 |  | St. Ann | Servite Primary |  | 22878672.3 | 17903244 | Damaged to timber framed roof at Admin, grade 5 blocks and canteen. Replacement of timber roof at Admin and grade 5 with reinforced concrete roof slab. Variation being prepared for approval for replacement of timber roof at canteen with reinforced concrete roof slab and electrical installation to code. | 1 | TSU | Modern Waterproofing | 3 | Approval granted | 2026-01-12 | 2026-09-25 | 80% - 94% ; work in progress | Project is affected by delays related to variation in scope of work
24 |  | St. Ann | St. Christopher School for the Deaf |  | 250732010.11 | 58270878.86 | Replacement of roofs to Classroom Blocks and Administration Department and Dormitory. General repairs to facilities | 1 | NET | N.F Barnes Construction | 1 | Approval Granted | 2026-02-04 | 2026-10-31 | 61% -79% ; work in progress | Project Percentage Completion: 75% Proposed Project Completion Date: October 30, 2026 (Awaiting contractors formal request for extension of time) Project Status: Male Dormitory Replace roof - 98% Female Dormitory Replace roof - 98% Sagicor Building 98%. Laundry 98% Block B (L shaped Bldg.) 90% Block C 10% Block D 70% Teacher's Cottage 50% Issues:/Challenges: The repair work to nog walls of Block E may require a re-build instead of repair, Hence the contractor was asked to provide a quotation to carry out re-build.
25 |  | St. Ann | Sturge Town Primary |  | 74973800 | 52755927.5 | Re-roofing of Classroom Blocks and Administrative Department | 1 | NET | Dutch Construction | 2 | Approval Granted | 2025-12-29 | 2026-06-27 | Work Completed | Project Percentage Completion: 100% Proposed Project Completion Date: Project Status: All works under the contract have been completed. Only items of Defects are now to be carried out. Taking Over Certificate issued July 13, 2026 Issues:/Challenges: None
26 |  | St. Ann | Waltham Abbey Primary and Infant |  | 58533650 | 21462264.5 | Re-roofing of Classroom Blocks, Upgrading of electrical and Water Supply System | 1 | NET | E.C.J Construction | 3 | Approval Granted | 2026-01-05 | 2026-05-05 | 95% - 99% ; practical completion | Project Percentage Completion: 95% Proposed Project Completion Date: September 30, 2026 (Awaiting contractors formal request for extension of time) Issues:/Challenges: None
27 |  | St. Ann | Watt Town Primary and Infant |  | 23995475.9 |  | Damaged to timber framed roof at Grade 1 Classroom Block, Infant Department and Administrative Department. Replacement of timber roof sheeting and ceiling at Infant Department. Replacement of sections of roofs at Grade1 and Admin Department and electrical installation to code. | 1 | TSU | Rhino Construction | 3 | Approval granted | 2026-01-20 | 2026-08-14 | Work Completed | Final account is being prepared
28 |  | Trelawny | Albert Town Primary and Infant |  | 124717745 | 72926076.68 | Re-roofing of Classroom Blocks, Infant Department and upgrading of Electrical System | 1 | NET | Build-rite Construction | 1 | Approval granted | 2026-04-16 | 2026-10-15 | 80% - 94% ; work in progress | Project Percentage Completion: 85% Proposed Project Completion Date: October 2026 Project Status: 1. All electrical works are fully completed Issues:/Challenges: None
29 |  | Trelawny | Clark's Town Primary |  | 36213580 |  | Re-roofing of Grade 4 Classroom Block and renovation of Teacher Cottage | 1 | NET | Yardworks Construction | 1 |  |  |  | 21% - 40% ; work in progress | Project Percentage Completion: 30% completed Proposed Project Completion Date: Project Status: No work was done this week due to non-payment. The contractor received payment on September 16, 2026. An email was sent on September 17, to the contractor to resume construction activities. Issues:/Challenges: Work has stopped due to non-payment.
30 |  | Trelawny | Granville Primary and Infant |  | 175820040 |  | Re-roofing of existing Classroom Blocks | 1 | NET | Marshall Construction | 1 |  |  |  | Work to Commence | Project Percentage Completion: 0% completed Proposed Project Completion Date: Project Status: Work to commence the week of September 21. Issues:/Challenges:
31 |  | Trelawny | Hague Primary and Infant |  | 216672653.33 |  | Re-roofing of Grade 3, 4 & 5 Classroom Block to include Stairway, Linkway and Canteen Facility | 1 | NET | Rogers Land Development | 1 |  |  |  | 21% - 40% ; work in progress | Project Percentage Completion: 28% completed Proposed Project Completion Date: Project Status: Welding works on the walkways, resheeting and ceiling works ongoing. Issues:/Challenges:
32 |  | Trelawny | Hampden Primary and Infant | 182424664.4 |  |  | Re-roofing of both Classroom Block Buildings, Infant School and Administrative Department, Water proofing to the bathroom block and general repairs | 1 | NET | Diverse Services and Construction Limited | 1 |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 17% Proposed Project Completion Date: TBD Project Status: Infant School roof and capping are 95%, storage building 65% completed, decking has started, and awaiting materials for the main building (15% completed.) Regarding the modular classrooms, American Friends of Jamaica (AFJ) would have visited the school to assess and select a suitable location for 2 donated modular classrooms. The letter of award was issued to the contractor on September 8, 2026. Issues:/Challenges:
33 |  | Trelawny | Hastings Primary and Infant |  | 39848000 | 14843576 | Re-roofing of Primary and Infant Department, Replacement of existing Drywall partitions for classrooms | 1 | NET | Marshall Construction | 1 | Approval granted | 2026-04-08 | 2026-10-07 | 80% - 94% ; work in progress | Project Percentage Completion: 92% Proposed Project Completion Date: The Infant Department and Primary School (September 5, 2026) & Grade 6 & Guidance Office (TBD) Project Status: Installation of the fencing to the Primary School is 92% electrical works 98% completed and painting 100%. The costing for the additional works were submitted by the contractor and is currently being reviewed for approval. The contractor is to provide stamped structural designs and BQ for the design component of the classroom and guidance counsellor's office. Issues:/Challenges:
34 |  | Trelawny | First Hill Primary and Infant |  | 49430601.46 | 21650003.45 | Damaged to timber roof at student bathroom, cottage and security fencing. Replacement of timber roof with reinforced concrete roof slab to code. Replacement of chain-link security fencing and electrical installation to code. | 1 | TSU | Odel Allen | 2 | Approval granted | 2026-01-20 | 2026-08-21 | Work Completed | Final account is being prepared
35 |  | Trelawny | Sawyers Primary and Infant |  | 21865193.5 | 2560524.45 | Damaged timber roof at student bathroom, cottage and security fencing. Replacement of timber roof with reinforced concrete roof slab to code. Replacement of chain-link security fencing. | 1 | TSU | Project Percentage Completion: 75% Proposed Project Completion Date: June 2026 Project Status: Male Dormitory Replace roof - 98% Female Dormitory Replace roof - 98% Sagicor Building 98%. Laundry 98% Block B (L shaped Bldg.) 90% Block C 10% Block D 70% Teacher's Cottage 50% Issues:/Challenges: The repair work to nog walls of Block E may require a re-build instead of repair, Hence the contractor was asked to provide a quotation to carry out re-build. | 2 | Approval granted | 2026-01-20 | 2026-08-14 | Work Completed | Final account is being prepared
36 |  | Trelawny | Stewart Town Primary and Infant |  | 46121800 | 22973985 | 1. Classrooms to be enclosed by erecting block wall along open space 2. Additional anchorage and minor repairs to roof | 1 | NET | ECJ | 2 | Approval Granted | 2026-02-04 | 2026-08-03 | 21% - 40% ; work in progress | Project Percentage Completion: 40% Block wall installation- 50% Block wall rendering - 0% Block wall painting - 0% Restoration of walkway covering - 100% Minor repairs and reinforcement to roof - 0% Proposed Project Completion Date: August 2026 Issues:/Challenges: Work has halted as a Contract Addendum is being resolved to ensure payments can be made going forward. Addendum is required given the additional scope of works & the justification was sent to the Procurement Unit to finalise the Addendum.
37 |  | Trelawny | Ulster Spring Primary and Infant | 15867500 | 149010053.5 |  | Construction of gabion retaining wall, construction of perimeter fencing, and upgrading of the electrical system. Installation of waterproof membrane to Infant Department | 1 | NET | Diverse Services and Construction Limited | 1 |  |  |  | 61% -79% ; work in progress | Project Percentage Completion: 65% Proposed Project Completion Date: TBD Project Status: All roof sheeting has been completed. Electrical work is ongoing. Grade 1 fans and electrical work have been completed. The ceiling work on the main building has commenced, along with electrical work. The fence work has halted due to a material shortage. The waterproof membrane is to be installed on the Infant Department. Issues:/Challenges: Material shortage for fence repairs.
38 |  | Trelawny | Bounty Hall Primary and Infant |  | 29521879.94 | 4789500 | Damaged timber roof at Principals Cottage, waterproofing membrane and windows at Classroom Block. Replacement of timber roof at cottage with reinforced concrete roof slab to code. Waterproofing of roof slab and replacement of windows . General electrical installation. | 1 | TSU | Brentwood Construction | 1 | Approval granted |  | 2026-09-25 | 80% - 94% ; work in progress | Project is affected by challenges with material supply, periodic rainfall and logistics challenges with contractor
39 |  | Trelawny | Daniel Town Primary and Infant |  | 50801803.46 |  | Damage to metal framed classroom block, timber framed roof at student bathroom and cottage. Replacement of sheeting and ceiling at classroom block and student bathroom. Replacement of timber roof at cottage with reinforced concrete roof slab and electrical installation to code. | 1 | TSU | Odel Allen | 2 | Approval granted | 2026-01-20 | 2026-08-14 | Work Completed | Final account is being prepared
40 |  | Trelawny | Salt Marsh Primary and Infant |  | 52927356.5 | 26390214.75 | Damaged to timber roof at classroom blocks A,B, Infant Department, cottage and security fence. Replacement of sheeting and ceiling at blocks A,B and Infant Department. Replacement of timber roof at cottage with reinforced concrete roof slab to code. Replacement of chain-link security fencing and electrical installation to code.. | 1 | TSU | Odel Allen | 2 | Approval granted | 2026-01-20 | 2026-09-18 | Work Completed | Final account is being prepared
41 |  | Trelawny | Waldensia Primary and Infant |  | 34193350 | 31751407.19 | Re-roofing of Classroom Blocks to include Pest Control Treatment | 1 | NET | DAWAFA | 3 | Approval Granted | 2025-12-18 | 2026-02-16 | Work Completed | Project Percentage Completion: 100% Project Status: Taking Over Inspection Requested by the Contractor. A Site Visit is to be scheduled in the week of September 28, 2026. Issues:/Challenges: There is a need for the construction of a retaining wall Jand the justification was sent to the Procurement Unit to finalise contract arrangements for this additional scope.
42 |  | Trelawny | Unity Primary |  | 72229480 | 43191706.4 | Re-roofing and General Repairs to Classroom Blocks to include reinforcement of Security Fencing | 1 | NET | Marshalls | 1 | Approval Granted | 2026-04-16 | 2026-10-16 | 95% - 99% ; practical completion | Project Percentage Completion: 97% Proposed Project Completion Date: August 31, 2026. Project Status: The Taking Over Certificate was issued to the contractor on August 17, 2026. The additional variation works have been completed. Final assessment to be conducted. Issues:/Challenges: None
43 |  | Trelawny | Wakefield Primary and Infant |  | 70428859.96 | 31931516.49 | Damaged to timber roof at Admin, classroom blocks A,B and cottage. Replacement of sheeting and ceiling atAdmin, blocks A,B. Replacement of timber roof at cottage with reinforced concrete roof slab and electrical installation to code. | 1 | TSU | Odel Allen | 2 | Approval granted | 2026-01-20 | 2026-09-18 | Work Completed | Final account is being prepared
44 |  | Trelawny | Warsop Primary |  | 135529250 | 36634332.5 | Construction of Security Fencing | 1 | NET | Skymar Construction | 1 | Approval granted | 2026-03-12 | 2026-09-11 | 80% - 94% ; work in progress | Project Percentage Completion: 94%% Infant Department - 90% Multi - Purpose Building - 100% Canteen - 100% Chain-link Fence - 100% Upper School Block: 85% Proposed Project Completion Date: September 30, 2026 (Awaiting contractors formal request for extension of time) Works done this week: Primary Block Painting - 100% Guttering - 70% Canteen Membrane installed Multi-purpoused Building Works to be done next week: Guttering to be completed Comments/Issues:/Challenges: Kitchen cabinetry to be priced along with other variated items .
|  | Trelawny |  |  |  |  | Installation of water harvesting & sanitation, water storage and pumps | 1 | DONOR | UNICEF
45 |  | Trelawny | Wilson's Run Primary and Infant |  | 82130640 | 20978250 | Repairs to Cottages to include Upgrading of Electrical System | 1 | NET | Skymar Construction | 1 | Approval granted | 2026-03-12 | 2026-09-11 | 95% - 99% ; practical completion | Project Percentage Completion: 95% Infant Department - 90% Main Building - 90% Chain-link Fence - 100% Waterproofing - 100% Proposed Project Completion Date: September 30, 20263(Awaiting contractors formal request for extension of time) Works done this week: Guttering - 50% Works to be done next week: Principal door to be installed Comments/Issues:/Challenges: Variation items (Flooring, Ceiling, Partitions) to be priced
46 |  | St. Ann | St. Hilda's Diocesan High |  | 82061065 |  | The scope of works scheduled for restoration includes: Water Tank (Replace Roof), Principal's Cottage, Grade 7 Block and the Chemistry lab | 1 | NET | Morris Hill Limited | 1 |  | 2026-04-16 | 2026-10-15 | 61% -79% ; work in progress | Project Percentage Completion: 65% Proposed Project Completion Date: October 15, 2026 Project Status: Teacher's Cottage 1. Place roof Sheeting 100% 2. Replace ceiling 100% 3. Tiling 100% 4. Electrical 60% 5. Plumbing Fixtures 95%% 6. Kitchen Cupboards 50% Science Lab 1. Replace damage windows 50% Grade 7 Classroom Block Replace roof frame and sheeting 60% 2. Replace Damaged Doors 0% Issues:/Challenges: Contract is being prohibited from carrying out works to the Water Storage Tank and prevented from entering the school last week by the principal.
47 |  | St. Ann | Aabuthnott Gallimore High |  | 45759402 | 31670452 | Damage to blocks B and C waterproofing membrane, sections of timber roof at block A, windows at block D and security fencing. Waterproofing to blocks B and C. Replacement of timber roof at section block A with reinforced concrete roof slab to code. Replacement of windows at Block D and construction of chain-link security fence and electrical installation to code. | 1 | TSU | Brentwood Construction | 1 | Approval granted | 2026-01-20 | 2026-08-14 | Work Completed | Final account is being prepared
48 |  | St. Ann | Aboukir High |  | 41901715.9 | 13389310.56 | Damaged Admin Building, Foods Lab and canteen. Replacement of sheeting on metal roof frame and ceiling at Foods Lab and canteen and electrical installation to code. | 1 | TSU | Brentwood Construction | 1 | Approval granted | 2026-01-05 | 2026-09-18 | 80% - 94% ; work in progress | Project is affected by challenges of periodic rainfall and variation in scope of work
49 |  | St. Ann | Brown's Town High |  | 106986094 | 16652929.05 | 1. Replacement of existing roof sheeting to classroom block 2. Replacement of ceiling to existing classroom block 3. Replacement of Guttering to roofs 4. Repair of leaks to roofs | 1 | NET | Brentwood Construction | 1 | 2025-12-19 | 2026-07-03 | 2026-10-04 | 61% -79% ; work in progress | Project Percentage Completion: 77% Block A: 88% Block B and C window replacement: 50% *Sliding windows on sections of block B and C in admin rooms where Ac units are installed Math Block Roof Repairs: 100% Auditorium Roof Repairs: 100% Greenhouse Replacement:0% Tuck Shop Roof Repairs: 100% Broiler and Layer Unit Roof Repair: 70% Fencing: 100% Proposed Project End Date: October 2026 Works done in the week of the current period : Math Block : 100% Works to be done is next period : 1. Variation rates to be reviewed 2. Block A: Partitions to be commence. Electrical installation to continue, window installation to commence. Install flashing and capping Issues/ Challenges: Addendum issued. Certificate #1 $16,652,929.05 PAID. Claim #2 $31,789,787.20 Pending. Delays of VO processing delayed due to competing activities from QS.
50 |  | St. Ann | Discovery Bay High |  | 83301114.04 |  | Damaged to resource building used by Primary Department, Block B metal frame roof and chain-link fencing. Replacement of sheeting and ceiling to section of metal frame roof at Block B. Installation of chain-link fencing and electrical installation to code. | 1 | TSU | Costley's Construction | 1 | Approval granted | 2026-01-15 | 2026-09-18 | 41% - 50% ; work in progress | Project is affected by challenges of material supply, periodic rainfall and variation in scope of work
51 |  | St. Ann | Ferncourt High |  | 260145244.8 | 86313544.26 | Roof repairs to buildings, teachers’ cottages and poultry house. General repairs to facilities | 1 | NET | Skymar Construction | 1 | Approval granted | 2026-04-08 | 2026-10-07 | 61% -79% ; work in progress | Project Percentage Completion: 65% Farming Area- 40% Auditorium - 100% (Clean up/Make good required) Teachers' Cottage - 100% Principal's Cottage - 0% Sharon Kelly Block window replacement& roof repairs-50% Aubyn Haye Block window replacement & roof repairs-0% Oswald Fisher Block window replacement & Roof repairs- 60% Ethyl Mullings Block - 100% Graphics & Automation Building- 70% Timber Structure – Seventh Grade Block - 50% Retaining Wall- 100% Fencing-0% Curphy Hall Nursing Building and - Design and Build Proposed Project End Date: October, 2026 Works done in the week of the current period: 1. Teachers cottage Work complete 2. Graphics Building: painting 3. Grade 7 Block: block work completed. boxing up in progress for slab 4. Retaining Wall: Work completed 5. Oswald Fisher Block: painting completed 6. Farm Area: Continued Works to be done is next period : 1. Minor finishes required in teachers' cottages 2. Grade 7: rendering works, 3. Retaining Wall: Final backfill and compaction methodology 4. Installation of windows and doors for Information and complete painting 5. Complete Farm Area 6. Fencing: Commence 7. Oswald Fisher Block: Louvre window and final finishes 8. Ethyl Mullings: Add guttering and replace window No.1 Issues/ Challenges: Awaiting Addendum. Certificate #1 86,313,544.26 PAID Window fabrication delayed due to material shortage.
52 |  | St. Ann | Walkerswood Academy |  | 23992645 | 5682500 | Damaged to metal frame classroom blocks A, B and timber roof at Admin. Replacement of sheeting ceiling and block A and B and Admin and electrical installation to code. | 1 | TSU | Cambridge Trading Limited | 2 | Approval granted | 2026-01-20 | 2026-08-07 | Work Completed | Final account is being prepared
53 |  | Trelawny | Cedric Titus High |  | 32017700 |  | Repairs to existing Teachers Cottages to include Upgrading of Electrical System | 1 | NET | Skymar | 1 | Approval granted | 2026-01-29 | 2026-07-28 | Work Completed | Project Percentage Completion: 100% Project Status: A taking-over certificate was issued to the contractor on July 13, 2026. Proposed Project Completion Date: Issues:/Challenges:
54 |  | Trelawny | Troy High |  | 13659120 | 9937689.6 | Upgrading of Water Supply and Catchment System | 1 | NET | J. Neil Construction | 3 | Approval granted | 2026-06-19 | 2026-09-18 | Work Completed | Project Percentage Completion: 100% Rainwater Installation - 100% Classroom Partition - 100% Window - 100% Chain-link Fence - 100% Actual Project Completion Date: June 31, 2026 next week:
55 |  | Trelawny | Westwood High |  | 389223204.82 | 88710079.45 | "Construction of reinforced concrete slabs for the Teacher's Cottages, Visitors Area, Concrete water tanks Replacement of timber roof for Classrooms and TD Building Replacement of sheeting for Auditorium Renovation of Principal's Cottage" | 1 | NET | Pavecon Ltd. | 1 | Approval granted | 2026-02-19 | 2026-10-01 | 80% - 94% ; work in progress | Project Percentage Completion: 80% Reroofing four classrooms - 100% Reroofing TD Building - 90% Reroofing auditorium - 100% Reroofing cottages - 90% Renovation of cottages - 85% Reroofing visitors area/hostel/6th form - 90% Restoration of Nurses station - 90% Renovation of Principal's Quarters - 85% Covering of water tanks - 100% Proposed Project Completion Date: EOT ( October 1, 2026 Issues:/Challenges: Contractor has been assigned a significant number of projects with several outstanding payments disrupting cash flow and slowing activity at several sites. Additional floor repairs being considered in the TD Building. Additional items being considered for scope to be determined.
56 |  | Trelawny | William Knibb Memorial High |  | 478912048.12 | 186579126.44 | Re-sheeting of classroom block, gazebo, chicken house, and construction of fencing | 1 | NET | Archistruct Limited | 1 | Approval granted | 2026-03-12 | 2026-09-11 | 80% - 94% ; work in progress | Project Percentage Completion: 91% as of September 17, 2026. Proposed Project Completion Date: September 30, 2026 (Awaiting contractors formal request for extension of time) Project Status: Ceiling works have been completed, Works on the staffroom ceiling remains ongoing, however, works on the staffroom ceiling remains ongoing. Roof works and construction of the gazebo have been completed. Work Scheduled for Next Period: Installation of windows and doors and electrical and teachers' cottage and staffroom works remain ongoing. Issues:/Challenges:
57 |  | Trelawny | Holland High |  | 458017973.2 | 45801797.32 | Repairs to the roofing and ceiling on all blocks to include the administrative building, labs, staff room and repairs to the poultry house | 1 | NET | Buildrite | 1 | Approval granted | 2026-06-11 | 2026-12-10 | 20% & Below ; work in progress | Project Percentage Completion: 12% Proposed Project Completion Date: December 30, 2026 Project Status: Painting to the grades 7 and 8 has been completed. The preparation of the south-western boundary wall and removal of existing PVC vinyl and batt insulation are ongoing. Issues:/Challenges: Difficulty finding skilled labour and sub-contractors; contractors, as rates are not attractive this then intern creates a demand and supply dilemma. Difficulty in getting the required material from suppliers on time, due to bottleneck effect and limited raw materials.
58 |  | St. Ann | Marcus Garvey Technical (St. Ann's Bay) |  | 122665651 | 74588871.59 | Renovation to Industrial Arts Department and Poultry House | 1 | NET | N.F Barnes Construction | 1 | Approval granted | 2026-01-09 | 2026-06-30 | Work Completed | Project Completed and taking Over Certificate Issued on August 4, 2026
|  |  | Marcus Garvey Technical (Mansfield) |  | 31854000 |  | Damaged to waterproofing membrane at Blocks A,B and C and chain-link fence. Replacement of waterproofing membrane to Blocks A, B and C. Installation of chain-link fencing. | 1 | TSU | Costley's Construction | 1 | Approval granted | 2026-01-05 | 2026-08-07 | Work Completed | Final account is being prepared
59 |  | Trelawny | Muschett High |  | 262541050 |  | Roofing repairs to multiple buildings to include the admin department, water proofing of the concrete slabs, renovation to the teachers cottages and allied health centre | 1 | NET | Skymar Construction | 1 | Approval granted | 2026-06-11 | 2026-12-08 | 41% - 50% ; work in progress | Project Percentage Completion: 47% Proposed Project Completion Date: December 8, 2026 Project Status: Electrical, plumbing, carpentry, masonry, and painting works are ongoing. Waterproof membrane was completed for the Administrative and main buildings Issues:/Challenges: .
[7 empty] | Installation of water harvesting & sanitation, water storage and pumps | 1 | DONOR | UNICEF
60 |  | St. Ann | Brown's Town Community College - Main & Technical Campus |  | 394313050 | 132571279.67 | Roof repairs including modification of roof to slab. Electrical work and general repairs to facilities | 1 | NET | Morris Hill Limited | 1 | Approval granted | 2026-01-26 | 2026-07-25 | 51% - 60% ; work in progress | Project Percentage Completion: 60% Proposed Project Completion Date: October 30, 2026, (Awaiting contractors formal request for extension of time) Project Status: Work is currently being carried out to the following buildings: N1 Building 1. Replace roof 100% 2. Painting 90% Swaby Building 1. Replace Roof 100% 2. Electrical 95% 3. Painting 95% Canteen 1. Replace Roof 100% 2. Painting 90% Arts Building 1. Replace Roof 100% 2. Painting 90% 3. Electrical 90% Computer Building 1. Replace roof 95% 2. Electrical 0% 2. Painting 0% Student's Affairs Building 1. Replace roof 95% 2. Electrical 0% 3. Painting 0% Issues:/Challenges:
60 | TOTAL |  |  | 292190664.4 | 5874294263.62 | 1556395192.09
9
Formulas:
Contract End Date = [Contract Start Date]+90

## REGION 4
POST-HURRICANE ASSESSMENT DATA ― IMPACT OF HURRICANE MELISSA ON SCHOOLS' INFRASTRUCTURE
No of Schools | Region | Parish | Name of School | Preliminary Cost $ | Contract Sum $ | Expenditure to Date $ | Scope of Works | PRIORITY 1. Severely Damaged - may affect school reopening. 2. Moderately Damaged - Significant repairs. School can operate while repairs are done. 3. Minor Damage - school can operate while repairs are done. | Person Responsible (TSU , NET, JSIF , DONOR) | Name of Contractor Assigned | Contractor Grade | Projected Date of Procurement for PS Approval | Contract Start Date | Contract End Date | Status | Remarks
1 | 4 | St. James | Corinaldi Avenue Primary |  | 104263300 | 58669693.97 | Repairs to roofs, ceiling and gutters for Grades 2, 3 and 4 buildings to be replaced. Repairs to electrical system, water storage facility and security post as per Standard Building Code | 1 | NET | Brothers Concept | 1 | Approval granted | 2026-04-23 | 2026-10-22 | 61% -79% ; work in progress | Project Percentage Completion: 67% Proposed Project Completion Date: October 2026 Project Status: Project on Track Issues:/Challenges: Variation approval pending to facilitate payment
2 |  | St. James | Cornwall College |  | 351250547.5 |  | Repairs to lower school library, staffroom, classroom and science lab and roof. Repairs to upper school science building, staffroom, Grades 10 & 11 buildings. Roof repairs to Auditorium & Canteen Building. Fencing, repairs to block wall near the playfield. Replacement of damage windows and doors as per Standard Building Code | 1 | NET | Brothers Concept | 1 | Approval granted | 2026-08-28 | February 29, 2027 | 21% - 40% ; work in progress | Project Percentage Completion: 40% Proposed Project Completion Date: February 2027 Project Status: Issues:/Challenges: Awaiting payments for other projects and issuance of contract for this project.
3 |  | St. James | Green Pond High | 100000000 |  |  | Repairs to sewer system, windows and doors and canteen. Repairs to bathrooms and corridor roofing. Roof, ceiling & gutter repairs, windows, electrical, repairs to holding area, security post repairs, sanitation, water storage, as per Standard Building Code | 1 | DONOR | Sagicor |  |  |  |  | 21% - 40% ; work in progress | Project Percentage Completion: 30% Proposed Project Completion Date: Project Status Works done in the week of the current period: Works to be done is next period: Issues:/Challenges:
4 |  | St. James | Montego Bay High |  | 114336600 | 7176180 | Repairs to roof on old stone building and a timber-framed building as per Standard Building Code | 1 | NET | RSJ Construction Company Limited | 2 | Approval granted | 2026-04-16 | 2026-10-15 | 41% - 50% ; work in progress | Project Percentage Completion: 50% Proposed Project Completion Date: October 15, 2026 Project Status: Works ongoing Issues:/Challenges: Contractor made arrangement with the principal to discuss completion of roofing. Final roof repairs to commence September 18, 2026
5 |  | St. James | Montego Bay Infant |  | 112303500 | 17332973 | Roof of Principal office, canteen and Staffroom, lower class building and auditorium roofs are damaged. Installation of windows and doors, and repairs to stonewall boundary as per Standard Building Code | 1 | NET | Construction 365 Company Limited | 1 | Approval granted | 2026-05-25 | 2026-11-24 | 80% - 94% ; work in progress | Project Percentage Completion: 85% Proposed Project Completion Date: November 21, 2026 Project Status: Works ongoing Issues:/Challenges:
6 |  | St. James | Mount Salem Primary and Infant |  | 147721875 |  | Roof repairs to main classroom block as per Standard Building Code | 1 | NET | C&D Construction | 1 | Approval granted | 2026-07-28 | 2027-01-29 | 20% & Below ; work in progress | Project Percentage Completion: 15% Proposed Project Completion Date: January 2027 Project Status: Issues:/Challenges: Contractor awaiting contract issuance
7 |  | St. James | St. James High |  | 132893000 |  | Roof repairs on admin building, electrical repairs/supply, windows and doors as per Standard Building Code | 1 | NET | RSJ Construction Company Limited | 2 | Approval granted | 2026-05-22 | 2026-11-23 | 61% -79% ; work in progress | Project Percentage Completion: 65% Proposed Project Completion Date: November 2026 Project Status: 80% re-roofing, 100% waterproofing, Ceiling & Electrical works ongoing Issues:/Challenges:
8 |  | St. James | Barracks Road Primary | 5000000 |  |  | Landscaping and beautification project at front of school wall - planter box, concrete walkway | 1 | DONOR | NET / UNICEF |  |  |  |  | 61% -79% ; work in progress | UNICEF
[7 empty] | Repairs to windows and electrical system to main classroom block as per Standard Building Code | 1 | TSU | [5 empty] | Contractor to be given site possession | 1. Site assessment Completed 2.Pre-Tender Estimate Completed 3.Contractor Priced BQ's being reviewed for submission by September 25, 2026
9 |  | St. James | Green Pond Primary and Infant |  | 34177172 |  | Roof repairs to classroom buildings, canteen and corridors, repairs / modification of suspended ceiling, electrical repairs | 1 | TSU | VM Construction & Haulage | 2 | Approval granted | 2026-02-14 | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion
10 |  | St. James | Buckingham Primary and Infant | 75000000 |  |  | Roof repairs to lower school, canteen and classrooms. Repairs to damaged upper school buildings as per Standard Building Code | 1 | NET | Pavecon | 1 |  |  |  | Contractor to be given site possession | Project Percentage Completion: 0% Preliminary designs for the rebuild has been received and feedback provided. Final designs being completed. Proposed Project Completion Date: To be determined pending issuance of commencement letter Project Status: Technical Team to review the contractors submission for D+B Issues:/Challenges: "Final design and BQ submitted on September 11, 2026. To be reviewed by Technical Team "
11 |  | St. James | Goodwill Primary and Infant |  | 100127350 | 69034000.85 | Roof, ceiling, electrical, waterproofing, toilets and replacement of water tanks . Repairs to the library and the Infant department as per Standard Building Code | 1 | NET | CA Quality Development & Construction | 1 | Approval granted | 2026-04-16 | 2026-10-15 | 21% - 40% ; work in progress | Project Percentage Completion: 21% Proposed Project Completion Date: October 15, 2026 Project Status: Issues:/Challenges: Awaiting payment
12 |  | St. James | John Rollins Success Primary |  | 35522900 |  | Replacement of roof sheeting of main classroom building. Construction of security fence and guardhouse as per Standard Building Code | 1 | NET | Pavecon | 1 | Approval granted | 2026-08-10 | 2027-02-11 | 21% - 40% ; work in progress | Overall Project Percentage: 40% Progress: 1. Roof sheeting being removed to accommodate dedusting and coating of walkway framing – All Blocks 2. Priming of all metal connections throughout 3. Roof-work to rectify classrooms that were leaking 4. Removal of guttering and flashing that showed signs or decay/rust 5. Replacing damaged zinc sheeting for roof – All blocks 6. Removing tree from Block 2 roof and replace damaged areas 7. Removing damaged Purlins from Gazebo 8. Removing damaged purlins from staircase areas Upcoming Events: 1. Excavation of foundation for block boundary wall 2. Make new to damaged chain link fencing 3. Removal & replacing of Guttering and flashing 4. Bathroom works for Canteen area. 5. Replacing of mesh for Canteen/kitchen 6. General painting Issues: 1. Planning works to minimize disruption of school activities 2. Long lead time for metal works material delivery Resolution: 1. Night works initiated and extending the work week to include Saturdays and Sundays.
13 |  | St. James | John's Hall Primary | 150000000 |  |  | Repairs to roof and structure. Repairs to electrical supply, construction of retaining wall as per Standard Building Code | 1 | NET | CA Quality Development & Construction | 1 | Approval granted |  |  | 20% & Below ; work in progress | Project Percentage Completion: 5% Proposed Project Completion Date: Project Status: Temporary classrooms 1. Excavate Foundation 100% 2. Cast Foundation 100% 3. Timber walling 50% Preparation of Design and working drawings 1. Preliminary Designs 10% 2. Working Drawings 05% 3. Municipal Approval 0% Reconstruction of Classroom and Administrative Block 1. Setting Out 0% 2. Excavation of Foundation 0% Issues:/Challenges:
14 |  | St. James | Mount Zion Primary and Infant |  | 191720978.84 | 68454220.65 | Reconstruction of toilet block and roof repairs to main classroom building as per Standard Building Code | 1 | NET | Construction Solutions Limited |  | Approval granted | 2026-06-19 | 2026-12-20 | Work to Commence | Project Percentage Completion: 0% Proposed Project Completion Date: December 2026 Project Status: Work to commence pending payment of mobilization Issues:/Challenges: Contractor awaiting payment for mobilization
15 |  | St. James | Somerton Primary and Infant | 70000000 |  |  | Roof repairs and window replacement | 1 | NET | S&G |  |  |  |  | Contractor to be given site possession | Project Percentage Completion: 0 Proposed Project Completion Date: To be determined pending issuance of commencement letter Project Status: Technical team to review. Issues:/Challenges:
16 |  | St. James | Spot Valley High |  | 73803000 | 20195972.5 | Repairs to roof, electrical system and gutter replacement to main building as per Standard Building Code | 1 | NET | Monticon Limited | 1 | Approval granted | 2026-03-27 | 2026-09-28 | 80% - 94% ; work in progress | Project Percentage Completion: 90% Proposed Project Completion Date: September 30, 2026 Project Status: Issues:/Challenges: The contractor has formally submitted a claim for payment. This claim is currently undergoing internal review and has not yet been disbursed
17 |  | St. James | Sudbury Primary and Infant |  | 27938000 |  | Roof repairs, electrical repairs and replacement of doors, windows and cupboard | 1 | NET | Marlon Turner Construction | 1 | Approval granted | 2026-06-19 | 2026-12-20 | 20% & Below ; work in progress | Project Percentage Completion: 15% Proposed Project Completion Date: December 12, 2026 Project Status: CONTRACTOR COMMENCED WORKS AUGUST 3, 2026 Issues:/Challenges: None
18 |  | St. James | Adelphi Primary | 25000000 |  |  | Repairs to roof and roof members and electrical system to main classroom block as per Standard Building Code | 1 | TSU | C & D Construction and Engineering Limited | 1 | 2026-03-17 |  |  | 20% & Below ; work in progress | Temporary structure under construction . QS assigned. Priced estimate to be completed by contractor by August 31, 2026
19 |  | St. James | Barrett Town Primary and Infant |  | 30267285 |  | Repairs to roof, ceiling, windows and doors, sanitation and siding of building of main classroom block as per Standard Building Code | 1 | TSU | Tropical Metal Products Limited | 1 | Approval granted | 2026-02-11 | 2026-05-07 | 95% - 99% ; practical completion | Practical Completion attained. Variation order to be requested for critical termite treatment
20 |  | St. James | Dumfries Primary |  | 14027637 |  | Repairs to roof, electrical system, fencing and water storage to main classroom block as per Standard Building Code | 1 | TSU | Tropical Metal Products Limited | 1 | Approval granted | February 11, 2026 | 2026-09-04 | Work Completed | Final Account to be prepared
21 |  | St. James | Irwin High |  | 33000000 |  | Repairs to roof, electrical system and water supply to block B and C as per Standard Building Code | 1 | TSU | V M Construction & Haulage |  | Approval granted | 2026-01-24 | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion
22 |  | St. James | Irwin Primary |  | 21430000 | 10095300 | Repairs to roof, ceiling and electrical system to Block 2 as per Standard Building Code | 1 | TSU | V M Construction & Haulage | 3 | Approval granted | 2026-01-23 | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion
23 |  | St. James | Lottery Primary and Infant |  |  |  | Repairs to roof, electrical system and water storage to school buildings (3) as per Standard Building Code | 1 | TSU | THLC Company Limited | 2 | 2026-03-24 |  |  | 20% & Below ; work in progress | Temporary structure completed . QS assigned.
24 |  | St. James | Bogue Hill Primary and Infant | 25000000 |  |  | Repairs to roof for infant department as per Standard Building Code | 1 | DONOR | Canadian Trades Professionals and JDF |  |  |  |  | Work Completed | Work completed December by Donor - Canadian Trades Professionals and JDF
|  |  |  | 16674500 |  |  | Repairs to roof for infant department as per Standard Building Code | 1 | NET | Yardworks Construction |  |  |  |  | Contractor to be given site possession
25 |  | St. James | Catherine Hall Primary and Infant |  | 127740135.37 | 28872380 | Repairs to damaged canteen. Roof repairs to the kitchen, waterproofing of roof and window replacement as per Standard Building Code | 1 | NET | Brothers Concept & Solutions Limited | 1 | Approval granted | 2026-06-19 | 2026-12-18 | 80% - 94% ; work in progress | Project Percentage Completion: 80% Proposed Project Completion Date: December 18, 2026 Project Status: Works being completed on the Canteen & Storeroom Issues:/Challenges: Funding
26 |  | St. James | Herbert Morrison Technical |  | 562597880 | 49208210 | Roof, ceiling and gutters repairs and replacement, electrical repairs. Replacement of windows and doors, canteen and auxiliary building repairs as per Standard Building Code | 1 | NET | Costley Construction | 1 | Approval granted | 2026-02-19 | 2027-08-18 | 51% - 60% ; work in progress | Project Percentage Completion: 55% Proposed Project Completion Date: Project Status: Issues:/Challenges: Addendum to contract was issued and payment can now be processed.
27 |  | St. James | Tower Hill Primary and Infant | 228813502.5 |  |  | Roof repairs and electrical repairs | 1 | NET | CA Quality Development & Construction | 1 |  |  |  | Work to Commence | Project Percentage Completion: 0% Proposed Project Completion Date: Project Status: Awaiting contractors submission to finalize issuance of commencement letter Issues:/Challenges: Awaiting contractors submission
28 |  | St. James | Granville Primary and Infant |  | 29225229 |  | Major repairs to roof system, windows and doors, sanitation, metal staircase and siding of building to canteen and classroom block. Repairs to roof for infant department as per Standard Building Code | 1 | TSU | Tropical Metal Products Limited | 1 | Approval granted | 2026-02-14 | 2026-09-11 | 80% - 94% ; work in progress | Practical Completion
29 |  | St. James | Howard Cooke Primary |  | 23526900 |  | Waterproofing of slab roofs. Replacement of roofs. Electrical repairs. Repairs to sections of perimeter wall / fencing. Clearing of mud clogged drains, Replacement of doors. Canteen repairs, Sanitation repairs to main classroom and office as per Standard Building Code | 1 | TSU | Marken Construction Company Limited | 3 | Approval granted | 2026-03-24 | 2026-09-04 | 80% - 94% ; work in progress | Practical Completion
30 |  | St. James | Chetwood Memorial Primary |  | 23526900 |  | Repairs to Canteen, two classrooms and part of Grade 2 block. Replacement of Grade three classroom windows | 1 | DONOR | Canadian Trades Professionals and JDF |  |  |  |  | Work Completed | Project Percentage Completion: 100% Project Status: Project completed-Donor initiative
|  |  |  | 30000000 |  |  | Repair of Grade 2 classroom roof | 1 | NET | Brothers Concept |  |  |  |  | Contractor to be given site possession
31 |  | St. James | Flankers Primary and Infant |  | 70658775.37 |  | Toilet block repairs, roof repairs, associated electrical repairs | 1 | NET | Brothers Concept | 1 | Approval granted | 2026-06-19 | 2026-12-20 | 41% - 50% ; work in progress | Project Percentage Completion: 45% Proposed Project Completion Date: December 18, 2026 Project Status: Works ongoing at a slow pace. Issues:/Challenges: Contractor awaiting payments
32 |  | St. James | Mount Alvernia High |  | 177968965 | 31711077.39 | Repairs to roofs, ceiling, and gutters on buildings . Repairs to fence and windows | 1 | NET | Costly Construction | 1 | Approval granted | 2026-06-26 | 2026-12-27 | 41% - 50% ; work in progress | Project Percentage Completion: 48% Proposed Project Completion Date: Project Status: December 2026 Issues:/Challenges: Works delayed
33 |  | St. James | Anchovy High |  | 120285650 | 41698079.5 | CAMPUS 2 - Significant roof replacement on buildings - classrooms, toilets, sickbay, computer room, fence repairs, water storage CAMPUS 1 - Roof replacement & ceiling installation on Auditorium building. Roof replacement in book room. Other roof replacement on cottage building, classroom. Fence repairs | 1 | NET | Build Management Technology & Logistic | 2 | Approval granted | 2026-04-08 | 2026-10-09 | 80% - 94% ; work in progress | Project Percentage Completion: 80% Proposed Project Completion Date: October 2026 Project Status: Works delayed Issues:/Challenges: Roofing activities has encountered delays due to a shortage of essential materials, specifically purlins and sheeting.
|  |  | Anchovy High (Fidel Castro Campus) | 126578000 |  | 45714740 | Construction of 8 classrooms and sanitary facilities (containerised system being erected as temporary measure) | 1 | NET | Pave-con Limited |  | Approval granted | 2026-08-28 |  | Work to Commence | Project Percentage Completion: 0% Proposed Project Completion Date: October 2027 Project Status: Container systems shipped Issues:/Challenges: Payment issues
34 |  | St. James | Anchovy Primary |  | 174675554.9 | 47140642.65 | Re-roofing. Roof, ceiling, and electrical. (Recommending slab) | 1 | NET | Diverse Services & Construction Limited |  | Approval granted | 2026-03-19 | 2026-09-20 | 80% - 94% ; work in progress | Project Percentage Completion: 88% Proposed Project Completion Date: September 2026 Project Status: Works delayed Issues:/Challenges: Payment
35 |  | St. James | Cambridge High |  | 317308190.2 | 47596228.53 | Fencing, electrical, water tanks, sanitation, cottage flats | 1 | NET | Build- Rite Construction | 1 | Approval granted | 2026-06-11 | December 12, 2026 | 51% - 60% ; work in progress | Project Percentage Completion: 60% Proposed Project Completion Date: December 2026 Project Status: Roof membrane completed Issues:/Challenges: Payment of claim
36 |  | St. James | Cambridge Infant |  | 74963600 | 20494950 | Replace destroyed timber building. Fencing. Electrical. General repairs | 1 | NET | Build- Rite Construction | 1 | Approval granted | 2026-03-26 | 2026-09-27 | 80% - 94% ; work in progress | Project Percentage Completion: 85% Proposed Project Completion Date: September 2026 Project Status: Works delayed Issues:/Challenges: Payment issues
37 |  | St. James | Cambridge Primary |  | 125499000 | 38814535 | Roof, ceiling & gutters replacement, | 1 | NET | Marlon Turner Construction |  |  |  |  | 21% - 40% ; work in progress | Project Percentage Completion: 28% Proposed Project Completion Date: December 2026 Project Status: Work is ongoing Issues:/Challenges: Awaiting contract issuance
38 |  | St. James | Catadupa Primary |  | 64251628.1 | 25062007.7 | Roof repairs to the main building, computer room, Grade 6 classroom block. | 1 | NET | Diverse Services & Construction Ltd | 1 | Approval granted | 2026-03-19 | 2026-09-19 | 80% - 94% ; work in progress | Project Percentage Completion: 95% Proposed Project Completion Date: September 20, 2026 Project Status: Taking over certificate to be issued Issues:/Challenges: None
39 |  | St. James | Chatsworth Primary and Infant |  | 56524006 | 27445576.8 | Roof, Roof members, electrical, water storage, windows and doors, external erosion, repairs to sanitation | 1 | NET | Diverse Services & Construction Ltd | 1 | Approval granted | 2026-03-19 | 2026-09-19 | 95% - 99% ; practical completion | Project Percentage Completion: 95% Proposed Project Completion Date: September 20, 2026 Project Status: Taking over certificate to be issued Issues:/Challenges: None
40 |  | St. James | Garlands Primary |  | 182212339.13 |  | Re-roofing of Timber building, guard house and cottage and replacement of water tanks | 1 | NET | Brothers Concept | 1 | Approval granted | 2026-06-19 | 2026-12-20 | Work to Commence | Project Percentage Completion: 0% Proposed Project Completion Date: December 2026 Project Status: Issues:/Challenges: Contractor awaiting payment for other projects to commence works at this site
41 |  | St. James | Lethe Primary and Infant |  | 209937690 |  | Replacement of roof and clean mud from classrooms. Replace timber buildings at Infant Department | 1 | NET | CA Quality Development & Construction | 1 | Approval granted |  |  | Work to Commence | Project Percentage Completion: 0% Proposed Project Completion Date: March 2027 Project Status: Issues:/Challenges: Awaiting contractor's submission
42 |  | St. James | Mount Carey Baptist Infant |  | 82681787 | 40202066.75 | Repairs to roof, ceiling, gutters, fencing, electrical and classroom | 1 | NET | Monticon | 1 | Approval granted | 2026-07-29 | 2026-01-30 | 61% -79% ; work in progress | Project Percentage Completion: 61% Proposed Project Completion Date: September 30, 2026 Project Status: Works ongoing Issues:/Challenges:
43 |  | St. James | Vaughansfield Primary and Infant |  | 53890000 |  | repairs- Roof, Roof members, electrical, water storage, windows and doors | 1 | NET | Sylvester |  | Approval granted | 2026-06-19 | 2026-12-18 | Work to Commence | Project Percentage Completion: 0% Proposed Project Completion Date: December 2026 Project Status: Work to commence Issues:/Challenges:
44 |  | St. James | Maldon High |  | 26844100 |  | Roof repairs to classroom, tuck shop, cottage and eating area; electrical repairs and painting as per Standard Building Code | 1 | TSU | D.R. Foote Construction Co. Ltd | 1 | 2026-01-16 | 2026-01-23 | 2026-09-04 | 80% - 94% ; work in progress | Practical Completion, Variation order being prepared for additional work on damaged wall and cottage
45 |  | St. James | Maldon Primary |  | 38354497 |  | Roof and water pipes repairs to main classroom block as per Standard Building Code | 1 | TSU | Tropical Metal Products Limited | 1 | Approval granted | 2026-02-28 | 2026-09-11 | 80% - 94% ; work in progress | Practical Completion
46 |  | St. James | Mount Horeb Primary and Infant |  | 29031100 |  | Repairs to roof and electrical system to main classroom block as per Standard Building Code | 1 | TSU | D R Foote Construction Company Limited | 1 | Approval granted | 2026-01-23 | 2026-09-04 | 80% - 94% ; work in progress | Practical Completion. Particular work now focussed to maintaining Infant Department
47 |  | St. James | Niagara Primary and Infant |  | 14295400 | 17393850 | Repairs to roof and electrical system to main Primary School building as per Standard Building Code | 1 | TSU | V M Construction & Haulage |  | Approval granted | 2026-01-23 | 2026-09-04 | 80% - 94% ; work in progress | Practical Completion.
48 |  | St. James | Orange Hill Primary and Infant |  | 40106190 | 13251000 | Repairs to roof, windows and doors, electrical system and water harvesting to main classroom building as per Standard Building Code | 1 | TSU | Cambridge Trading Limited | 2 | Approval granted | 2026-02-02 | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion. Final Account to be completed
49 |  | St. James | Roehampton Primary & Infant |  | 55810250 |  | Repairs to roof, water storage and electrical system to main classroom building as per Standard Building Code | 1 | TSU | Tropical Metal Products Limited | 2 | 2026-03-24 |  |  | 41% - 50% ; work in progress | Work in progress
50 |  | St. James | Springfield Primary and Infant |  | 49620124 |  | Waterproofing of roof slab, window replacement, water storage, chain-link fence to main classroom building as per Standard Building Code | 1 | TSU | Modern Waterproofing & Construction | 1 | Approval granted | 2026-01-29 | 2026-09-04 | 80% - 94% ; work in progress | Practical Completion. Defects being addressed
51 |  | Hanover | Askenish Primary and Infant |  | 188827125 | 32463223.53 | Roof, ceiling, gutters and associated electrical | 1 | NET | NF Banes |  | Approval granted | 2026-05-22 | 2026-11-21 | 41% - 50% ; work in progress | Project Percentage Completion: 60% Proposed Project Completion Date: November 21, 2026 Project Status: Classroom Block 1. Replace roof and ceiling 98% 2. Electrical Repairs 0% 3. Painting 0% Administrative Block 1. Repair roof 0% 2. Provide Toilet Facility 0% 3. Electrical 0% 4. Painting 0% Teachers Cottage 1. Demolish Existing Roof 100% 2. Replace roof 90% Issues:/Challenges:
52 |  | Hanover | Clifton Primary and Infant |  | 91031700 | 18110400.8 | Roof, ceiling, gutters and associated electrical and fencing | 1 | NET | NF Barnes | 1 | Approval granted | 2026-05-27 | 2026-11-26 | 21% - 40% ; work in progress | Project Percentage Completion: 35% Proposed Project Completion Date: November 2026 Project Status: Administrative, Classroom and Kitchen Block 1. Replace Timber Roof 50% 2. Cast slabs 100% 3. Electrical 0% 4. Painting 0% Infant Block 1. Repair Roof 0% Issues:/Challenges: Progress on this project is very slow.
53 |  | Hanover | Cove Primary |  | 49239520 | 10111097.5 | Roof, ceiling, gutters and associated electrical and window and doors | 1 | NET | NF Barnes | 1 | Approval granted | 2026-05-06 | 2026-11-07 | 20% & Below ; work in progress | Project Percentage Completion: 05% Proposed Project Completion Date: November 2026 Project Status: Principal's Cottage 1. Demolish Existing Roof 100% 2. Replace roof 05% Issues:/Challenges: The initial scope included repairs to the Administrative and Classroom Block, however this aspect of the repair work was being carried by Sandals Resort
54 |  | Hanover | Green Island High |  | 76172400 | 39712864.75 | Waterproofing of roof, Metal Works, Windows and doors, structural reinforcements To make repairs and install roof slab to construction build To make repairs and install roof slab to Agri Room To make repairs and install roof slab to teachers cottage To make repairs to poultry house and install timber roof To make repairs to nursery and install timber roofing Waterproofing membrane to be installed to roofing slabs | 1 | NET | Dukes Electrical and Building Solutions Limited | 2 | Approval granted | 2026-02-02 | 2026-08-01 | 61% -79% ; work in progress | Project Percentage Completion: 76% Poultry House - 80% Construction Classroom - 95% Agri Classroom - 96% Slaughter House - 75% Cottage - 70% Nursery - Proposed Project Completion Date: September 31, 2026 (EOT GRANTED) Works done this week: Poultry House - wire mesh installation to poultry house Construction Classroom Rendering completed. Agri Classroom - Painting works ongoing Slaughter House - Roof sarking installed Cottage - Wall rendering completed. Garage roof framed Works to be done next week: Agri Classroom - Painting to be completed Slaughter House - Roof sheeting to be installed Cottage - Membrane to be installed. Sheeting to be installed. Construction Classroom - Windows to be installed Comments/Issues:/Challenges: Claim #2 is yet to be processed.
55 |  | Hanover | Rusea's High |  | 153908858 | 56090769.2 | Campus 1 Replace roof of Grade 11 block, 4 Teacher's cottages buildings, and Tuckshop. Auditorium- replace doors gone and roof repairs. Campus 2 Roof repairs for a sections of main building. Roof replacements for the entire section of building that houses the computer lab and the tuckshop. Roof replacement for the canteen and sections of the roof on the Industrial Arts building and Grade 8 building. Repairs to Students' restrooms, and guidance department. | 1 | NET | J & H Construction | 1 | Approval granted | 2026-01-26 | 2026-07-25 | 80% - 94% ; work in progress | Project Percentage Completion: 80% 7 & 8 Block (Brick) - 100% Block 7 & 8 T1-11 Building - 50% Block A/Computer Lab - 100% Gazebo (Campus 1) - 0% Container Tuck Shop (Campus 1) - 100% Industrial Block - 75%Grade Bathroom (Male and Female) - 100% Canteen (Campus 2) - 90% Teacher Room - 90% Old Fort Building - 100% Overall Demolition - 95% Proposed Project Completion Date: October 31, 2026 Works done this week: 7&8 Block (Brick building roofing) - 85% Old Fort Building (roofing) - 100% Works to be done next week: Comments/Issues:/Challenges: Contractor to provide costing for variations items identified.
56 |  | Hanover | Cacoon Primary and Infant |  | 15888037 | 13238037 | Roof repairs, waterproofing of slab roofs, restoration of wall, chain-link fencing to main classroom building as per Standard Building Code | 1 | TSU | Cambridge Trading Limited | 2 | Approval granted | 2026-02-10 | 2026-09-04 | 80% - 94% ; work in progress | Practical Completion. Defects being addressed
57 |  | Hanover | Cave Valley Primary and Infant |  | 29324000 |  | Major replacement and repairs on all buildings – roof sheeting & members, blocking boards, sarking. Replacement of roof drainage system, termite treatment. Repairs to electrical system – supply and lighting arrestor and associated painting to main classroom building as per Standard Building Code | 1 | TSU | THLC Company Limited | 2 | Approval granted | 2026-03-31 | 2026-09-04 | 80% - 94% ; work in progress | Practical Completion
58 |  | Hanover | Chambers Pen Primary |  | 16004311 |  | Repairs to roof of canteen, electrical system and fence as per Standard Building Code | 1 | TSU | THLC Company Limited | 2 | Approval Granted | 2026-03-02 | 2026-09-11 | 80% - 94% ; work in progress | Practical Completion
59 |  | Hanover | Church Hill Primary |  |  |  | Repairs to electrical supply and distribution, roof repairs and fence repairs to main classroom building as per Standard Building Code | 1 | TSU | Build Management Technology & Logistic |  | 2026-03-24 |  |  | Contractor to be given site possession | 1. Site Assessment Completed 2.Pre-Tender Estimate Completed 3.Contractor Priced BQ's being reviewed for submission by September 25, 2026
60 |  | Hanover | Esher Primary |  | 23413800 |  | Repairs to roof, windows and electrical system to main classroom building as per Standard Building Code | 1 | TSU | Marken Construction Company Limited | 3 | 2026-03-24 |  |  | 41% - 50% ; work in progress | Work in progress
61 |  | Hanover | Lucea Infant |  | 29690620 | 10718750 | Major repairs to roofing system, roof drainage, electrical system to main classroom building as per Standard Building Code | 1 | TSU | Modern Waterproofing & Construction | 1 | Approval granted | 2026-01-29 | 2026-09-11 | 95% - 99% ; practical completion | Practical completion attained. Addressing minor defects
62 |  | Hanover | Lucea Primary |  | 60985750 |  | Repairs to roof and roof members, waterproofing of concrete slab, electrical system, windows and doors to buildings 1 and 2 as per Standard Building Code | 1 | TSU | H T Roofing & Construction Limited | 2 | 2026-03-24 |  |  | 21% - 40% ; work in progress | Work in Progress
63 |  | Hanover | Pell River Primary |  | 13639800 |  | The decorative blocks needs to remove to replace with windows as it cannot withstand heavy rainfalls and hurricane seasons. Roof repairs to the canteen. Electrical works. Roof repairs to the Grade 5 and 6 and Grade 1 and 2 classroom blocks as per Standard Building Code | 1 | TSU | V M Construction & Haulage |  | Approval granted | 2026-01-23 | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion. Finla account to be completed
64 |  | Hanover | Bethel Primary |  | 113287564.73 | 16993134.71 | Grade 1 (Rebuild), Grade 1,2 & 3 Roofing and Electrical work | 1 | NET | Quality Plus Contracting Company Limited |  | Approval granted |  |  | 20% & Below ; work in progress | Project Percentage Completion: 20% Works commence - 17/8/2026 Grade 1 (Rebuild) - Awaiting Parish Council approval Grade 2 & 3 (Roof, walls & Columns) - 65% Proposed Project Completion Date: January 31, 2027 Works done this week: Sheeting and capping installation Site Hoarding Belt Beams Works to be done next week: Painting Works Masonry Comments/Issues:/Challenges:
65 |  | Hanover | Brownsville Primary |  | 123232623.08 |  | Major roof replacement on steel framed buildings, repairs to toilet building, electrical repairs | 1 | NET | Roger Land Development |  |  |  |  | Work to Commence | Project Percentage Completion: 0% Preliminaries Primary Block 1 Primary block 2 Bathroom Block Infant Block External works Proposed Project Completion Date: January 31, 2027 Works done this week: LOA issued to contractor. Works to be done next week: Contractor to mobilize on 7/9/2026 Comments/Issues:/Challenges: Awaiting confirmation from contractor in regards to the construction of temporary class
66 |  | Hanover | Claremont Primary and Infant |  | 50459950 |  | Repairs to roof of Infant department and fencing | 1 | NET | NF Barnes | 1 |  |  |  | 41% - 50% ; work in progress | Project Percentage Completion: 46% Preliminaries - 60% Demolition - 75% Roofing - 85% Fencing - Painting - 80% Electrical - 10% Proposed Project Completion Date: October 31, 2026 Works done this week: Ceiling works completed - Infant Department Painting works advanced Formwork to bathroom slab stripped Works to be done next week: Rendering to bathroom Painting to be completed Guttering to commence Comments/Issues:/Challenges:
67 |  | Hanover | Gurney's Mount Primary and Infant |  | 67413885 | 32191425.5 | Replace roof, doors and windows | 1 | NET | Cenitech | 1 | Approval granted | 2026-07-30 | 2027-01-31 | 61% -79% ; work in progress | Project Percentage Completion: 75% Preliminaries - 80% Primary School Block - 80% Infant School Block - 85% School Canteen/Admin - 80% Fencing - 0% Proposed Project Completion Date: September 31, 2026 Project Status: Works began on Monday August 3, 2026 Works done in the week of the current period: Infant Department - Ceiling painted. Canteen - Painting and electrical works completed Primary Department - Plycem Boards Installed Works to be done is next period: Infant Department - Damaged wood trims to be demolished and replaced. Painting to be completed Primary - Electrical works to commence Issues:/Challenges: Variation Items - Fencing, Primary partitions | This says 70% but band selected says 51-60%
68 |  | Hanover | Hopewell High |  | 67413885 |  | Roof repairs ( including corridors, two classrooms, goat pen, and receptacle). | 1 | DONOR | [5 empty] | 41% - 50% ; work in progress | Project Percentage Completion: 44% Awnings - 25% Roofing - 65% Fencing - 85% Guttering - Proposed Project Completion Date: September 30, 2026 Works done this week: Roofing repair to Goat pen Works to be done next week: Roof repairs to affected blocks Chain-link fence to be completed Comments/Issues:/Challenges:
69 |  | Hanover | Knockalva Technical High | 480176717.95 |  |  | Roof replacement on buildings, window replacement, door replacement, fencing repairs | 1 | NET | Brothers Concept |  |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 1.9% Block A - 5% Block B - 5% Cosmetology Lab Food Lab Block C Linkways Block D & Gr Block D13 Auditorium and Kitchen - 10% Auto Mechanic Teachers Flat - 2% Agri Units - 2% Classrooms atop block A 3 Cottages - 4% (Roof Demolition) Solar System Works commenced on the 7/8/2026. Proposed Project Completion Date: January 31, 2027 Works done this week: Screeding to Block A and B Installation of scaffoldings Slabs prepped to receive membrane Works to be done next week: Demolition to Auditorium and canteen roofing Roofing membrane to be installed to Block A and B Comments/Issues:/Challenges: Contractor has commenced works however the staffing is low. No LOA issued
70 |  | Hanover | Merlene Ottey High |  | 64548300.3 |  | To make General roofing repairs to Blocks: A1, A2, B, C, D, E1, E2, F, L, G and M Electrical works | 1 | NET | S&G Construction | 1 | Approval granted | 2026-07-29 | 2027-01-31 | 21% - 40% ; work in progress | Project Percentage Completion: 25% Blocks M1 - Blocks A1 and A2 - 50% Block B - Block D - Block C and E1 - 50% Block E2 - 60% Computer Lab - Block F Block L - 60% Greenhouse - Proposed Project Completion Date: January 31, 2027 Works done this week: Termite Treatment to classes Smart Board room - Membrane installation Ceiling repairs General Electrical works Home Econ Block - Roof capping in process Zinc sheeting replaced on blocks A1, A2, C, E1, E2 and Library Works to be done next week: Roofing works - Block M1 and B Replace damaged windows Replace white boards Library partition and ceiling replacement Computer room partition and ceiling Sliding window installation - General Transom windows to be replaced Comments/Issues:/Challenges: Variation document to be submitted
71 |  | Hanover | Mount Hannah Primary |  | 97071564.8 |  | Roof , ceiling, gutter and electrical | 1 | NET | Proven Construction |  | Approval granted | 2026-09-01 | 2027-03-02 | 61% -79% ; work in progress | Works commenced May 2026 Overall Project Percentage: 75% Progress: 1. Main Block- Roofing, plumbing and installation oof door and jambs ongoing 2. Gazebo- Reconstruction of gazebo almost complete Upcoming Events: 1. Main Building Continue installation of partition system (track and stud framing, Plycem boards, plastering and sanding). 2. Principal's Office Remove existing windows, redress openings and reinstall windows. 3. Tuck Shop & Storage Complete steel-float finish to floor. Issues: 1. Active learning environment 2. Limited availability of Plycem boards and other construction materials 3. Challenging geographical location and road conditions Resolution: 1. Work activities are being scheduled and managed to reduce disruption during school hours. 2. Procurement efforts are ongoing, and alternative suppliers are being explored where practical. 3. Material deliveries are being coordinated to minimize logistical delays.
72 |  | Hanover | Mount Ward Primary |  | 68066050 | 10209907.5 | Replace damaged roof with concrete slab. Establish steel water storage tank and support stand | 1 | NET | Monticon | 1 | Approval granted | 2026-08-10 | 2027-02-11 | 20% & Below ; work in progress | Project Percentage Completion: 2% Work commence - 17/8/2026 Preliminaries - Roofing - 15% Internal works - Furniture - Painting - Windows and doors - Water supply - Electrical - Fencing - Proposed Project Completion Date: February 11, 2027 Works done this week: Contractor has issues with the carpenter showing up. Carpenter to be replaced Works to be done next week: Roof to be framed Comments/Issues:/Challenges:
73 |  | Hanover | Pondside Primary |  | 64548300.3 |  | Waterproofing, linkway, windows, doors | 1 | NET | Construction 365 Company Limited | 1 |  |  |  | Contractor to be given site possession | Awaiting contractor's submission
74 |  | Westmoreland | Mount Airy Primary and Infant | 45000000 |  |  | Roof repairs, building repairs, water supply, electrical | 1 | NET | Pavecon | 1 |  |  |  | Contractor to be given site possession | Feedback provided to the preliminary designs. The Full design and BQ are expected by September 30, 2026
75 |  | Hanover | Watford Hill Primary |  | 58285800 | 6534150.19 | Repairs to roof and gutters of the main building with the computer lab. 3 blade window to be replaced, 2 double doors to be replaced. 2- Double doors to be replaced. | 1 | NET | Marlon Turner Construction |  | Approval granted | 2026-04-23 | 2026-10-22 | 80% - 94% ; work in progress | Project Percentage Completion: 91% Infant Department - 100% Pavillion - 100% Kitchen - 100% Main Building Roofing - 100% Main Building painting - 100% Fencing - 50% Windows, doors and guttering - 15% Electrical - 98% Proposed Project Completion Date: October 2026 Works done this week: Windows and doors fabricated - to be installed Works to be done next week: Installation of windows, doors and guttering Fencing works to commence (14/9/2026) Comments/Issues:/Challenges: Contractor submitted 2nd claim/variations. QS to review Contractor awaiting payments on other projects to complete works
76 |  | Hanover | Cacoon Castle Primary and Infant |  | 24118455 |  | Roof and ceiling repairs, waterproofing of slab roofs, electrical repairs and fence repairs to main classroom building as per Standard Building Code | 1 | TSU | Cambridge Trading Limited | 2 | Approval granted | 2026-02-10 | 2026-09-04 | 80% - 94% ; work in progress | Practical completion - variation order being prepared for windows and internal repairs to canteen
77 |  | Hanover | Chester Castle Primary and Infant |  | 46255500 |  | Repairs to roof, fencing and electrical system to main classroom building as per Standard Building Code | 1 | TSU | Maxwell Construction Company Limited | 2 | Approval granted |  | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion by September
78 |  | Hanover | Jericho Primary and Infant | 4000000 |  |  | Repairs to roof, water storage and windows to main classroom building as per Standard Building Code | 1 | TSU | Marshall Construction Company Limited | 1 | 2026-03-24 |  |  | Contractor to be given site possession | 1. Site Assessment Completed 2.Pre-Tender Estimate Completed 3.Contractor Priced BQ's being reviewed for submission by September 25, 2026
79 |  | Hanover | Maryland Primary and Infant |  | 35052441 |  | Repairs to roof and roof members and sanitation to Primary school and Infant Department as per Standard Building Code | 1 | TSU | RSJ Construction Company Limited | 2 | 2026-03-24 |  |  | 21% - 40% ; work in progress | Work in progress. Teaching areas are okay
80 |  | Hanover | Mount Peto Primary | 15000000 |  |  | Renovation of the canteen block and water supply, roof repairs to main classroom block as per Standard Building Code | 1 | TSU | Maxwell Construction Company Limited | 2 | 2026-03-24 |  |  | 21% - 40% ; work in progress | Work in progress. QS assigned.
81 |  | Hanover | Sandy Bay Primary |  | 29649600 |  | Repairs to roof and electrical system to office building, classroom and admin block and cottage as per Standard Building Code | 1 | TSU | THLC Company Limited | 2 | Approval granted | 2026-01-30 | 2026-05-18 | Work Completed | Final Account to be completed
82 |  | Hanover | Success Primary and Infant |  | 23235500 | 21234000 | Repairs to roof and roof members and electrical system to main classroom block and infant department as per Standard Building Code | 1 | TSU | D R Foote Construction Company Limited | 1 | Approval granted | 2026-02-17 | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion
83 |  | Westmoreland | Paul Island Primary and Infant | 70000000 |  |  | Roof, associated electrical, sanitation | 1 | DONOR | Pavecon |  |  |  |  | 20% & Below ; work in progress | Final Designs & BQ is to be submitted by the contractor for review on September 18, 2026. Foundation works has commenced.
84 |  | Westmoreland | Strawberry Primary and Infant |  | 80459170 |  | Roof, electrical, fencing, windows | 1 | NET | Pavecon | 1 | Approval granted | 2026-08-10 | 2027-02-11 | 80% - 94% ; work in progress | Overall Project Percentage: 80% Progress: Rehabilitation to Infant School 95% Rehabilitation to Primary School 60% Construction of library - 0% designs completed. Issues:/Challenges: Contractor awaiting contract to generate payment to undertake the works
85 |  | Westmoreland | Blauwearie Primary and Infant | 40000000 |  |  | Repairs to roof and electrical system | 1 | NET | C& D Construction |  |  |  |  | Contractor to be given site possession | Temporary facilities are currently being installed
86 |  | Westmoreland | Broughton Primary |  | 97524896 |  | Repairs to roof and electrical system to main classroom block as per Standard Building Code | 1 | TSU | Geecho Construction | 1 | Approval granted |  | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion
87 |  | Westmoreland | Friendship Primary and Infant |  | 81965511.08 |  | Repairs to roofs, fencing, windows, doors, cottage, electrical system to main classroom block as per Standard Building Code | 1 | TSU | Marshall Construction Company Limited | 1 | Approval granted | 2026-02-15 | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion
88 |  | Westmoreland | Grange Hill High | 118947900 |  |  | PHASE 1 - Electrical repairs. PHASE 2 - Cottage & Greenhouse rehabilitation | 1 | NET | Build Management Technology & Logistic | 1 |  |  |  | Contractor to be given site possession | Review to be done for newly submitted bid Designs received, reviewed and is to be revised in accordance to issues highlighted during the drawing review
89 |  | Westmoreland | Grange Hill Primary |  | 73929240 |  | Repairs to roof and members, hardcourt, and electrical system to all 9 classroom blocks as per Standard Building Code | 1 | TSU | Build Management Technology & Logistic | 2 | Approval granted |  | 2026-09-19 | 61% -79% ; work in progress | Practical Completion by September 11, 2026
90 |  | Westmoreland | Little Bay Primary and Infant |  | 44557650 |  | Repairs to roof, fencing and electrical system to main classroom block as per Standard Building Code | 1 | TSU | K & R and Associates | 1 | Approval granted | 2026-03-26 | 2026-09-19 | 61% -79% ; work in progress | Work in progress
91 |  | Westmoreland | Little London Primary and Infant | 30000000 |  |  | Waterproofing of slab roof, other roof repairs, replacement of damaged safety rails to main classroom block as per Standard Building Code | 1 | TSU | HT Roofing & Construction Limited | 3 | 2026-03-24 |  |  | 41% - 50% ; work in progress | Work in progress.
92 |  | Westmoreland | Moreland Hill Primary and Infant | 35000000 |  |  | Repairs to roof, fencing and electrical system to main classroom block as per Standard Building Code | 1 | TSU |  |  | Approval Granted |  |  | Contractor to be given site possession | 1. Site Assessment Completed 2.Pre-Tender Estimate Completed 3.Contractor Priced BQ's being reviewed for submission by September 25, 2026
93 |  | Westmoreland | Mount Grace Primary and Junior High | 25000000 |  |  | Roof repairs, building repairs, water supply, electrical - Grades 1,4 & 6. Erosion near playfield | 1 | NET | K and R and Associates |  |  |  |  | 20% & Below ; work in progress | Stripping of roofs has commenced
94 |  | Westmoreland | Peggy Barry Primary and Infant |  | 32571902 |  | Major roof replacement and repairs on building; waterproofing of roof and associated masonry repairs; repairs to electrical system – supply and lighting; major repairs to kitchen area,; window and door replacement; repairs to sanitary building and associated painting to main classroom block as per Standard Building Code | 1 | TSU | Cambridge Trading Limited | 2 | Approval Granted | 2026-04-02 | 2026-09-04 | 80% - 94% ; work in progress | Windows to be fabricated and installed
95 |  | Westmoreland | Revival Primary |  |  |  | Repairs to roof of administrative block and staffroom and repairs to windows of grade 3 block as per Standard Building Code | 1 | TSU | Build Management |  | 2026-03-25 |  |  | Contractor to be given site possession | 1. Site assessment Completed 2.Pre-Tender Estimate Completed 3.Contractor Priced BQ's being reviewed for submission by September 25, 2026
96 |  | Westmoreland | Sheffield Primary |  | 23784000 | 14585000 | Repairs to canteen, waterproofing and electrical system to main classroom block as per Standard Building Code | 1 | TSU | J Niel Construction Limited | 3 | Approval Granted | 2/206/2026 | 2026-09-04 | Work Completed | Practical Completion. Final Account to be completed
97 |  | Westmoreland | St. Paul's Primary |  | 23887500 |  | Repairs to sanitation, roof and electrical system to main classroom block as per Standard Building Code | 1 | TSU | J Niel Construction Limited | 3 | Approval granted | 2/206/2026 | 2026-09-04 | Work Completed | Practical Completion. Final Account to be completed
98 |  | Westmoreland | Townhead Primary and Infant |  | 69016000 |  | Repairs to roof, fence and electrical system to main classroom block as per Standard Building Code | 1 | TSU | Yardworks Construction Company Limited | 1 |  |  | 2026-10-02 | 20% & Below ; work in progress | Work in progress.....slow
99 |  | Westmoreland | Culloden Infant | 100000000 |  |  | Rehabilitation of Classroom 7 and external works, such as upgrading the water supply and installing perimeter fencing. | 1 | DONOR | Accu-rate Builders Incorporated |  |  |  |  | Work Completed | Completed by Sandals Foundation
|  |  |  | 71810693 | 89657269 |  | Construction of two classrooms and sanitary facilities for students and staff and fencing | 1 | NET | Howard Construction |  | Approval granted |  |  | 20% & Below ; work in progress | Works commenced July 27, 2026 Overall Project Percentage: 20% Progress: 1. Clearing of site (Removal of items in the immediate building area and removal of topsoil) 2. Installation of Hoarding and supply of storage container 3. Setting out of building 4. Decommissioning of absorption pit and sanitation 5. Earthworks (excavation of building foundation) 6. Steel & Formwork – (Cutting and bending of steelwork) Making up of formwork. Upcoming Events: 1. Blinding of Foundation 2. Erecting of steel reinforcement 3. Casting of Foundation 4. Masonry works – Laying of blocks 5.Installation of form Work to columns and stiffeners Issues: 1. Delays were experienced with the removal of salvable items by the school in the immediate area of the building 2. Torrential rain in the afternoons limiting working for a full 8 hr day 3. Difficulty in obtaining skilled and unskilled labour in and around the immediate project area or parish. Resolution: 1. Start the workday earlier to achieve a full eight-hour workday. 2. Importing skilled and unskilled workers form other parishes
100 |  | Westmoreland | Kings Primary and Infant | 72068665 |  |  | Construction of Infant Dept. Renovations to primary school buildings and electrical. | 1 | DONOR | NET and Sandals Foundation 50/50 funding |  |  |  |  | 80% - 94% ; work in progress | Donor Initiative- Approximately 90% of primary and 50% of infant block completed.
[7 empty] | Construction of Kitchen and canteen, 4 classrooms and sanitary facilities, along with external works to include fencing, retaining wall and driveway | 1 | NET | Howard Construction |  |  |  |  | 20% & Below ; work in progress | Works commenced July 27, 2026 Overall Project Percentage: 15% Progress: 1. Demolition and clearing of site (Demolition of existing classroom block and tuckshop and carting away of debris) 2. Installation of Hoarding and supply of storage container 3. Setting out of building (2 Classroom Block) (Tuckshop) (2 Classroom Block & Bathroom) 4. Demolition of Fencing and 5. Earthworks (Cut and Fill excavation, Excavation of building foundation) 2 classroom blocks at top, 2 classroom blocks at bottom. 6. Steel & Form Work – (Cutting and bending of steel work) Making up of form work. Upcoming Events: 1. Blinding of Foundation 2. Erecting of steel reinforcement 3. Casting of Foundation 4. Masonry works – Laying of blocks 5.Installation of formwork to columns and stiffeners Issues: 1. Difficulty in obtaining skilled and unskilled labour in and around the immediate project area or parish. 2. Torrential rain in the afternoons limiting working for a full 8 hr day 3. Difficulty in finding reasonable and adequate housing for workers Resolution: 1. Start the workday earlier to achieve a full eight-hour workday. 2. Importing skilled and unskilled workers from other parishes 3. Employ additional Labour and equipment to offset works
101 |  | Westmoreland | Chantilly Infant |  |  |  | Waterproofing of slab roof, replacement of framed roof and roof members, repairs to sanitation/ toilets, repairs to general damaged areas- doors, windows, painting, repairs to the damaged electric system complete with external lighting, etc. Construction of security fencing enclosure to secure school buildings and infants while outdoors, repair to play area- equipment etc. | 1 | NET | [5 empty] | Contractor to be given site possession | NO WORK TO BE DONE- TO BE CONSOLIDATED
102 |  | Westmoreland | Bethel Town Primary | 80000000 | 457840000 |  | Re-roofing of Main Block, Construction of classroom block, kitchen canteen and staff facilities along with boundary fence Construction of an infant department | 1 | NET | Chins Construction |  | Approval granted | 2026-08-28 | 2027-03-29 | 20% & Below ; work in progress | Project Percentage Completion: 10% Proposed Project Completion Date: March 2027 Project Status: Demolition of derelict classroom, cottage, and damaged school buildings Three (3) temporary timber classrooms constructed Issues/Challenges:/Challenges: Delay in getting designs for new construction from the contractor
103 |  | Westmoreland | Darliston Primary |  | 126772850 | 21176412.5 | To construct a concrete roof slab on both school buildings with waterproofing. To construct new bathroom facilities and to construct perimeter fence. | 1 | NET | D.R. Foote Construction Co. Ltd | 1 | Approval granted | 2025-12-12 | 2026-06-10 | 21% - 40% ; work in progress | Project Percentage Completion: 35% Proposed Project Completion Date: December 31, 2026 (EOT Approval granted) Project Status: Tuckshop – 45% Principal Office Block – 45% Classroom Block – 60% Canteen – 45% Rest Room – 95% Fencing – 30% Issues:/Challenges: ● Payment delays ● Works are progressing slowly. ● Repair works may not be completed in time for next school year.
104 |  | Westmoreland | Little London High |  |  |  | Waterproofing of roof, major repairs to holding area, roof repairs and replacement | 1 | DONOR | Sagicor |  | 2026-01-12 |  |  | 80% - 94% ; work in progress
105 |  | Westmoreland | Maud McLeod High |  | 193727300 | 30405805 | Replacement of the roof frame with a similar using improved anchorage to the roof frame and restoration of the waterproof membrane where damaged, as indicated in the assessment report. | 1 | NET | D.R. Foote Construction Co. Ltd | 1 | Approval granted | 2026-02-13 | 2026-08-14 | 61% -79% ; work in progress | Project Percentage Completion: 70% Proposed Project Completion Date: October 31, 2026 (EOT Granted) Project Status: Sixth Form Block – 70% Ancillary Area – 80% Tuck-shop – 70% Agriculture Area – 50% Principal Cottage – 80% Teachers Cottage – 20% PE Department – 10% Auto mechanic – 90% Admin Block – 0% Issues:/Challenges: Payment delays. ● Construction works are progressing slowly. ● Repair works may not be completed in time for next school year.
106 |  | Westmoreland | Petersfield Primary and Infant |  | 263375246.41 | 26375246.41 | Total re-roofing and supplementary structural reinforcement needed, electrical upgrades and general repair works. Rebuild of Block E | 1 | NET | Archistrust | 1 | Approval granted | 2026-07-30 | 2027-01-31 | 95% - 99% ; practical completion | Works commenced, May 5, 2025 Overall Project Percentage: 98% Designs and BQ for the rebuild element completed and is to be submitted to the Municipal Corporation. Progress: 1 Block D ceiling works are approximately 100% complete. Block B ceiling works are approximately 100% complete. Block C ceiling works are approximately 100% complete. 2 The installation of zinc roofing sheets on Block B, C, and D has been completed. 3 Zinc roofing installation on Block A is 100% complete. 4 Partition installation has been completed. Upcoming Events: 1. Four doors remain outstanding for installation. 2. Minor adjustments to toilets remain outstanding. 3. Fascia capping to be installed. At a 60% completion. Issues: 1. N/A Resolution: 1. N/A
107 |  | Westmoreland | Content Primary & Infant School |  | 81165100 | 25814660 | To repair damaged roof sections for the principals cottage. To repair damaged roof section for the primary school building. To repair damaged administration block. To repair damaged bathroom block. The re-construction of the infant school building. | 1 | NET | Chins Construction |  | Approval granted | 2026-05-06 | 2026-11-05 | 21% - 40% ; work in progress | Project Percentage Completion: 25% Proposed Project Completion Date: December 31, 2026 Project Status: Principal Cottage – 55% Classroom Block – 55% Admin Block – 10% Rest Room – 0% Infant Block – 0% Issues:/Challenges: ● Payment delays ● Works are progressing slowly. ● Repair works may not be completed in time for next school year.
108 |  | Westmoreland | Retrieve Primary | 35000000 |  |  | Repairs to roof, fence and electrical system and rebuild toilet building | 1 | NET | Pavecon | 1 |  |  |  | Contractor to be given site possession | Bids received July 14, 2026 and is being reviewed
109 |  | Westmoreland | Seaford Town Primary and Infant |  | 334014000 |  | Demolition of the existing derelict structure. Renovation and reroofing of the existing Administration and Kitchen Block. Construction of new facilities comprising: Six (6) classrooms; A Resource Room; and A Wellness Facility. | 1 | NET | Pavecon | 1 | Approval Granted | 2026-07-29 | 2027-01-28 | 20% & Below ; work in progress | Project Percentage Completion: 0 Proposed Project Completion Date: Project Status: "Designs and BQ received - Submission to the Municipal Corporation in progress. Foundation work has commenced. Designs accepted to be circulated with stakeholders BQ submitted June 8, 2026 - to finalise the review of BQ, recommendation for LOA submitted to the Procurement Unit, A contract to be drafted to facilitate the execution of works" Issues:/Challenges: Temporary facility to be reinforced, enclosed and fitted with electrical, lighting, and whiteboards in existing facility
110 |  | Westmoreland | St. John's Infant |  | 282066650 |  | Repairs to electrical supply, water storage, roof and roof members and windows and doors replacement | 1 | NET | Pavecon | 1 | approval granted | 2026-07-29 | 2027-01-01 | Work to Commence | Project Percentage Completion: 0% Proposed Project Completion Date: January 2027 Project Status: "Design for retaining wall to be submitted September 17, 2026 Foundation set to be poured"
111 |  | Westmoreland | St. Leonard's Primary | 25000000 |  |  | Structural repairs to the existing classroom block and conversion to a reinforced concrete roof slab Construction of a new kitchen and canteen, Renovation of sanitary facility | 1 | NET | Pavecon | 1 |  |  |  | 20% & Below ; work in progress | Slab system is currently being reinforced to receive concrete. Temporary facilities are being constructed to facilitate opening of school
112 |  | Westmoreland | Ashton Primary |  | 55496038 |  | Repairs to roof, electrical system, cupboards, windows and doors and floor finish to main classroom block as per Standard Building Code | 1 | TSU | RSJ Construction Company Limited | 2 | Approval granted | 2026-02-19 | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion. Final account to be completed
113 |  | Westmoreland | Beaufort Primary |  | 23956629 |  | Repairs to roof, roof members, windows and doors, water storage, fencing, cupboards and electrical system to main classroom block as per Standard Building Code | 1 | TSU | J Niel Construction Limited | 3 | Approval granted |  | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion
[7 empty] | Installation of water harvesting & sanitation, water storage and pumps | 1 | DONOR | UNICEF |  |  |  |  | Contractor to be given site possession
114 |  | Westmoreland | Belmont Academy |  | 74693553 |  | Waterproofing of roof slab, Roof repairs, electrical repairs, doors, windows, fencing and cottage repairs to main classroom block as per Standard Building Code | 1 | TSU | Maxwell Construction Company Limited | 2 | Approval granted | 2025-12-29 | 2026-09-11 | 95% - 99% ; practical completion | Practical completion. Final account to be completed
115 |  | Westmoreland | Carmel Primary and Infant |  | 30186264 |  | Repairs to roof, windows and demonstration board, chain-link fence, electrical system, sanitation and access roadway to main classroom block as per Standard Building Code | 1 | TSU | Maxwell Construction Company Limited | 2 | Approval granted | 2025-12-29 | 2026-09-04 | 95% - 99% ; practical completion | Practical completion. Final account to be completed
116 |  | Westmoreland | Dundee Primary and Infant |  | 96358560 |  | Repairs to roof and electrical system to main classroom block as per Standard Building Code | 1 | TSU | Geecho Consultants & Construction | 2 | 2026-03-20 |  |  | 41% - 50% ; work in progress | Work in progress.
117 |  | Westmoreland | Enfield Primary and Infant |  | 59749840 |  | Repairs to roof and electrical system to main classroom block as per Standard Building Code | 1 | TSU | RSJ Construction Company Limited | 2 | 2026-03-20 |  | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion by September 11, 2026
118 |  | Westmoreland | Holly Hill Primary and Infant |  | 58432280 |  | Repairs to roof and members, hardcourt, and electrical system to main classroom block as per Standard Building Code | 1 | TSU | D.R. Foote Construction Company Limited | 1 | Approval Granted | 2026-02-20 | 2026-10-30 | 80% - 94% ; work in progress | Roof and ceiling completed. Electrical underway, windows by next Sept 25, 2026. Extension in effect
119 |  | Westmoreland | Kentucky Primary and Infant |  | 72100048 |  | Repairs to roof and roof members, electrical system, cottage, fencing and water supply to main classroom block as per Standard Building Code | 1 | TSU | Geecho Construction | 1 | Approval granted |  | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion
120 |  | Westmoreland | Kew Park Primary and Infant | 20000000 |  |  | Repairs to roof and members, hardcourt, and electrical system to main classroom block as per Standard Building Code | 1 | TSU | THLC COMPANY LIMITED | 2 |  |  |  | 20% & Below ; work in progress | Work in progress.
121 |  | Westmoreland | Mearnsville Primary and Infant | 8000000 | 187832973.33 |  | Repairs to roof, electrical system and water storage | 1 | NET | Cenitech | 1 |  |  |  | 20% & Below ; work in progress | The installation of new roof being executed
122 |  | Westmoreland | Mount Hermon Primary and Infant |  | 84399500 |  | Repairs to roof, fencing, electrical and water supply to main classroom block as per Standard Building Code | 1 | TSU | Yardworks Construction Company Limited | 1 | Approval Granted | 2026-02-19 | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion
123 |  | Westmoreland | New Hope Primary |  | 60498970 |  | Repairs to roof, associated electrical repairs and sanitation to main classroom block as per Standard Building Code | 1 | TSU | Maxwell Construction Limited Company | 2 | Approval Granted |  | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion. Final account to be completed
124 |  | Westmoreland | New Roads Primary |  | 23988400 |  | Waterproofing to roof, roof repairs and electrical system to main classroom block as per Standard Building Code | 1 | TSU | Marken Construction Company Limited | 3 | Approval Granted | 2026-03-16 | 2026-09-11 | 80% - 94% ; work in progress | Work in progress.
125 |  | Westmoreland | New Works Primary and Infant |  | 12594305 |  | Major repairs to roof system, windows and doors, sanitation and electrical to main classroom block as per Standard Building Code | 1 | TSU | Maxwell Construction Limited | 2 | 2026-03-24 |  | 2026-09-18 | 80% - 94% ; work in progress | Major roof repairs will be completed by September. Other works to be done during September
126 |  | Westmoreland | Salem Primary |  | 67671934 |  | Repairs to water storage and windows and doors and access roadway to main classroom block as per Standard Building Code | 1 | TSU | RSJ Construction Company Limited | 2 | Approval granted | 2026-02-25 | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion. Final account to be completed
127 |  | Westmoreland | Savanna-La-Mar Inclusive Academy | 10000000 |  |  | Roof repair and fencing | 1 | DONOR | Rock House Foundation |  | 2026-01-06 |  |  | Work Completed | Rock House Foundation
128 |  | Westmoreland | Submission has been made to the Municipal Corporation for the rebuild of the 6 classrooms facilities (bathrooms, administration facilities). Site preparations are underway with detailed BQ to be submitted by Friday September 18, 2026 | 60000000 |  |  | Construction of a new primary school to include 6 classroom, multipurpose room , computer lab, staffroom, wellness centre, kitchen and canteen and sanitary facilities | 1 | NET | Quality Plus Contracting | 1 |  |  |  | Work to Commence | Submission has been made to the Municipal Corporation for the rebuild of the 6 classrooms facilities (bathrooms, administration facilities). Site preparations are underway with detailed BQ to be submitted by Friday September 11, 2026
129 |  | Westmoreland | Frome Technical High |  | 87395450 |  | Roof replacement, windows and doors, Gutters, Fencing, and electrical works Repairs to the building that houses farm animals: pigs, goats, | 1 | NET | Build Management Technology & Logistic | 2 | Approval granted | 2026-01-12 | 2026-07-11 | 20% & Below ; work in progress | Project Percentage Completion: 5% Proposed Project Completion Date: December 31, 2026 Project Status: Stripping of damaged roofing from piggery Issues:/Challenges: Contractor delay in executing the works. Contractor's limited cash flow is impacting the progress of the works to be undertaken
130 |  | Westmoreland | Godfrey Stewart High |  | 556670794 |  | Construction of seven classrooms, one cosmetology lab, demolition of derelict buildings, Waterproofing of the roofs, window and door replacement, fence repairs, installation of 5 temporary facilities | 1 | NET | S&G Construction | 1 | Approval granted | 2026-08-25 | 2027-02-26 | 21% - 40% ; work in progress | Overall Project Percentage: 36% Progress: 1. Continued framing to roof on Teachers’ Cottage – 90% 2. Continued works on Boundary wall 3. Set out of new classroom block 4. Demolition of Building 5. Cleaning of Classrooms Block A 6. Demolition of bases to accommodate new classroom block Upcoming Events: 1. Partition of Block B classroom 2. Painting of ceilings and reno areas on Block A 3. Completion of boundary wall. 4. Continued fabrication of roof to teachers’ cottage. 5. Continued installation of roofing membrane. 6. Demolition of PE Room 7. Setting out for new Prep Area 8. Roof work for Auditorium 9. Cladding of Gym 10. General Electrical Repairs Issues: 1. Equipment in gym needs to be relocated. 2. School is in full session and as such interior works are paused. 3. Lead time is long for windows Resolution: 1. Work will be done on weekend 2. Hoarding has been installed to separate school population from general work areas.
131 |  | Westmoreland | Llandilo School of Special Education (Campus 1 -Westmoreland) |  | 136094491 | 39245564.59 | Roof, gutters, electrical repairs | 1 | NET | Build rite |  | Approval granted | 2026-05-27 | 2026-11-28 | 41% - 50% ; work in progress | Overall Project Percentage: 50% Progress: 1. The Information Technology Building has now been completed and is fully operational. The new timber roof and roof covering have been completed, together with the electrical installation, internal wall and ceiling painting, sarking painting and associated finishing works. 2. Additional external painting works to the Information Technology Building were also completed to address the condition of the existing external walls. These works were undertaken to ensure that the facility was presented in a complete and serviceable condition, notwithstanding that the external painting was outside the original Bill of Quantities. 3. The successful completion of the Information Technology Building facilitated the relocation of staff from the Main Block, thereby creating the required access to advance the major structural rehabilitation works to the Main Block. 4. The damaged existing timber roof structure over the Main Block has been completely removed, allowing the project team to proceed with the preparation of the building for the proposed reinforced concrete roof slab. 5. Formwork and shoring works for the Main Block belt beam and roof slab have progressed to approximately 90% completion. 6. Reinforcement steel installation is currently in progress at 90 % and is being coordinated with the remaining formwork and shoring activities in preparation for the casting of the reinforced concrete belt beam and roof slab. 7. The current construction effort is primarily concentrated on the Main Block structural works, with the project team targeting completion of the remaining formwork and reinforcement installation to facilitate concrete casting by the end of the upcoming work period. Upcoming Events: 1. Complete the remaining formwork and steel reinforcement to the main block 2. Conduct final inspections and preparation of the structural works prior to concrete placement. 3. Cast the reinforced concrete belt beam and roof slab. 4. Continue structural rehabilitation works to position the Main Block for phased occupation prior to the reopening of school. Issues: 1. Frequent periods of rainfall continue to affect structural concrete works and overall construction productivity. 2. The Main Block rehabilitation involves significant structural works that require careful sequencing to maintain quality and ensure compliance with engineering requirements. 3. The compressed construction window associated with the school recess places additional pressure on the project team to advance the Main Block structural works before the commencement of the new school term. 4. Earlier delays associated with execution of the contract and receipt of mobilization funds affected the initial project programme; however, the project has since recovered significant progress Resolution: 1. Completion of the Information Technology Building enabled the successful relocation of staff, providing unrestricted access to the Main Block and significantly improving construction efficiency. 2. The summer recess is being fully utilized to expedite demolition, formwork, reinforcement installation and roof slab preparation activities. 3. Maintained continuous coordination with the school administration and Ministry representatives to facilitate phased implementation of the works. 4. The project team is targeting completion of the slab preparation works and concrete casting at the earliest practical opportunity, subject to completion of all required structural preparations and suitable weather conditions.
132 |  | Westmoreland | Manning's High |  | 638180231.67 | 266023061.93 | Major roof repairs to 12 facilities, auditorium Waterproofing to five blocks Structural works (conversion to concrete slabs) to six blocks - Mumby, Prescott, Chemistry, Biology, Gen Science and bathrooms Electrical upgrade and other general renovation | 1 | NET | C&D Construction | 1 | Approval granted | 2025-12-08 | 2026-09-19 | 80% - 94% ; work in progress | Works commenced December 17, 2025 Overall Project Percentage: 82% Progress: 1. Technical Block- Installation of Ceiling Bed 2. Staff Room- Installation of Ceiling Frame and Sheetrock 3. Clean Up- Ongoing Site Clean-up of Debris (All Over the School Compound) 4. D-Block- Electrical Works being done (There were Electrical Shortages on the entire Block) 5. Canteen- Final Painting Works being done 6. Mumby- Block Installation of Metal Frames for Support 7. Temporary Classrooms- Completed, installation of fans to follow Upcoming Events: 1. Final Touches to Outstanding Structures that should be completed for the week of September 14. 2. Working towards the completion of Mumby and Prescott Block. Issues: 1. Rainfall – 10 hours lost Resolution: 1. N/A
133 |  | Westmoreland | Petersfield High |  | 263752464.14 |  | Re-roofing of school facilities, membrane application electrical upgrades and general repair works | 1 | NET | M&M Construction | 1 | Approval granted | 2026-05-27 | 2026-11-26 | 41% - 50% ; work in progress | Works commenced, April 1, 2025 Overall Project Percentage: 50% Progress: 1. Timber framing of agriculture building 2. Window installation 3. Chain-link fencing Upcoming Events: 1. Roof sheeting 2. Painting 3. Electrical upgrades Issues: 1. N/A Resolution: 1. N/A
134 |  | Westmoreland | Petersville Primary | 75000000 | 144337312.54 |  | Repairs to roof, electrical system upgrades, perimeter fencing and general repair works | 1 | NET | Marshall Construction Company Limited | 1 | Approval granted | 2026-08-25 | 2027-02-26 | 20% & Below ; work in progress | Works commenced, May 5, 2025 Overall Project Percentage: 5% Progress: 1. Completion of Demolition of roof, ceilings, doors, kitchen, tiles torn down partitions, etc 2. Removal of roof purlins Upcoming Events: 1. Installation of Roofing 2. Installation of ceiling 3. Installation of wall partitions 4. Installation of fencing Issues: 1 Payment of mobilization Resolution: 1. N/A
135 |  | Westmoreland | Sir Clifford Campbell Primary |  | 99651245 |  | Major reroofing - conversion to reinforced concrete slab - to two-storey block, bathrooms and classroom, Repairs to roof and metal frame, Installation of windows,, doors, and partitions in classrooms, Electrical upgrade and general repairs | 1 | NET | Pavecon | 1 |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 10% Proposed Project Completion Date: Project Status: "Concrete slab for main block has been cast in place. Concrete slab for bathroom to be cast during week September 14-18, 2026" Issues:/Challenges: Contractor awaiting contract to generate payment to undertake the works
136 |  | Westmoreland | Unity Primary and Infant |  | 998610246.2 |  | Construction of 8 new classroom block and sanitary facility. Reconstruction of the Auditorium and 10 classroom. General renovation to existing facilities | 1 | NET | Pavecon | 1 | Approval granted | 2026-08-25 | 2027-02-27 | 21% - 40% ; work in progress | Overall Project Percentage: 31% Progress: 1. Replace damaged roof sheeting on Block 5 & Block 6 2. Ceiling replacement commenced for Block 5 & Block 6 3. Completion of 6 ½ Temp Structures (13 classes); ready for classes. 4. Erect chain link fence (136’-0 x 5’-0) 5. Cart-away of all debris off site from the initial storage area in the parking lot. 6. Column and beams; rebar and carpentry continuing for Block 3 Upcoming Events: 1. Cleaning up Bathroom #1 to facilitate usage. 2. Block 1 – Decking of the entire block. 3. Block 3 – Pour concrete in beams and columns 4. Bathroom #2 – Demolition of roof 5. Pouring Concrete Stanchion 5. Demolition of Auditorium Issues: 1. The designated field area for the temporary structures had soft and unsuitable existing ground conditions, which did not provide an adequate bearing surface. 2. The materials ordered for the temp structures as per design was inadequate to provide a stable structure. 3. Additional bathroom facilities are being incorporated into existing Bathroom Nos. 1 and 2. However, no drawings or as-built documentation are available for the existing sewage system, and the existing pipe routing, sizes and connection points are therefore not documented. Resolution: 1. Timber plinths were constructed and installed to provide a stable, level and elevated base for the temporary structures due to the soft existing ground conditions. 2. Additional materials for the temp structures had to be ordered to facilitate the completed works within the short time span. 3. The existing sewage system will need to be investigated and verified on site, following which a new sewage layout/design is to be prepared to accommodate the additional bathroom facilities and establish the required connections to the existing system.
137 |  | Westmoreland | Williamsfield Primary and Infant | 30000000 |  |  | Roof repairs. General renovation of facilities including doors at the main office and Guidance Counsellor's Office, water tanks. Infant Department - roof repairs. Re-construction of Security Post. | 1 | NET | Pavecon | 1 | Approval granted | 2026-08-26 | 2027-02-27 | 20% & Below ; work in progress | Roof repairs to infant block completed Temporary facilities are currently being installed
138 |  | Westmoreland | Caledonia Primary and Infant |  | 23943429 |  | Major repairs and replacement to roof system - sheeting, frame, capping, gutters, associated painting, partition replacement, electrical repairs, masonry repairs, repairs to water storage system, repairs to security fencing, repairs to sanitation, replacement of defective doors, floor repairs to main classroom block as per Standard Building Code | 1 | TSU | Marken Construction Company Limited | 3 | Approval granted | 2026-03-21 | 2026-09-04 | 95% - 99% ; practical completion | Practical Completion
139 |  | Westmoreland | Cornwall Mountain Primary and Infant |  | 23975100 |  | Repairs to roof and electrical system to main classroom block as per Standard Building Code | 1 | TSU | HT Roofing & Construction Limited | 3 | Approval granted | 2026-02-06 | 2026-09-04 | Work Completed | Final Account to be completed
140 |  | Westmoreland | Ferris Primary |  | 23800000 |  | Roof replacement and repairs, fencing repairs, other repairs to building to main classroom block as per Standard Building Code | 1 | TSU | HT Roofing & Construction Limited | 3 | Approval granted | 2026-02-19 | 2026-05-28 | Work Completed | Final Account to be completed
141 |  | Westmoreland | George's Plain Primary and Infant |  | 79174750 |  | Electrical supply and distribution, roof repairs, structural repairs, fencing, windows to main classroom block as per Standard Building Code | 1 | TSU | Marshall Construction Company Limited | 1 | Approval granted | 2026-02-15 | 2026-09-04 | 80% - 94% ; work in progress | Work in progress.
142 |  | Westmoreland | Haddo Primary and Infant |  | 42777000 | 16944800 | Repairs to roof and members, hardcourt, and electrical system to main classroom block as per Standard Building Code | 1 | TSU | D.R. Foote Construction Company Limited | 1 | Approval Granted | 2026-02-27 | 2026-09-26 | 80% - 94% ; work in progress | Work in progress.
143 |  | Westmoreland | Porter's Mountain Primary |  | 23759530 |  | Replacement of roof and electrical repairs to main classroom block as per Standard Building Code | 1 | TSU | J Niel Construction Limited | 2 | Approval granted | 2026-02-23 | 2026-09-04 | 95% - 99% ; practical completion | Practical completion attained
144 |  | Westmoreland | Savanna-La-Mar Infant |  | 33406200 |  | Repairs to roof, ceiling, electrical, fencing to main classroom block as per Standard Building Code | 1 | TSU | Yardworks Construction Company Limited | 2 | Approval granted |  | 2026-09-26 | 20% & Below ; work in progress | Work in progress....slow
145 |  | Westmoreland | Savanna-La-Mar Primary |  | 93971280 |  | Repairs to roof, ceiling, associated electrical system and fencing of main classroom building as per Standard Building Code | 1 | TSU | Geecho Consultants & Construction | 1 | Approval granted |  | 2026-09-11 | 95% - 99% ; practical completion | Practical Completion. Addressing defects
146 |  | St. James | Llandilo School of Special Education (Campus 3 - St. James) | 25000000 |  |  | Minor roof repairs, ceiling, flood damage to partition wall (moulds), electrical repairs and inspection/reconnection, collapsed security/safety wall near canal to main classroom building as per Standard Building Code | 1 | NET | Build rite |  |  |  |  | Contractor to be given site possession
147 |  | Hanover | Llandilo School of Special Education (Campus 2 - Hanover) | 20000000 |  |  | Roof, electrical, gutters, fencing to main classroom building as per Standard Building Code | 1 | NET | Build rite |  |  |  |  | Contractor to be given site possession
148 |  | Hanover | Knockalva Polytechnic College | 771360604.55 |  |  | General Repairs to Farm managers house, Chemistry, Physics and Biology Labs Computer Lab, Library and Resource Centre, Gazebo, Kitchen, Administration, Girls and Boys Dormitory Health Centre, Engineering Dept., Argo Processing Building, Cottage 1-4, Principals Cottage, Vice Principal Cottage, Guest Cottage, Farming Units, Solar System and Electrical | 1 | NET | Brothers Concepts | 1 |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 2% Kitchen - 25% Slab Cast, Tiles Hacked up Cottage Demo - 80% Principal and V. Principal cottage demolition - 80% Boys Dormitory Demo - 80% Scaffolding to boys dorm erected. Proposed Project Completion Date: January 31, 2027 Works done this week: Demolition of tiles and windows/door jambs to the Principals and vice principals cottages Comments/Issues:/Challenges: An additional 4 workmen have been added to the team, so currently there are 9 workmen onsite.
149 |  | St. James | Montego Bay Community College |  | 388973450.15 |  | Repairs to two campuses in St James and Westmoreland - roof replacement, roof repairs, waterproofing of roof slabs, window repairs as per Standard Building Code | 1 | NET | Brothers Concepts |  | Approval granted | 2026-07-28 | 2027-01-29 | 21% - 40% ; work in progress | Works ongoing
150 |  | St. James | Sam Sharpe Teachers' College | 70000000 |  |  | Replacement and or major repairs to all roofs, ceiling & guttering. Windows, doors, electrical repairs as per Standard Building Code | 1 | NET | [6 empty] | The school is undertaking project.
150 | TOTAL |  |  | 3405791063.66 | 12295010166.81 | 1174161484.65

## REGION 5
POST-HURRICANE ASSESSMENT DATA ― IMPACT OF HURRICANE MELISSA ON SCHOOLS' INFRASTRUCTURE
No of Schools | Region | Parish | Name of School | Preliminary Cost $ | Contract Sum $ | Expenditure to Date $ | Scope of Works | PRIORITY 1. Severely Damaged - may affect school reopening. 2. Moderately Damaged - Significant repairs. School can operate while repairs are done. 3. Minor Damage - school can operate while repairs are done. | Person Responsible (TSU , NET, JSIF , DONOR) | Name of Contractor Assigned | Contractor Grade | Projected Date of Procurement for PS Approval | Contract Start Date | Contract End Date | Status | Remarks
1 | 5 | St. Elizabeth | Middlesex Infant | 17854500 |  |  | 1. Minor roof and ceiling repairs 2. Restoration of fencing throughout school | 1 | NET | Maxwell Construction | 2 |  |  |  | 61% -79% ; work in progress | Project Percentage Completion: 65% Fence repair & replacement - 90% Ceiling and Sarking repair & replacement - 90% Electricals - 50% Minor roof repairs - 70% Repainting damaged walls - 30% Issues:/Challenges: School is opting to delay reopening one week to facilitate internal works and fencing be completed. Addition of new floor finish being considered for a particular classroom
2 |  | St. Elizabeth | Accompong Primary and Infant |  |  |  | Repairs to roof of main classroom block as per Standard Building Code | 1 | DONOR | [5 empty] | Work Completed | DONOR EXECUTED REPAIRS-PROJECT COMPLETED
3 |  | St. Elizabeth | Beersheba Primary |  | 89864246.5 | 21416608.17 | Re-roofing works and repairs to ceiling of main classroom block as per Standard Building Code | 1 | NET | Build -Rite | 1 | Approval granted | 2026-08-04 | 2027-03-03 | 51% - 60% ; work in progress | Project Percentage: 55% Progress: 1. Electrical installations (section #1): on-going 80% 2. Ceiling installations to office, library, staffroom & bathroom: 50% 3. Blocking board and collar tie support installation (section #1): 50% 4. Felt and 2 x 4 installation (section #2): 75% Upcoming Events: 1. Continued electrical installations (section#1) 2. Continued ceiling installations to office, library, staffroom & bathroom 3. Continued blocking board and collar tie support installation (section #1) 4. Continued felt and 2 x 4 installations (section #2) 5. Commence electrical installations (section #2) 6. Commence painting works (section #1) Issues: 1. Re-mobilizing of existing workforce 2. Availability of skilled labour 3. Availability of housing accommodations in and around the area 4. Delay in the supply of critical materials due to the increased demand (roof sheeting, cement board, lumber etc…) Resolution: 1. Imported skilled labour force 2. Early commencement and extended working hours 3. Increased outreach to attract skilled labour force
4 |  | St. Elizabeth | Carisbrook Primary and Infant |  | 151980473.54 |  | Re-roofing works to include sarking to roof of main classroom block and re-roofing and ceiling repairs to single storey classroom block as per Standard Building Code | 1 | NET | Build -Rite | 1 | Approval granted | 2026-07-30 | February 29, 2027 | 21% - 40% ; work in progress | Project Percentage: 25% Progress: 1. Demolition of existing damaged timber roof to classroom block #2: complete 100% 2. Installation of belt beam to classroom block #2: complete 100% 3. Roof framing to classroom block #2: ongoing 25% 4. Demolition of existing damaged metal frame roof to main block: ongoing 25% Upcoming Events: 1. Continued framing of roof classroom block #2 2. Sarking of roof classroom block #2 3. Continued demolition of metal frame roof to main block 4. Commence purlin & sheeting installations to roof main block 5. Masonry finishing works to tuck shop and outdoor kitchen Issues: 1. Re-mobilizing of existing workforce 2. Availability of skilled labour 3. Availability of housing accommodations in and around the area 4. Delay in the supply of critical materials due to the increased demand (roof sheeting, cement board, lumber etc…) Resolution: 1. Imported skilled labour force 2. Early commencement and extended working hours 3. Increased outreach to attract skilled labour force
5 |  | St. Elizabeth | Clapham Primary and Infant |  | 46258240 | 46420279.2 | Re-roofing and repair works to include sarking to roof of main classroom block , Bathroom and Infant Department as per Standard Building Code | 1 | TSU | Southern Contracting Company | 1 | Approval granted | 2025-12-29 | 2026-03-10 | Work Completed | Part payment amounting to $20,133,010.00 submitted to Project Accounts for processing
6 |  | St. Elizabeth | Elderslie Primary and Infant |  | 74771850 | 53579938.28 | Repairs to roof of administration block. Roof repairs of Grades 1-3 Block as per Standard Building Code | 1 | NET | Maxwell Construction Limited | 2 | Approval granted | 2026-02-02 | 2026-09-28 | 95% - 99% ; practical completion | Project Percentage Completion: 97% Proposed Project Completion Date: September 28, 2026 Project Status: All Roofs and primary Learning space fixed. 100% Additional works on the school compound including a wall for safety and Covered Walkway 100% Issues:/Challenges:
7 |  | St. Elizabeth | Ginger Hill Primary |  | 124632320 | 47488192.7 | Repairs to roof of classroom block and Administrative Block as per Standard Building Code | 1 | NET | Cenitech | 1 | Approval granted | 2026-06-11 | 2026-12-10 | 61% -79% ; work in progress | Project Percentage Completion: 67% Replacement of timber roofs - 100% Replacement of roof slab - 70% Renovation to bathroom - 80% Renovation to Canteen - 50% Proposed Project Completion Date: September 18 2026 Issues:/Challenges: Teaching spaces are in operation
8 |  | St. Elizabeth | Glen Stuart Primary, Infant and Special Education |  | 134300100 |  | Re-roofing and repairs to two (2) storey administration block (Block A), Block B and Re-roofing and repairs to Infant Department as per Standard Building Code. Installation of water harvesting & sanitation, water storage and water pumps | 1 | NET | FSC | 2 | Approval granted | 2026-06-11 | 2026-12-10 | 80% - 94% ; work in progress | Works commenced, February 9, 2026 Overall Project Percentage: 92% Progress: 1 Installation of windows for all of Grade 6 classrooms 2 Installation of windows for Infant Department 3 Completed All roofing activities for primary and Infant Department 4 Completed all painting activities for primary and Infant department Upcoming Events: 1 Tiling of Canteen 2 Tiling of Unfinished Section 3 Installation of Top Windows for Grade 4 classrooms and Grade 5 classroom Issues: 1 Shortage of material by window manufacturers Resolution: 1. N/A
9 |  | St. Elizabeth | Holland Primary |  | 23982240 | 21885850 | Re-roofing & renovation works to main classroom block and student bathroom block as per Standard Building Code | 1 | TSU | J. Neil Construction | 3 | Approval granted | 2026-01-26 | 2026-09-04 | 80% - 94% ; work in progress | Part payment made; Completion to works delayed by severe weather.
Phase 2 - Construction of temporary classrooms and Rehabilitation of partial Nog structure
10 |  | St. Elizabeth | Kilmarnock Primary and Infant | 104935551.1 |  |  | To repair damaged roof sections on block A - C. To apply waterproofing to administration block. The construction of a concrete base for water tanks. The construction of a perimeter fence as per Standard Building Code | 1 | NET | Roger Land Development | 1 |  |  |  | Contractor to be given site possession | Project Percentage Completion: 0% Proposed Project Completion Date: January 20, 2027 Project Status: Letter of commencement issued on July 20, 2026 Issues:/Challenges: Works on starting on time.
11 |  | St. Elizabeth | Lacovia Primary and Infant |  | 35717885 | 14877438.96 | Replacement of Admin Building and Bathroom roofs(previously timber framed) with reinforced concrete slabs as per Standard Building Code | 1 | NET | Howard Construction | 2 | Approval granted | 2026-02-20 | 2026-09-19 | 95% - 99% ; practical completion | Project Percentage Completion: 97% Reroofing of Admin Office - 100% Electrical works for Admin Office - 100% Plumbing works for Admin Office - 100% Floor restoration for Admin Office - 100% Reinstallation of Countertops and cabinets - 100% Reroofing of Student Bathroom - 100% Electrical works for Student Bathroom - 100% Plumbing works for Student Bathroom - 100% Comments/Issues:/Challenges: Taking Over Inspection to be scheduled
12 |  | St. Elizabeth | Merrywood Primary |  | 53216000 |  | Re-roofing and ceiling repairs to Block A as per Standard Building Code | 1 | NET | Chins Construction | 1 |  |  |  | 61% -79% ; work in progress | Project Percentage Completion: 64% Reroofing of Block A - 100% Reroofing of Block B - 100% Reroofing of Cottage - 100% Electrical installation in Cottage - 30% Plumbing installation in Cottage - 0% Wall Finishes for Cottage - 10% Proposed Project Completion Date: Comments/Issues:/Challenges: Contractor has halted works waiting for contract to be able to process first payment. Draft Contract was sent to the contractor on July 31, 2026.
13 |  | St. Elizabeth | Retirement Primary and Infant |  | 26514000 | 12231500 | Phase 1 - Repairs to roof of main classroom block as per Standard Building Code | 1 | TSU | K&R Associates | 2 | Approval granted | 2026-02-02 | 2026-03-31 | Work Completed | Request for Addition Funding for works not measured & Follow-on Contract for internal works.
[5 empty] | 10433800 |  | Phase 2 - Partitioning works and repairs to kitchen as per Standard Building Code | 1 | TSU |  |  | Approval granted |  |  | 20% & Below ; work in progress
14 |  | St. Elizabeth | Springfield Primary | 124640000 |  |  | To repair damaged roofs and ceiling repairs to administrative block, two (2) Classroom Blocks, Industrial Arts Block. To waterproof Block G & F. Repair 5 cottages. Re-construct perimeter fencing as per Standard Building Code | 1 | NET | J&H Construction | 1 | Approval granted | 2026-01-05 | 2026-07-04 | 61% -79% ; work in progress | Project Percentage Completion: 65% Proposed Project Completion Date: January 31, 2027 Project Status: Roofing – 100% Ceiling – 100% ECC Block – 0% Rest Room – 0% Walkway – 0% JPS Re-connection – 0% Issues:/Challenges:
15 |  | St. Elizabeth | Lewisville High |  | 689893620 | 162688499.2 | Re-roofing and ceiling repairs to administrative block, two (2) Classroom Blocks, Industrial Arts Block as per Standard Building Code | 1 | NET | Southern Contracting Company Limited | 1 | Approval granted | 2026-01-22 | 2026-07-22 | 61% -79% ; work in progress | Project Percentage Completion: 65% Proposed Project Completion Date: December 31, 2026 Project Status: Block A – 80% Block B – 80% Block C – 80% Block D – 80% Block E – 90% Block F – 30% Block G – 10% Literacy Cafe – 10% Security Post and Covered Entrance – 95% Teachers Cottage 1 – 70% Teachers Cottage 2 – 70% Teachers Cottage 3 – 70% Teachers Cottage 4 – 70% Principals Cottage – 70% External Works (Link-ways) – 80% External Works (Perimeter Fence) – 60% External Works (Lightning Protection System) – 0% External Works (Signage) – 0% Issues:/Challenges: ●Significant scope creep, most of which has resulted in delays. ●Costing for additional changes. ●Request that all focus be placed on functional areas.
16 |  | St. Elizabeth | Bogue Primary and Infant |  | 51434830 |  | Re-roofing and repairs to ceiling of main classroom block to include fencing repairs as per Standard Building Code | 1 | NET | Cenitech | 1 |  | 2026-05-07 | 2026-11-06 | 41% - 50% ; work in progress | Project Percentage Completion: 50% Proposed Project Completion Date: October 9,2026 Project Status: Works done in the week of the current period: Standing Seam installation 100% Works to be done is next period: Electrical work to continue Painting to continue Challenges/Issues: material acquisition, Certificate #1$24,041,212.70 PAID. Temporry Classroom made available, Classroom space made available for the new school term. Work will continue to be completed by October 9,2026.
17 |  | St. Elizabeth | Burnt Savannah Primary | 40000000 | 185730573 |  | Replacement of roof sheeting and framing across entire school property inclusive of classrooms and offices as per Standard Building Code | 1 | NET | Yardworks | 1 |  | 2026-09-03 | 2027-03-03 | 21% - 40% ; work in progress | Project Percentage Completion: 30% Reroofing of Admin Office - 80% Electrical for Admin Office - 30% Reroofing of Grade 5&6 - 80% Electrical for Grade 5&6 - 30% Reroofing of Grade 4 - 30% Restoration of temporary Grade 4 structure - 0% Electrical for Grade 4 - 1% Reroofing of Grade 1 - 2% Restoration of temporary Grade 1 structure - 0% Electrical for Grade 1 - 1% Proposed Project Completion Date: Comments/Issues:/Challenges:
18 |  | St. Elizabeth | Marie Cole Memorial Primary |  | 15218000 |  | Repairs to roof and electrical system of main classroom block as per Standard Building Code | 1 | TSU | Maxwell Construction Limited | 2 | Approval granted | 2026-01-09 | 2026-03-09 | Work Completed
19 |  | St. Elizabeth | Park Mountain Primary and Infant |  | 159713733.52 | 56534083.86 | Repairs to roof for primary and infant department. Revamp of infant department bathroom as per Standard Building Code | 1 | NET | Proven Construction | 1 |  | 2026-02-24 | 2026-08-24 | 80% - 94% ; work in progress | Works commenced March 9, 2026 Overall Project Percentage: 85% Progress: 1.Park Mountain Infant Department - Internal painting complete 2. Park Mountain Infant Department - Kitchen- Solid surface and sinks to be installed 3. Park Mountain Infant Department - Bathroom- Showerhead to be installed and new plumbing fixtures 4. Park Mountain Block B - Bathroom- Electrical works upgrades completed 4. Park Mountain Block B - Bathroom- Painting of tongue and groove ceilings Upcoming Events: 1. Park Mountain Infant Department - Kitchen- Solid surface and sinks to be installed Issues: N/A
20 |  | St. Elizabeth | Quickstep Primary |  |  |  | Re-roofing and ceiling repairs to Main Classroom Block and Student Bathroom Block as per Standard Building Code | 1 | NET | C&D Construction | 1 |  |  |  | 20% & Below ; work in progress | "Project Percentage Completion: 5% Proposed Project Completion Date: January 2027 Project Status: Demolition and cart away activities commenced Works to be done is next period: Temporary Classroom No. 3 commenced Roof Demo activities to continue. Challenges/Issues: Awaiting Contract. LOA to be issued. Contractor experienced delays in commencing Temp structure. 3 Classrooms should be completed by September 12, 2026
21 |  | St. Elizabeth | Roses Valley Primary and Infant |  | 67455400 |  | Re-roofing and ceiling repairs, wall replacement to Main Classroom Block. Re-roof Block A and B. Re-roof Canteen as per Standard Building Code | 1 | NET | Chins Construction | 1 |  | 2026-02-21 | 2026-08-21 | 51% - 60% ; work in progress | Project Percentage Completion: 57% Classroom A:100% Classroom B and Library: 99% Main Classroom Block: 40% Canteen: 0% Proposed Project End Date: July 28, 2026 Works done in the week of the current period: 1. Main Block: Roof structure in progress 2. Classroom A&B: Resheeting (one sheet and fascia outstanding) and ceiling complete 98% complete Works to be done is next period: 1. Main Block: Resheeting Issues/ Challenges: Material availability
22 |  | St. Elizabeth | Thornton Primary and Infant |  | 74260500 |  | Re-roofing and repairs to ceiling of main classroom block and Administrative Block and Roofing repairs to Infant Department as per Standard Building Code | 1 | NET | Maxwell Construction Limited | 2 |  | 2026-02-17 | 2026-08-16 | Work Completed | Project Percentage Completion: 100% Reroof Infant: 100% Reroof Canteen/Library Block: 100% Reroof Staff Room/Class Block/Guidance: 90% Guttering: 100% Epoxy Floor: 100% Proposed Project Completion Date: August 28, 2026 Issues/Challenge: Contractor Claim outstanding. Variation identified at infant block to be rectified. Awaiting Cost Proposal. Taking Over Site Inspection to be arranged.
23 |  | St. Elizabeth | St. Elizabeth Technical High |  | 310986764 | 194800078.01 | Roof repairs | 1 | NET | Pavecon | 1 | Approval granted | 2025-11-18 | 2026-05-17 | 80% - 94% ; work in progress | PHASE 2 Project Percentage Completion: 80% Proposed Project Completion Date: September 2026 Project Status: Meeting held with Contractor August 27, 2026 to clarify workforce and progress. Justification for assessments required to support the water run-off challenges at the school submitted. Works done in the week of the current period: 1. Male Dorm: Kitchen cupboard 2. Female Dorm: tiling 100% 3. Grade 11 Block: white boards installed 4. Admin block(unfinished building):100% complete 5. Teachers Cottage: 100% 6. Media Building: Tiling ongoing 7. Principal Cottage: bathroom tiling commenced. 8. Industrial Block: electrical installations continue 9. Grade 9: membrane complete 10. Bus Shed: 100% 11. Pavilion: Electrical 100% 12. Playfield: Lights 100% 13. Welding Lab: nil 14. Boundary Wall: weep holes completed Works to be done next period: 1. Male Dorm: gravel on the perimeter as identified 2. Female Dorm: water connection and faucet 4. Principal Cottage: bathroom tiling and cupboard installation, painting, flashing No. 1 5. Industrial Block: electrical installation to be completed. Ceiling installation 6. Media Building: Electrical work to continue (complete September 30, 2026) 7. Chicken Coup- Ridge Board support installed 8. Home Econ/Cosmo- Roof demolition to commence (commence September 30, 2026) 9. Welding Lab: Sheeting, ceiling and electrical to commence and completed 10. Nurse Station: Capping to be installed Issues:/Challenges: Work force and flow . No intermediary doors in partitions at Grade 11 Block. Contractor advised it is requirement by our standards and Fire. Email sent to Contractor re progress
24 |  |  |  |  | 73205890 | 57519048.7 |  | 1 | NET | Southern Contracting |  | Approval granted | 2026-02-02 | August 1, 2026 | Work Completed | Phase 1 Completed
25 |  | St. Elizabeth | Sydney Pagon STEM Academy |  | 654929435.83 | 147689511.72 | Re-roofing and ceiling repairs to Grade 7 Classroom Block, Auditorium, Staff Room Block, Guidance Laboratory, staff flatlets, male and female student dormitories as per Standard Building Code | 1 | NET | Denron Engineering | 1 | Approval granted | 2026-02-26 | 2026-08-25 | 80% - 94% ; work in progress | Project Percentage Completion: 85% Proposed Project End Date: October 2026 Project Status: Works done in the week of the current period: 1. Female Dorm#1: Clean up. Lattice at transom installed 2. Female Dorm #2&#3: Fascia Board, fascia cap, ceiling and door installation commenced 3. Male Dorm#1: Finishes in progress 4. Male Dorm 3&4: Termite Treatment, ceiling work complete , (1of2 Dorm electrical) 5. Teachers Cottages: 90% internal finishes continue 6. Teachers Flat#2. Form work removed, dressing on outside completed, electrical completed 8. Tractor House: 100% 9. B No. 3 : Purlin installation 100% 10. Piggery: 100% 11. Staff Room:90% complete 12. Link Way @ Staff Room No.2: painting to commence 13. Walkway @ Staff Room: rendering in progress 75% 14. Science Block: 100% 16. E-Learning/Computer Lab: Ceiling 100% 17. Grade 7 Block: white board installed 18.Apiary : Belt Beam 100% 19. Layer House: Sheeting complete. 20. Staff Room: cubicles installed, external painting complete 21. Water Tank: block work to continue 22. Admin: Belt bean cast complete 23: Guardhouse: Ceiling 100% 24. Ancillary Room: 100% 25. GOatery: Holes dug to plant posts Works to be done is next period: 1. Female Dorm #2&#3: Painting and doors to commence Female #1- Waterproofing to commence, 2. Male Dorm #1: Window installation to commence (fabrication delays) installation for Aug 18, 2026. Male Dorm 3&4: Doors and painting to commence. Boxed eaves outstanding 3. Teachers Cottage: Ceiling work to continue on 1 No. (Teacher moved out 13Aug) 4.B No. 3: Roof sheeting to commence 5.Layer House: Ventilation requirements to be addressed 6. Science Block: Fascia board installation to continue 7. Horticulture: Ceiling work to be complete 8. Staff Room: minor clean up activities 9. Machine Shop: Ceiling to be complete 10. Apiary-Roof Sheeting to commence 11. Water: block work to continue 12. Admin:Belt Beam poured 13. Goatery: post work to continue Issues/Challenges: Delays in the fabrication of purlins. Certificate #2 $74,397,929.60 PAID work coordination to improve. The school hosts campers and 2 female dorms will be occupied and work ceased temporarily. The large tank that required roofing is now leaking, and discussions with the contractor to rectify issue. Boiler 3, Apiary, Goatery, Admin, Tank complete by October 2026
26 |  | St. Elizabeth | Ballards Valley Primary |  | 24147380 | 21194620 | Re-roofing and renovation of Grade 1 & 6 blocks and student bathroom as per Standard Building Code | 1 | TSU | Southern Contracting Company | 1 | Approval granted | 2025-12-29 | 2026-08-21 | Work Completed | Part payment made; Final payment documents being prepared.
27 |  | St. Elizabeth | Brinkley Primary and Infant |  | 68276510 | 28390739.3 | Replacement of classroom block roof with reinforced concrete slab roofing inclusive of structural modification to columns and beams to support new roof system as per Standard Building Code | 1 | NET | Southern Contracting Company | 1 | Approval granted | 2026-03-24 | 2026-09-23 | 95% - 99% ; practical completion | Project Percentage Completion: 95% Foundation - 100% Columns - 100% Beams - 100% Electrical works - 100% Windows and doors- 100% Ramp & railings - 95% Roof waterproofing - 95% Wall finishes - 100% Floor Finishes(Epoxy) - 100% Proposed Project Completion Date: August 2026 Comments/Issues:/Challenges: Taking Over Inspection to be scheduled
28 |  | St. Elizabeth | Mayfield Primary and Infant |  | 22200000 |  | Roof repair to Grades 4-6 Classroom Block, lifting of membrane to two storey classroom block. Roof repairs to the infant department as per Standard Building Code | 1 | DONOR | [5 empty] | 80% - 94% ; work in progress | Project Percentage Completion: 90% Proposed Project Completion Date: August 2026 (Pending the issue with the Admin Block Project Status: Infant Roof 100% Primary Department Roof 100% Library Roof 100% Admin Roof? Issues:/Challenges: Contractor to remedy cosmetic fixes identified during the visit in July 2026. This include edges of the roof membrane. Whether the roof of the Admin block was within the scope or outside of same, and if its the later will Sagicor include it.
29 |  | St. Elizabeth | Hampton School |  | 163301686 | 81831882.9 | Replacement of roofing and restoration of electrics, fixtures and finishes at Dorms, Admin, Science Labs, Art Room, Home Econ Lab and minor repairs to several areas across the school as per Standard Building Code | 1 | NET | Denron Engineering | 1 | Approval granted | 2025-12-01 | 2026-06-15 | 95% - 99% ; practical completion | Project Percentage Completion: 95% Reroofing of Dorms - 100% Repainting Dorms - 100% Replace doors and windows at Dorms - 100% Reroofing Labs - 100% Installation of Ceiling in Labs - 100% Electrical works in Labs - 100% Replacement of doors at Labs - 100% Construction of linkway cover along Lab corridor - 90% Reroofing of Art Room - 100% Electrical works in Art Room - 100% Finishes in Art Room - 100% Reroofing at Home Econ Lab - 90% Electrical works Home Econ Lab - 100% Renovation of Home Econ Lab - 100% Resheeting at Admin Building - 100% Roof repairs to Laundry room - 100% Ceiling replacement for Laundry room - 80% Minor repairs across school - 80% Proposed Project Completion Date: September 2026 Comments/Issues:/Challenges: Taking Over inspection to be scheduled
30 |  | St. Elizabeth | Munro College |  | 137743857.34 | 44241490.64 | Replacement of roof with reinforced concrete slab and renovation to Coke Building Replacement of roof to Biology Lab Repair of Guidance Office ceiling and minor repair to roof Repair of water tank covers at Hostel Facility as per Standard Building Code | 1 | NET | Denron Engineering | 1 | Approval granted | 2025-12-01 | 2026-06-16 | 95% - 99% ; practical completion | Project Percentage Completion: 95% Replacement of Roof on Coke Building - 100% Installation of ceiling on Coke Building - 100% Installation of classroom wall partitions on Coke Building - 100% Electrical works for Coke Building - 100% Finishing of classroom wall partitions on Coke Building - 95% Replacement of windows and doors on Coke Building - 100% Replacement of Biology Lab Roof - 100% Installation of ceiling in Biology Labs - 100% Restoration of Biology Labs fixtures and finishes - 90% Resheeting and frame repair of water tanks at Hostel - 100% Replacement of ceiling at Guidance Office - 100% Proposed Project Completion Date: September 2026 Comments/Issues:/Challenges: Taking Over inspection to be scheduled
31 |  | St. Elizabeth | Sandy Bank Infant | 20000000 |  |  | Repairs to damaged roof of main classroom block as per Standard Building Code | 1 | NET | Maxwell Construction | 2 | 2026-01-05 |  |  | Contractor to be given site possession | Project Percentage Completion: 0% Procurement/Donor - Design & Build engagement or Donor support to be initiated Proposed Project Completion Date: TBD Issues:/Challenges: Modular solution to be provided by a Donor. Technical Team finalising the scope for supporting infrastructure works to enable the contract
32 |  | St. Elizabeth | Black River Primary and Infant |  | 564829194.56 |  | Repairs to roof of main classroom blocks as per Standard Building Code. Replacement of windows and doors, repairs to sanitary block and fencing. | 1 | NET | Proven Construction | 1 | Approval granted | 2026-02-18 | 2026-08-17 | 80% - 94% ; work in progress | Works commenced February 23, 2026 Overall Project Percentage: 85% Progress: 1. General Re-Roofing works- 90% 2. Door installation- 90% 3. Painting works to walls and ceilings underway 4. General electrical works Grades 2-6, computer rooms, reading room electrical completed 5. Finishes to admin office- completed 6. Chain-Link fence- 85% Upcoming Events: 1. Installation of plumbing fixtures 2. General painting works 3. Electrical works Issues: 1. Continuous rainfall 2. Unavailability of key materials 3. Active learning environment Resolution: N/A
33 |  | St. Elizabeth | Brompton Primary |  | 168080714 | 50415249.66 | Reconstruction of the Infant Block, repair damaged roofs on all the affected buildings at the primary school. Construction of a reinforced roof slab on the canteen block as per Standard Building Code | 1 | NET | HDB Construction | 1 | Approval granted | 2026-02-10 | 2026-08-09 | 51% - 60% ; work in progress | Project Percentage Completion: 55% Proposed Project Completion Date: December 31, 2026 Project Status: Infant Block – 85% Library – 10% Rest Room – 70% Building A – 50% Building B – 10% Building C – 0% Canteen – 50% Issues:/Challenges: • Payment delays. • The contractor's progress is very slow in general. • Additional items of work were added to the scope. • Repair works may not be completed in time for next school year.
34 |  | St. Elizabeth | Crawford Primary and Infant |  | 52130988 | 9774882.15 | Re-roofing repairs to single-storey classroom block and replacement of windows to administrative block as per Standard Building Code | 1 | NET | Build Rite | 2 | Originally assigned to T.S.U. Re-assigned to N.E.T | 2026-03-23 | 2026-09-22 | 51% - 60% ; work in progress | Works commenced on March 23, 2026 Overall Project Percentage: 60% Food for the Poor completed the infant department. Progress: 1 Installation of roof slab to tuck shop: on-going 90%
35 |  | St. Elizabeth | Fullerswood Primary and Infant |  | 57454455.5 | 22414410.95 | Re-roofing repairs to Infant department, Principals Office Main building and Restrooms. Removal of damaged whiteboard and Installation of new white boards. Replace doors installation of chain-link fence and gate, painting and electrical works as per Standard Building Code | 1 | NET | HDB Construction | 1 | Approval granted | 2026-02-11 | 2026-08-10 | 80% - 94% ; work in progress | Project Percentage Completion: 90% Proposed Project Completion Date: September 30, 2026 Project Status: Infant School: final finishes to be completed by this weekend; 90% complete. For the Primary School: translucent sheeting and ridge capping to be installed. Issues/Challenges: Difficulty securing the correct size translucent sheeting
36 |  | St. Elizabeth | Fyffes Pen Primary and Infant |  | 304767100 |  | Repairs to damaged roof of main classroom block of Primary School and roof repairs to the Infant Department as per Standard Building Code | 1 | NET | Southern Contracting Company | 1 |  | 2026-05-21 | 2026-12-31 | 21% - 40% ; work in progress | Works commenced May 2026 Overall Project Percentage: 35% Progress: 1. Roughcast and Render columns 50% completed. 2. Reroute hoarding to specified sections to accommodate School opening for September 100% completed. 3. Application of 2 coats of emulsion paint to the canteen and bathroom 100% completed. 4. Block A stripping of formwork from roof slab 100% completed. 5. Roughcast underside of cantilever 100% completed 6. Roughcast Blackwall. 100% completed. 7. Installation of water closets 100% completed 8. Demolish counter and cupboard in the Canteen.100% completed 9. Casting of temporary staircase to access lavatories. 100% completed. Upcoming Events: 1. Installation of doors and fitting to the canteen and bathroom. 2. Remove damage doors and fittings from canteen. 3. Electrical works in block A, canteen, and bathroom. 4. Chain link fence completion. Issues: N/A Resolution: N/A
37 |  | St. Elizabeth | Geneva Primary |  | 20358500 |  | Re-roofing and ceiling repairs to main classroom block to include structural steel repair works as per Standard Building Code | 1 | TSU | Maxwell Construction Limited | 2 | Approval granted | 2026-01-09 | 2026-03-09 | Work Completed
38 |  | St. Elizabeth | Hopewell Primary |  |  |  | Re-roofing and ceiling repairs to the two (2) storey main classroom block and repairs to roof of student bathroom block as per Standard Building Code | 1 | DONOR | Clare Lionel Foundation |  |  |  |  | 41% - 50% ; work in progress | Project Percentage Completion: 46% Proposed Project Completion Date: Project Status: Continuing the pour for the concrete walls for the ground floor of the main building 46%. The guardhouse and electrical room were cast. Formwork is being prepared for casting of the upper floor of the main building. Work for next period: Work to commence pouring of the upper floor and finish works on the lower floor, guardhouse and electrical room. Issues:/Challenges:
39 |  | St. Elizabeth | Middle Quarters Primary |  | 125619901 | 25822165.54 | Repairs to roof of the Infant and Primary Department and student bathroom as per Standard Building Code | 1 | NET | HDB Construction | 1 | Approval granted | 2026-02-09 | 2026-08-08 | 41% - 50% ; work in progress | Project Percentage Completion: 50% Proposed Project Completion Date: December 31, 2026 (Awaiting formal request of EOT from the contractor) Project Status: Block A – 90% Block B– 0% Block C – 90% Block D – 90% Bathroom – 90% Fencing – 90% D+ B TOR is being assessed Issues:/Challenges: • Payment delays. • The contractor's progress is very slow in general. • Existing nag building is to be demolished and a new building constructed in it s place. Rebuild of classroom block to be undertaken.
40 |  | St. Elizabeth | Mountainside Primary |  | 48260618 |  | Repairs to roof of main classroom as per Standard Building Code | 1 | TSU | Southern Contracting Company | 1 | 2026-08-03 | 6 weeks | 2026-09-04 | 61% -79% ; work in progress | Awaiting approval Memo from TSU
41 |  | St. Elizabeth | Newcombe Valley Primary |  | 31285550 | 14934300 | Re-roofing and ceiling repairs to the main classroom block as per Standard Building Code | 1 | TSU | Maxwell Construction Limited | 2 | Approval granted | 2026-01-09 | 2026-03-09 | Work Completed | Part Payment made
42 |  | St. Elizabeth | Parottee Primary |  | 84984000 | 56534083.86 | Re-roofing and ceiling repairs to the main classroom block and student bathroom as per Standard Building Code | 1 | NET | K& R & Associates |  |  | 2026-05-06 | 2026-11-05 | 61% -79% ; work in progress | Works commenced March 9, 2026 Overall Project Percentage: 75% Progress: 1. Electrical works complete 2. Roofing works complete 3. Ceiling works complete 4. Partition works complete Upcoming Events: 1. Fencing works 2. Painting works Issues: N/A Resolution: N/A
43 |  | St. Elizabeth | Pondside Primary |  | 152921879.19 |  | Replacement of classroom block roof with reinforced concrete slab roofing inclusive of structural modification to columns and beams to support new roof system as per Standard Building Code | 1 | NET | J&H Construction | 1 | Approval granted | 2026-01-26 | 2026-10-31 | 61% -79% ; work in progress | Project Percentage Completion: 75% Proposed Project Completion Date: October 2026 (Awaiting formal request of EOT from the contractor) Project Status: Painting of block All electrical works, painting and masonry work was completed on Block A. Electrical works have commenced at Block B on September 16 Installation of white boards for Block B will also commence on September 16. Issues:/Challenges: Number of masons need to increase in order to complete Block B.
44 |  | St. Elizabeth | Sandy Bank Primary |  |  |  | Re-roofing and ceiling repairs to administrative block as per Standard Building Code | 1 | DONOR | [5 empty] | 80% - 94% ; work in progress | German Government. Donor to execute the project
45 |  | St. Elizabeth | Slipe Leased Primary and Infant |  | 115162175 | 24461760 | Re-roofing of existing classroom blocks for Grades 1-4, installation of partitions, and replacement of the classroom block for Grades 5-6 roof with reinforced concrete slab roofing, inclusive of structural modification to columns and beams to support the new roof system, electrical works, installation of fencing to the Infant Department as per Standard Building Code | 1 | NET | chins Equipment & rental | 1 | Approval granted | 2026-04-23 | 2026-10-20 | 61% -79% ; work in progress | Project Percentage Completion: 77% Proposed Project Completion Date: October 17, 2026 for the Primary School and September 30, 2026 for the Infant School. Project Status: The ceiling works, installation of fans, and painting for the Infant Department have been completed. The installation of drywall for the resource room is scheduled to occur during the week of September 21. Regarding the Primary School, the decking for the Grade 6 Block has been successfully cast, and the parapet wall has been completed. The ceiling finishes are approximately 75% complete, while the wall finishes have reached 60% completion. Issues:/Challenges: Local labour shortages.
46 |  | St. Elizabeth | Black River High |  | 368884926 | 107293206.12 | Re-roofing and electrical repairs of Classroom Blocks, nurse's station, guidance department, administrative office, canteen/tuck, auditorium. Reconstruction of abattoir, reconstruction of the external fencing as per Standard Building Code | 1 | NET | Pavecon | 1 | Approval granted | 2026-07-03 | 2027-01-01 | 51% - 60% ; work in progress | Overall Project Percentage: 51% Progress: 1. Pouring of Block A 2. 95% of roof membrane works finished 3. Changing out purlins for auditorium 4. Gazebo and guard house 40% Upcoming Events: 1. Erection of framework for Principal's Office 2. Erection of framework for Nurse's station 3.Erection of chicken pen Issues: N/A
47 |  | Manchester | Ferguson Primary and Infant |  | 22686976 | 8971750 | Re-roofing and ceiling repairs to the main two (2) storey classroom block as per Standard Building Code | 1 | TSU | Velka Construction | 3 | Approval granted | 2026-01-19 | 2026-03-09 | Work Completed | Part payment made. Final payment documents submitted.
48 |  | Manchester | Grove Town Primary and Infant |  | 40272440 | 12841420 | Re-roofing & renovation work to main classroom block as per Standard Building Code | 1 | TSU | Southern Contracting Company | 1 | Approval granted | 2026-01-12 | 2026-03-10 | Work Completed | Second payment made; Completion to works delayed by severe weather.
49 |  | Manchester | Bishop Gibson High |  | 28767346.07 |  | Roofing and ceiling repairs to the Annex Block (Block C), Administrative Block (Block A) and Block B as per Standard Building Code | 1 | TSU | Denron Engineering | 1 | Approval granted | 2026-02-02 | 2026-04-29 | Work Completed | Second payment made. Final payment documents being prepared.
50 |  | Manchester | Manchester High |  | 91425000 | 52938319.7 | Re-roofing and ceiling repairs to third form classroom block, sixth form and second form classroom blocks as per Standard Building Code | 1 | NET | Pavecon | 1 | Approval granted | 2026-02-02 | 2026-08-03 | Work Completed | Works completed
51 |  | Manchester | Comfort Hall Primary and Infant |  | 23798100 | 13668208 | Re-roofing & renovation work to main classroom block as per Standard Building Code | 1 | TSU | J. Neil Construction | 3 | Approval granted | 2026-01-12 | 2026-03-10 | Work Completed | Second payment submitted; Completion to works delayed by severe weather.
52 |  | Manchester | New Green Primary and Infant |  | 36019410 |  | Re-roofing and ceiling repairs to Blocks A and B | 1 | TSU | Dutch Construction Limited | 3 | Approval granted | 2026-02-11 | 2026-03-24 | Work Completed | Part payment made. Completion to works delayed by severe weather.
53 |  | Manchester | St. Paul's Primary and Infant |  | 22850000.12 | 19287755.52 | Re-roofing and ceiling repairs to the main classroom block as per Standard Building Code | 1 | TSU | Cambridge Trading Limited | 3 | Approval granted | 2026-01-12 | 2026-03-10 | Work Completed | Part payment made. Final payment documents being prepared.
54 |  | Manchester | Mile Gully High |  | 41050060 | 15853190 | Re-roofing & ceiling repairs to the main two (2) storey classroom block and Grade 9 Classroom block as per Standard Building Code | 1 | TSU | Southern Contracting Company | 1 | Approval granted | 2026-01-12 | 2026-03-10 | Work Completed | Second payment submitted; Completion to works delayed by severe weather.
55 |  | Manchester | Bryce Primary | 26131000 | 47194350 | 34025210.5 | Re-roofing and ceiling repairs to the two (2) storey lightweight administrative block to include structural repairs. Re-roofing and ceiling repairs to Block D to include structural repairs as per Standard Building Code | 1 | NET | Cenitech | 1 | Approval granted | 2026-04-08 | 2026-11-07 | Work Completed | Work completed
56 |  | Manchester | Chantilly Primary |  | 55034035 |  | Grade 5/6 Block is to be demolished and replaced by a new building . Modification of sections of the main classroom block to provide space for guidance councillor, sick bay and additional classroom as per Standard Building Code | 1 | NET | K& R & Associates | 1 |  |  |  | Work to Commence | Project Percentage Completion: 0% Proposed Project Completion Date: January 31, 2027 Comments/Issues/Challenges: Two temporary structures are scheduled for erection, following the retraction of the design-build component. The contractor submitted a revised bid during the week of September 7, which has been forwarded to the technical team for formal review.
57 |  | Manchester | Christiana Moravian Primary and Infant |  | 18646860 | 17046860 | Re-roofing and ceiling repairs to the two (2) storey administrative block as per Standard Building Code | 1 | TSU | Duke's Electrical and Building Solution | 2 | Approval granted | 2025-12-29 | 2026-02-24 | Work Completed | Part payment made amounting to $13,634,905.00. Final payment documents submitted.
58 |  | Manchester | Craighead Primary |  | 23229700 | 11857300 | Re-roofing & ceiling repairs to main classroom block and Canadian-style block as per Standard Building Code | 1 | TSU | Duke's Electrical and Building Solution | 2 | Approval granted | 2025-12-29 | 2026-02-24 | Work Completed | Part payment made amounting to $11,857,300.00; Final payment document being prepared.
59 |  | Manchester | Mizpah Primary |  | 22975995 | 12215500 | Roofing and ceiling repairs to the main classroom block as per Standard Building Code | 1 | TSU | Velka Construction | 3 | Approval granted | 2026-01-09 | 2026-03-09 | Work Completed | Part payment made; Final payment document being prepared.
60 |  | Manchester | Pike Primary and Infant |  | 53748500 | 25242928.33 | Re-roofing and electrical repairs of classroom block as per Standard Building Code | 1 | NET | Slyvester Enterprise | 1 | Approval granted | 2026-03-23 | 2026-09-22 | 80% - 94% ; work in progress | Project Percentage Completion: 90% Resheeting:100% Electrical: 100% Painting: 100% Window: 0% Door: 100% Proposed Project Completion Date: August 2026 Works done in the week of the current period: Painting and electrical work complete Works to be done in next period : 1.window installation to commence 2. boxed eave at section of canteen Issues:/Challenges: VO be to include additional painting and window installation being reviewed and contractor making changes to cost proposal as advised. School conducting construction which is hindering the contractor's progress on boxed eaves activities. Email written to school.
61 |  | Manchester | Robins Hall Primary and Infant | 37917420 |  |  | Re-roofing and ceiling repairs to the Infant Department as per Standard Building Code | 1 | NET | Dwight's Construction | 1 |  |  |  | 20% & Below ; work in progress | Project Percentage Completion: 15% Repair Roof: 10% Electrical:0% Interior renovation and partition :0% Floor:0% Proposed Project Completion Date: October 2026 Project Status: Contractor restart work. Works done in the week of the current period: Beam Construction commenced Works to be done in next period: Roof Repair: Belt Beam construction Issues:/Challenges: Documents still outstanding for contractor. No contract in place.
62 |  | Manchester | Holmwood Technical High |  | 367429570.08 | 151376714.9 | Re-sheeting and associated electrical repairs of auditorium, administrative block, Jordan block, Industrial/ Technical block and rebuilding of Barnes Hall and the dormitory facilities as per Standard Building Code | 1 | NET | C&D Construction | 1 | Approval granted | 2026-02-10 | 2026-08-09 | 80% - 94% ; work in progress | Project Percentage Completion: 85% Proposed Project End Date: October 2026 Works done in the week of the current period: 1. Auditorium: Fans installed 2. Admin Block: Ceiling work in progress 3.Technical Block: Ceiling 100% Sheeting in progress 4. Jordan Block: Ceiling 100% Sheeting in progress 5. Associated electrical work commence Works to be done in next period: 1. Auditorium : one Fan outstanding, fascia board to installed and painted, electrical 2. Administrative Block: Ceiling work in progress 3. Revised Work Schedule to be submitted by Contractor 4. Technical Block: Sheeting in progress 5. Jordan Block: Sheeting complete Associated electrical work to continue Issues/ Challenges: Admin Ridge joints to be sealed. Site organisation to be addressed. Ply- Cem/ Material shortage. Classrooms can accommodate classes for the September 7 deadline considering outstanding activities. For design and build: A meeting was held with the school and the contractor. The contractor presented Dorm proposal. The contractor will complete the required Surveyors ID report to inform the development of the design. **Electrical Upgrade: Justification submitted to procurement -communication in progress**
63 |  | Manchester | Knox Community College (Cobbla Campus) |  | 336884425 | 26049618.09 | Repairs to 17 buildings on the campus in 2 phases [Domes, Administration Block, Engineering (TD), Electrical Technology Dept, Mechanical & Construction, Sporting Pavillion, Canteen/Auditorium] as per Standard Building Code | 1 | NET | Lottis Project Limited |  |  | 2026-02-09 | 2026-08-09 | 21% - 40% ; work in progress | Project Percentage Completion: 25% PHASE 1: Canteen/Auditorium 80% - Mechanical & Construction and Administration Blocks - 10%. Engineering Block: 80% Nurses Station 10% Student resident 80% Proposed Project Completion Date: Project Status: Contract issued on June 17, 2026. Issues:/Challenges:
| TOTAL |  |  | 371478471.1 | 6796922103.25 | 1725814594.96
Formulas:
Contract End Date = [Contract Start Date]+180

## REGION 6
POST-HURRICANE ASSESSMENT DATA ― IMPACT OF HURRICANE MELISSA ON SCHOOLS' INFRASTRUCTURE
No of Schools | Region | Parish | Name of School | Preliminary Cost $ | Contract Sum $ | Expenditure to Date $ | Scope of Works | PRIORITY 1. Severely Damaged - may affect school reopening. 2. Moderately Damaged - Significant repairs. School can operate while repairs are done. 3. Minor Damage - school can operate while repairs are done. | Person Responsible (TSU , NET, JSIF , DONOR) | Name of Contractor Assigned | Contractor Grade | Projected Date of Procurement for PS Approval | Contract Start Date | Contract End Date | Status | Remarks
1 | 6 | St. Catherine | Top Hill Primary |  | 47256565 |  | Repairs to the following facilities: Main Classroom Block Grades 5/6 Classroom Kitchen Corridor, Bathroom External Works: - collapsed pit slab - construct wall at Infant Department As per Standard Building Code | 1 | NET | Dwight's Construction | 1 |  |  |  | 61% -79% ; work in progress | Project Percentage Completion: 75% Main Classroom Block -50% Grades 5/6 Classroom -70 % Kitchen - 60% Corridor, Bathroom - - 5% External Works - 0% - collapsed pit slab - construct wall at Infant Dept Proposed Project Completion Date: October 31, 2026 Comments/Issues:/Challenges: None
2 |  | St. Catherine | Rosemount Primary and Infant |  | 42947500 | 16060800 | Emergency Waterproofing of Reinforced Concrete Roofs: Canteen Block and Administrative Block as per Standard Building Code | 1 | TSU | Dukes Electrical & Construction | 2 | Approval granted | 2026-01-12 | 2026-09-04 | 95% - 99% ; practical completion | Final account to be prepared
3 |  | St. Catherine | McGrath High |  | 70693036 |  | Waterproofing of the administrative block and Re-sheeting of Roofs at Canteen Block, Construction of roof Slab at Principal Block, Repairs to Metal Tank & Chain-link Fence as per Standard Building Code | 1 | TSU | Cambridge Trading Limited | 3 | 2026-01-27 | 2026-02-16 | 2026-09-30 | 80% - 94% ; work in progress | Work in progress
4 |  | St. Catherine | Southborough Primary |  | 27996000 | 24370875 | Proposed Emergency Waterproofing of Blocks 1-4 Reinforced Concrete Roofs as per Standard Building Code | 1 | TSU | Duke's Electrical & Building Solutions | 2 | 2026-01-27 | 2026-02-16 | 2026-05-15 | Work Completed | Final account to be prepared
5 |  | St. Catherine | Dinthill Technical High |  | 52947890 |  | Proposed Re-Sheeting of Roofs: Engineering Block, Grade 8 Block, Block N, Classroom Gazebo, Agriculture block and Replacement of windows of Administration Block as per Standard Building Code | 1 | TSU | Tropical Metal Products Ltd. | 1 | Approval granted | 2026-01-23 | 2026-09-18 | 95% - 99% ; practical completion | Final account to be prepared
6 |  | St. Catherine | The Enid Bennett High |  | 45223504 |  | Removal of raw sewage from septic tank & Absorption pit as per Standard Building Code | 1 | TSU | THLC | 2 | 2026-01-27 | 2026-02-16 | 2026-09-18 | 95% - 99% ; practical completion | Final account to be prepared
7 |  | St. Catherine | Marlie Hill Primary and Infant | 40000000 |  |  | Construction of retaining wall on boundary of school premises adjacent to parochial road as per Standard Building Code | 1 | NET | M&M Construction | 1 |  |  |  | Contractor to be given site possession | Project Percentage Completion: 0% Comments/Issues:/Challenges: The Letter of Award was issued to the contractor on September 3, 2026. Following this, the contractor refused to commence works regarding concerns of outstanding funds from a previous project.
8 |  | St. Catherine | Garden Hill Primary and Infant |  | 23080660 | 9047200 | Repairs to Roofs of Administrative and Canteen Block as per Standard Building Code | 1 | TSU | HT Roofing & Construction Limited | 3 | Approval granted | 2026-01-12 | 2026-04-10 | Work Completed | Final account to be prepared
9 |  | St. Catherine | Ginger Ridge Primary |  | 23032450 | 15312950 | Proposed Re-Sheeting & Waterproofing of Roofs as per Standard Building Code | 1 | TSU | HT Roofing & Construction Limited | 3 | Approval granted | 2026-01-20 | 2026-09-04 | 95% - 99% ; practical completion | Final account to be prepared
10 |  | St. Catherine | Guys Hill Primary | $94,700,000 Phase 1: $37,500,000 |  |  | Repairs to roofs on 3 buildings Phase 1 Reinforced concrete block Steel frame building Phase 2 Replacement of main classroom block with nog walls as per Standard Building Code | 1 | NET | Build Rite Construction |  |  |  |  | Contractor to be given site possession | Project Percentage Completion: 0% Comments/Issues:/Challenges: The Bid was received on September 11, 2026 and was sent to the technical team to be reviewed. An official response from the technical team is to be submitted to the procurement unit on Friday, September 25, 2026
11 |  | St. Catherine | Hamwalk Primary and Infant |  | 59150750 | 25316250 | Repairs to roofs of Canteen Block, Administrative Block, Auditorium Block as per Standard Building Code | 1 | TSU | Geeho Consultant & Construction Limited |  | 2026-01-27 | 2026-02-16 | 2026-09-04 | 95% - 99% ; practical completion | Final account to be prepared
12 |  | St. Catherine | Redwood Primary |  | 12466601 |  | Repairs to roof of Library Block as per Standard Building Code | 1 | TSU | J'Neil Construction | 3 | Approval granted | 2026-01-12 | 2026-08-07 | Work Completed | Final account to be prepared
13 |  | St. Catherine | Gregory Park Primary |  | 23994862 |  | Re-Sheeting of Administrative Roof Block as per Standard Building Code | 1 | TSU | HT Roofing & Construction Limited | 3 | Approval granted | 2026-01-15 | 2026-09-04 | 95% - 99% ; practical completion | Final account to be prepared
14 |  | St. Catherine | Naggo Head Primary |  | 48064542 | 12783413 | Waterproofing and Re-sheeting of Roofs, Repairs to Student Sanitary Facilities & Construction of Corridor Way as per Standard Building Code | 1 | TSU | Duke's Electrical & Construction | 2 | Approval granted | 2026-01-26 | 2026-09-04 | 95% - 99% ; practical completion | Final account to be prepared
14 | TOTAL |  |  | 40000000 | 429597795 | 102891488

## REGION 7
POST-HURRICANE ASSESSMENT DATA ― IMPACT OF HURRICANE MELISSA ON SCHOOLS' INFRASTRUCTURE
No of Schools | Region | Parish | Name of School | Preliminary Cost $ | Contract Sum $ | Expenditure to Date $ | Scope of Works | PRIORITY 1. Severely Damaged - may affect school reopening. 2. Moderately Damaged - Significant repairs. School can operate while repairs are done. 3. Minor Damage - school can operate while repairs are done. | Person Responsible (TSU , NET, JSIF , DONOR) | Name of Contractor Assigned | Contractor Grade | Projected Date of Procurement for PS Approval | Contract Start Date | Contract End Date | Status | Remarks
1 |  | Clarendon | Central High |  | 131252956.53 |  | Repairs to 4 blocks: Dormitory Grade 9 Grade 10 Administration Block As per Standard Building Code | 1 | NET | Chins Construction | 1 | Approval granted | 2026-08-10 | 2027-02-06 | 20% & Below ; work in progress | Project Percentage Completion: 17% Proposed Project Completion Date: February 2027 Comments/Issues:/Challenges: Contractor resumed duties in August and is currently working on the temporary facilities. Works on temporary facility is expected to conclude mid September 2026
2 |  | Clarendon | Alphansus Davis High (Spalding High) |  | 166627650 | 23641670.37 | Roof repairs for 5 facilities: * Water tank roof (wood to concrete) * Roof of Administration Bldg. * Poultry House * CAPE Block * Agricultural Science Block As per Standard Building Code | 1 | NET | Lottis Projects | 1 | Approval granted | 2026-04-08 | 2026-10-05 | 80% - 94% ; work in progress | Project Percentage Completion: 92% Proposed Project Completion Date: October 2026 Status: Water Tank - 100% Admin Bldg. - hording, 50% ; roof, 0% Poultry House - 90% CAPE & Agricultural Blocks - Schematic designs sent to stakeholders for feedback Proposed Project Completion Date: October 2026 Comments/Issues:/Challenges: Contractor slipping behind schedule. Remedy: Weekly virtual meeting to track progress
3 |  | Clarendon | Edwin Allen High |  | 270112200 | 72243249.8 | Repairs to 14 blocks/bldgs.: * Gr 7 Block * Gr 8 Bldg. * Agricultural Block * Guidance Councillor * Chemical Storeroom * Staffroom * Agric Classroom * Admination Block * Science Block/Block D * Block E * Old Auditorium * Auditorium Kitchen * Tuck Shop #1 As per Standard Building Code | 1 | NET | Chins Equipment & Rental | 1 | Approval granted | 2026-04-16 | 2026-10-13 | 80% - 94% ; work in progress | Project Percentage Completion: 85% Status: Project on track; walkthrough date for practical completion to be finalized with the contractor in the week of September 20, 2026 Proposed Project Completion Date: October 13, 2026 Comments/Issues:/Challenges: None
4 |  | Clarendon | Knox College | 100000000 | 319957457 | 21905830.76 | Repairs to 8 blocks/bldgs.: Phase 1 Nurses' Station Hostel Science Block Phase 2 Lewis Davidson Hall Library/Computer Lab Barbara Jones Auditorium Phase 3 Maintenance Office/Basketball Shed Humanities Block As per Standard Building Code | 1 | NET | Lottis Projects | 1 | Approval granted | 2026-06-22 | 2026-12-19 | 21% - 40% ; work in progress | Project Percentage Completion: 40% Phase 1 is currently in progress: Nurses' Station - 60%; Hostel - 60%; Science Block - 10% (demolition complete) Proposed Project Completion Date: December 2026 Comments/Issues:/Challenges: Delay on Science Block as a result of structural design concern
5 |  | Clarendon | Anderson Town Primary and Infant |  | 28596397 | 29789175 | Renovation of Classroom Blocks to include Electrical Upgrading, Tiling and Pest Control Treatment as per Standard Building Code | 1 | TSU | Britalex Construction | 2 | Approval granted | 2025-12-31 | 2026-03-06 | Work Completed | Final account submitted
6 |  | Clarendon | Bunkers Hill Primary and Infant |  | 23962229 | 13972310 | Repairs to Roof of Classroom Blocks to include upgrading of Electrical System as per Standard Building Code | 1 | TSU | HT Roofing & Construction Limited | 3 | Approval granted | 2025-12-28 | 2026-08-07 | Work Completed | Final account being submitted
7 |  | Clarendon | Trout Hall Primary and Infant |  | 12132009 | 10470943 | Repairs to Roof of Classroom Blocks, Cottages and Upgrading of Electrical System s per Standard Building Code | 1 | TSU | J. Niel Construction | 3 | Approval granted | 2025-12-28 | 2026-03-10 | Work Completed | Final account submitted
8 |  | Clarendon | Clarendon College | 330439400 | 330439440 | 36289899.1 | Repairs to 10 blocks/bldgs.: Tuckshop Tuckshop Storage Home Economic Lab Principal's Cottage Auditorium Computer Lab Staff Room #1, 1st/2nd Form Block Admin Bldg. Gym/Dormitory As per Standard Building Code | 1 | NET | Southern contracting Com Ltd. | 1 | Approval granted | 2026-06-22 | 2026-12-21 | 41% - 50% ; work in progress | Project Percentage Completion: 45% Home Econ Lab - 90%; Admin Block - 100%; Grades 7/8 Block - 15%; Proposed Project Completion Date: December 2026 Comments/Issues:/Challenges: Noone
9 |  | Clarendon | Main Ridge Primary |  | 11361490 | 8254990 | Repairs to Roofs of Classroom Blocks to include Upgrading of Electrical System as per Standard Building Code | 1 | TSU | J. Niel Construction | 3 | Approval granted | 2025-12-28 | 2026-02-09 | Work Completed | Payment amounting to sum of $8,254,990.00 submitted to Project Accounts. Final account being prepared, defects Identified and being corrected
10 |  | Clarendon | Knox Community College (Spalding) |  | 200095550 | 24412807.53 | Repairs to 7 blocks/bldgs.: Phase 1 Computer Lab/Staffroom, Canteen/Operations & Management Office Education & Liberal Studies Bldg. Phase 2 Registry Bldg. Maths Dept, Villa 1 Villa 2 As per Standard Building Code | 1 | NET | Skymar | 1 | Approval granted | 2026-08-28 | February 29, 2027 | 21% - 40% ; work in progress | Project Percentage Completion: 30% Proposed Project Completion Date: February 2027 Status: Works ongoing Comments/Issues:/Challenges: None,
11 |  | Clarendon | Windsor School of Special Education- Denbigh |  | 5909900 | 5435100 | Repairs to Roof of Classroom Blocks to include Upgrading of Electrical System as per Standard Building Code | 1 | TSU | Lesclar Synergy Co-Company Limited | 3 | Approval granted | 2025-12-28 | 2026-08-14 | Work Completed | Practically completed. Contractor addressing defects
11 | TOTAL |  |  | 430439400 | 1500447278.53 | 246415975.56
Formulas:
Contract End Date = [Contract Start Date]+180